## WP1
Makhuduthamaga Local Municipality
Mr Moganedi RM
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address
Procurement Plan 2022/23
Estimates Dates
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ref. No. | Description | VOTE | Type | Contract Number | No. of deliverables | Estimated Cost (R)/ Budgeted Amount |  |  | Method of Procurement | Source of Funding | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | PROGRESS AS AT 30TH SEPTEMBER 2022
[6 empty] | Total Funding | Government Grants & Subsidies | Own revenue |  |  | Advertising | Closing Bid | Appointments
KPA 2: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
BS01 | Construction of road from Mashabela Tribal office to Machacha (5.5km) PH2 |  |  |  |  | 20500000 | 20500000 | 0 | OT | ES | 2022-08-01 | 2022-09-01 | 2022-10-01 | Multiyearly funded Project
BS02 | Construction of road from Mokwete to Molepane /Ntoane(10km) |  |  |  |  | 18000000 | 18000000 | 0 | OT | ES | 2022-08-01 | 2022-09-01 | 2022-10-01 | Multiyearly funded Project
BS04 | Construction of access road from Glen Cowie Old Post Office to Phokwane (7km) |  |  |  |  | 15000000 | 15000000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised, Closed and Evaluated
BS06 | Construction of Mamone Internal Road |  |  |  |  | 10000000 | 10000000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS10 | Upgrading of sports facility phase 2 (Marishane sports facility |  |  |  |  | 5000000 | 5000000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS11 | Construction of Malegase to Mapulane access road and bridge (3,5Km) |  |  |  |  | 11976000 | 11976000 | 0 | OT | MIG | 2022-08-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS12 | Construction of Mochadi road and bridge (2.9km) |  |  |  |  | 21470000 | 21470000 | 0 | OT | MIG | 2022-08-01 | 2022-09-01 | 2022-10-01 | Advertised, Closed ,Evaluated , Adjudicated and Appointed
BS15 | Construction of access road from Jane Furse RDP to Mogorwane(5.8Km) |  |  |  |  | 550000 | 550000 | 0 | OT | MIG | 2022-08-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS16 | Construction of Access road and bridge from Makgeru Moshate to Mantime Primary School(0.85Km) |  |  |  |  | 11080000 | 11080000 | 0 | OT | MIG | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised, Closed and Evaluated
BS17 | Construction of Access road from Mohlala Mamone to R579 (1.2Km) |  |  |  |  | 8404000 | 8404000 | 0 | OT | MIG | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS18 | Construction of Access road from Mathapisa to Soetveld (6kM) |  |  |  |  | 500000 | 500000 | 0 | OT | ES | 2022-08-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS19 | Construction of Manyeleti to Mamone central access road(2.6Km) |  |  |  |  | 15949000 | 15949000 | 0 | OT | MIG | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised, Closed ,Evaluated , Adjudicated and Appointed
BS20 | Construction of access road from Masemola Moshate to Mohloding/Mamatjekele (10km) |  |  |  |  | 500000 | 500000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS21 | Construction of Access Road from Motor-gate Wonderboom to R579 (10km) |  |  |  |  | 500000 | 500000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS22 | Rehabilitation of access road at Hlalanikahle |  |  |  |  | 5000000 | 5000000 | 0 | OT | ES | 2022-07-01 | 2022-09-01 | 2022-10-01 | Advertised and Closed
BS24 | Electrification of Dihlabaneng (Ngwanakwena and Malatjane) |  |  |  |  | 6000000 | 6000000 | 0 | OT | INEP | 2022-10-01 | 2022-10-01 | 2022-11-01 | Advertised and Closed
BS25 | Installation of High mast lights |  |  |  |  | 3500000 | 3500000 | 0 | OT | ES | 2022-07-01 | 2022-07-01 | 2022-08-01 | Advertised and Closed
BS40 | Fire Arms |  |  |  |  | 200000 | 200000 | 0 | OT | ES | 2022-10-01 | 2022-10-01 | 2022-11-01 | Advertised and Closed
[6 empty] | 154129000 | 154129000 | 0
| Infrastructure Assets Sub-Total |  |  |  |  | 154129000 | 154129000 | 0