# MLM APPROVED 2019/20 IDP/Budget

## SC/10/05/2019

|  | TABLE OF CONTENTS |  |
| --- | --- | --- |
| 1. | Chpater 1:Context and overview | 06 |
| 1.1 | Context and overview | 06 |
| 1.2 | Vision and Mission | 07 |
| 2 | Chapter 2:Executive Summary | 08 |
| 2.1 | Introduction | 08 |
| 2.2 | Legislative background /contect | 08 |
| 2.3 | Policy context | 10 |
| 2.4 | Powers and functions | 21 |
| 2.5 | Basis for IDP review Process | 23 |
| 2.6 | Institutional arrangements for IDP process and implementation | 25 |
| 2.7 | Process overview:Steps and events | 25 |
| 2.8 | Outcomes of the IDP Community consultations meetings | 33 |
| 3 | Chapter 3:Situational analysis | 79 |
| 3.1 | Introduction | 79 |
| 3.2 | Spatial rationale | 87 |
| 3.3 | Basic Service Delivery and Infrastructure Development | 113 |
| 3.4 | Local Economic Development (LED) | 198 |
| 3.5 | Financial Viability | 216 |
| 3.6 | Good Governance and Public Participation | 244 |
| 3.7 | Municipal Transformation and Organisational Development | 262 |
| 4 | Chapter 4:Strategies Phase | 273 |
| 5 | Chapter 5:Projects Phase | 287 |
| 6. | Integration Phase | 353 |
| 7. | Annexure A :Draft Budget Summary 2019/20-2021/22 and Draft Organisational Structure | 359 & 376 |

LIST OF ACRONYMS

AC 	: Audit Committee

AFS	: Annual Financial Statements

AG	: Auditor General

AIDS	: Acquired Immune Deficiency Syndrome

ANC 	: African National Congress

APSP   : African People’s Socialist Party

AZAPO: Azanian People’s Socialist

B2B        : Back to Basics

BTO      : Budget and Treasury Office

CASP: Comprehensive Agricultural Support Program

CBO       : Community Based Organisation

CDG      : Care Dependency Grant

CGIS   : Corporate Geographic Information System

CS      : Community Survey

CSG     : Child Support Grant

CAPEX: Capital Expenditure

CWP	: Community Works Programme

CRDP   : Comprehensive Rural Development Programme

COGTA: Cooperative Governance and Traditional Affairs

CoGHSTA: Corporate Governance Human Settlement and Traditional Affairs

COPE	: Congress of the People

DA        : Democratic Alliance

DCF	: District Coordinating Forum

DG        : Disability Grant

DWS     : Department of Water and Sanitation

DRDLR: Department of Rural Development and Land Reform

ECD	: Early Childhood Development

EDP       : Economic Development and Planning

EFF       : Economic Freedom Fighters

EMS      : Environmental Management System

EPWP 	: Expanded Public Works Programme

FBW      : Free Basic Water

FCG      : Foster Care Grant

GIS     : Geographic Information System

HDI	: Historically Disadvantaged Individuals

ICT	: Information and Communication Technology

IDP	: Integrated Development Plan

ITP        Integrated Transport Plan

IGF         : Internally Generated Funds

IGR	: Inter Governmental Relations

IT	: Information Technology

IWMP     : Integrated Waste Management Plan

KFA	: Key Focus Area

KPAs     : Key Performance Areas

KPI 	: Key Performance Indicator

LED	: Local Economic Development

LEDET   : Limpopo Economic Development, Environment and Tourism.

LEGDP: Limpopo Employment, Growth and Development Plan

LG-MTEC: Local Government Medium Term Expenditure Committee

LGTA   : Local Government Turn Around Strategy

LTO       : Local Tourism Organisation

LUMS   : Land Use Management System

MSCOA: Municipal Standard Chart of Accounts

MFMA	: Municipal Finance Management Act

MDGs    : Millennium Development Goals

MIG     : Municipal Infrastructure Grant

MLM	: Makhuduthamaga Local Municipality

MPAC 	: Municipal Public Accounts Committee

MTAS	  : Municipal Turn-Around Strategy

MTSF	   : Medium Term Strategic Framework

MWIG    : Municipal Water Infrastructure Grant

NGO     : Non Government Organisation

NKPA	: National Key Performance Area

NSDP	: National Spatial Development Perspective

OA         : Old age

OPEX	: Operational Expenditure

OPMS    : Organisational Performance Management System

RBIG      : Regional Bulk Infrastructure Grant

RSA      : Republic of South Africa

PAC	: Performance Audit Committee

PDPF    : Provincial Development Planning Forum

PMS	: Performance Management System

PSO	: Provincial Strategic Objective

PTO      : Permission to Occupy

SASSA    : South African Social Security Agency

SAMEBA: South African Maintance and Estate Beneficiaries Association

SAPS       : South African Police Services

SCM  	: Supply Chain Management

SDBIP	: Service Delivery & Budget Implementation Plan

SDGs: Sustainable Development Goals

SMME	: Small Medium &Micro Enterprises

STATSSA: Statistics South Africa

SPLUMA: Spatial Planning and Land Use Management Act

SWOT     : Strength, Weakness, Opportunities and Threats

UN: United Nation

CHAPTER 1:  CONTEXT AND OVERVIEW

1.1 CONTEXT AND OVERVIEW

Municipalities are constitutionally mandated to prepare a five-year Integrated Development Plan (IDP), which serves as a strategic action and service delivery oriented resource and, as such, supersedes all other plans that inform the developmental agenda in local government.

Accordingly, the Makhuduthamaga Municipality’s IDP outlook is guided by its developmental goals, including the programmes of the provincial and national government.  The Makhuduthamaga Municipality’s IDP is a strategic planning instrument that necessitates the participation and input of all municipal residents. As such, it informs and guides all relevant planning, management, budgeting and decisionmaking processes within the institution.   It has the potential to transform local communities in direct response to the needs of our diverse communities and adapt to the changing demands and expectations.  And for this reason, communities are participating more dynamically in decisions and resource allocation, especially around the municipal budget and strategic planning initiatives. This is given expression through active involvement, giving residents more say in the provision of services and by enhancing customer satisfaction as the primary determinant of our success in the provision of services.

The new administration has engaged in a full evaluation of the functioning of every aspect affecting the lives of communities in Makhuduthamaga.  Our Constitution requires us as local government to be developmental – a responsibility to structure and manage the administrative, budgeting and planning processes that will give expression and priority to the basic needs of communities and to promote their social and economic development. Hence our IDP sets out a vision for the future of local government in Makhuduthamaga, in line with legislation and the Constitution.

Our vision points to democratic local government in which the needs of all, but especially the poor and vulnerable communities, are met with efficiency and effectiveness. This will ensure that we are accountable, viable, and capable of delivering sustainable services that meet the diverse needs of our communities

  - VISION AND MISSION

1.2.1 VISION

To be a catalyst of integrated community driven service delivery

    - MISSION

- to strive  towards service excellence

- to enhance robust community based planning

- to ensure efficient and effective consultation and communication with all municipal stakeholders

    - VALUES

| Values | Descriptive analysis |
| --- | --- |
| High standard of professional ethics | The MLM upholds high standards of professionalism as enunciated in the Constitution. Hard work, service to the people, humility, honesty and respect are integral components of professional values. Respect not only the laws of the land but also one another in a performance relationship – this emphasizes mutual respect and regard for dignity of a person or his/her responsibility |
| Consultation | Regular consultations with the people about the services MLM provides |
| Service standards | Need to specify the quality of services people can expect |
| Access | Increase access to services especially people disadvantaged by attitude related barriers |
| Courtesy | Treatment of customers with courtesy and consideration. Things such as smile, respect for customs, apology if things go wrong – this cost nothing |
| Information | Provide more and better information about services so that customers have full,accurate,relevant and up to date information about services they are entitled to receive |
| Openness and Transparency | Tell the people how MLM runs, its departments, costs and who is in charge |
| Redress | If the promised standard of services is not delivered (failures/mistakes/performance problems occur) citizens should be offered an apology, a full explanation and a speedy and effective remedy, and when the complaints are made, citizens should receive a sympathetic, positive responsible |
| Value for Money | Give the best possible value for money so that customers feel that their contribution through taxation is used effectively, efficiently and savings ploughed back to improve their lives. The implementation of Bathopele Principles is continuous process, not a once off task, to be done all the time. |

Source: Constitution (RSA, 1996) and RSA (Bathopele Principles)

## CHAPTER 2: EXECUTIVE SUMMARY

2.1. Introduction

The legislative and policy mandates that influence the activities of local government are numerous, encompassing international, national, provincial and regional influences.  It is important that there is a direct linkage between the activities at a local government level and the broader strategic policy and legislative environment in order that a common vision for the development of South Africans and Makhuduthamaga Local Municipality residents can be achieved

2.2. Legislative Background / Context

The formulation of the IDP must be guided by various pieces of legislation, amongst others are the following:

The Integrated Development Planning process originates in the Constitution of the Republic of South Africa (Act 108 of 1996), which enjoins local government to:

- To provide democratic and accountable government for local communities;

- To ensure the provision of services to communities in a sustainable manner;

- To promote Social and Economic Development;

- To promote a safe and healthy environment ;

- To encourage the involvement of communities and community organizations in the matters of Local Government.

The Constitution also demands local government to improve intergovernmental coordination and cooperation to ensure integrated development across neighboring communities.  The Constitution further commits government to take reasonable measures, within its available resources, to ensure that all South Africans have access to adequate housing, health care, education, food, water and social security.

The Municipal Structures Act (Act 117 of 1998)

The Municipal Structures Act (Act 117 of 1998) provides for the following:

- Chapter 5: Stipulates the general functions and powers of municipalities

- Section 83 (1): Each municipality has powers and functions assigned to it in terms of the provisions of the Constitution

- Section 83 (2): Powers and functions must be divided between the District Municipality and the Local Municipalities

Municipal Systems Act (Act 32 of 2000)

It regulates the IDP.It requires the municipality to undertake developmental oriented planning so as to ensure that it strives to achieve the objectives of local government set out in Section 152 and 153 of the Constitution of the Republic of South Africa.Section 25(1) requires the Municipal council within a prescribed period after the start of its elected term, to adopt a single, inclusive and strategic plan for the development of the municipality.

Chapter 5, Section 26 of the MSA indicates the core components of an IDP and that such an IDP must reflect the following:

- The municipal council’s vision for the long term development of the municipality with special emphasis on the municipality’s most critical development and internal transformation needs

- An assessment of the existing level of development in the municipality, which must include an identification of communities which do not have access to basic municipal services

- The council’s development priorities and objectives for its elected term, including its local economic development and internal transformation needs

- The council’s development strategies which must be aligned with any national and provincial sectoral plans and planning requirements that are binding on the municipality in terms of legislation

- A spatial development framework which must include the provision of basic guidelines for a land use management system for the municipality

- The council’s operational strategies

- Applicable disaster management plans

- A financial plan, which must include a budget projection for at least the next three years

- The key performance indicators and performance targets determined in terms of Section 41 of the MSA

Municipal Finance Management Act (Act 56 of 2003)

The MFMA was promulgated to sustain the finances of both the municipalities and other spheres of government.The Act also gives mandatory obligations on performance management system.Section 2 of the Act’s objectives is to secure sound and sustainable management of the financial affairs of the local government institutions to which this Act applies by establishing norms and standards.

The Makhuduthamaga Local Municipality budget process endeavors to comply to the provision of the MFMA.It is pertinent that the development of the IDP and the budget process are integrated and aligned as per legislation

Municipal Property Rates Act of 2004

The Municipal Property Rates Act of 2004 aims: to regulate the power of a municipality to impose rates on property; to exclude certain properties from rating in the national interest; to make provision for municipalities to implement a transparent and fair system of exemptions, reductions and rebates through their rating policies to make provision for an objections and appeals process.

The Municipal Planning and Performance Management Regulations (R796 of 2001) set out further requirements for an IDP:

- An institutional framework is required for implementation of the IDP and to address the municipality’s internal transformation;

- Investment initiatives;

- Development initiatives including infrastructure, physical, social and institutional development; and

- All known projects, plans and programmes to be implemented within the municipality by any organ of state

The White Paper on Developmental Local Government

The White Paper on Developmental Local Government puts forward a vision of a developmental local government which centres on working with local communities to find sustainable ways to meet their basic needs and improve the quality of their lives.

The following are the four characteristics of this developmental local government;

- Municipal powers and functions are exercised in a manner which maximises their impact on social and economic growth

- Playing an integrating and coordinating role to ensure alignment between all government spheres and private sector investment within the municipal area

- Democratising development

- Building social capital through providing community leadership and vision and seeking to empower marginalised and excluded groups within the community

2.3   Policy Context

Spatial Planning and Land Use Management Act (SPLUMA)

The Act provides a framework for Spatial Planning and Land Use Management.It provides inclusive,developmental,equitable and efficient spatial planning at different spheres of government.It promotes greater consistency and uniformity in the application procedures and decision making by authorities responsible for land use decisions and development applications.It provides for the establishment,functions and operations of Municipal Planning Tribunals

Intergovernmental Relations Framework Act (Act 13 of 2005)

The IGR Act creates a framework for intergovernmental cooperation as required by constitution in its definition of ‘cooperative governance’.Limpopo government has opted to use District municipalities as theatres for coordination of IDP planning among government spheres and their Parastatals.Here municipalities are supported in the planning and its alignment while provincial departments are also being opportune to know what municipalities are raising as development priorities that are sector specific for their own planning and budgeting

Expanded Public Works Programme (EPWP)

The EPWP is a programme that seeks to ensure that public bodies like municipalities formulate plans and budgets that will draw significant numbers of the unemployed into productive work while provide them with training.Makhuduthamaga Local Municipality is using the opportunity of labour intensive construction method to carry out Infrastructure,Environment and Community Works’s Programme under LED projects

Sustainable Development Goals (SDGs)

The 2030 Agenda on Sustainable Development was adopted by UN (United Nations) member states in September 2015.The SDGs are a new universal set of goals, targets and indicators that UN member states will be expected to use to frame their agendas and political policies over the next 15 years i.e 2015 to 2030.The Agenda consists of altogether 17 goals, 169 targets and 231 indicators.

- The SDGs take into account different national realities, capacities & levels of development, and respect national policies & priorities

- Build on the foundation laid by the MDGs

- Seek to complete the unfinished business of the MDGs & respond to new challenges

- The framework will retain goals, targets & indicators format of the MDGs

- Will address four dimensions: Economic development, Social inclusion, Environmental sustainability and Good Governance

Sustainable Development Goals

In 2015 the Millennium Development Goals (MDGs) came to the end of their term, and the sustainable developmebt goals were introduced as the post 2015 agenda comprising 17 Sustainable Development Goals, 169 targets and 229 indicators took their place. The SDG’s RE based on the moral principle of the Millennium Development Goals which strived to ensure that no one or one country should be left behind and that each country has a common responsibility in delivering on the global vision. The goals set out a holistic framework to help set the world on a path towards sustainable development, by addressing all three dimensions of economic development, social inclusion, and environmental sustainability. During the development of the 5 year IDP efforts were made to ensure that integration and institutionalization of the SDG in the planning processes of the municipality is achieved.

Transition from MDGs to the SDGs

There are three fundamental differences between the 2030 Development Agenda and the Millenium Development Goals:

- The SDGs are broader and more ambitious than the MDGs.They go beyond social development and include all three dimensions of sustainable development ,social.economic and environmental

- The SDGs are complex and integrated,with the integrated approach implying the need to manage trade offs and maximise synergies across targets

- The SDGs are universal while the MDGs were not, implying that the goals and targets are relevant to all countries and all stakeholders within the countries.The SDGs should benefit all –eradicating poverty and reducing inequalities.

| Millenium Development Goals |  | Sustainable Development Goals |
| --- | --- | --- |
| Goals | 08 | 17 |
| Targets | 21 | 169 |
| Indicators | 60 | 230 |

The Sustainable Development Goals (SDGs)

- End  poverty in all its forms everywhere

- End hunger,achieve food security and improved nutrition and promote sustainable agriculture

- Ensure healthy lives and promote well being for all at all ages

- Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all

- Achieve gender equality and empower all women and girls

- Ensure  availability and sustainable management of water and sanitation for all

- Ensure  access to affordable,reliable,sustainable and modern energy for all

- Promote sustained,inclusive and sustainable economic growth,full and productive employment and decent work for all

- Build resilient infrastructure,promote inclusive and sustainable industrialization and foster innovation

- Reduce  inequality within and among countries

- Make cities and human settlements inclusive,safe,resilient and sustainable

- Ensure  sustainable consumption and production patterns

- Take urgent action to combat climate change and its impacts

- Conserve and sustainably use the oceans,seas and marine resources for sustainable development

- Protect ,restore and promote sustainable use of terrestrial ecosystems,sustainably manage forests,combat desertification,and halt and reverse land degradation and halt biodiversity loss

- Promote peaceful and inclusive societies for sustainable development,provide access to justice for all and build effective,accountable and inclusive institutions at all levels

- Strengthen  the means of implementation and revitalize the global partnership for sustainable development

Reporting Obligations

| Global and Continental reporting |  | National reporting |  | Provincial reporting |
| --- | --- | --- | --- | --- |
| Sustainable Development Goals | Continental reporting:Agenda 2063 | National Development Plan | Medium Term Strategic Framework | Provincial Development Plan |

Alignment for integrated implementation

| SDGs | Agenda 2063 | Regional (SADC) | National Development Plan | MTSF | LDP | District Development Plan | IDP |
| --- | --- | --- | --- | --- | --- | --- | --- |

National Spatial Development Perspective (NSDP)

It provides for focusing of development on areas of potential as a catalyst towards improvement of lives of communities. Areas of potential or nodal points should be prioritized for infrastructure investment. The development of the municipal SDF took into consideration proposals of the NSDP.

The National Development Plan

The South African Government has through the Minister of Planning published the National Development Plan. The plan aims to eliminate poverty and reduce inequality by 2030. The plan has a target of developing peoples’ capabilities to improve their lives through education and skills development, health care, better access to public transport, jobs, social protection, rising incomes, housing and basic services and safety.

It proposes the following strategies to address the above goals:

- Creating jobs and improving livelihoods

- Expanding infrastructure

- Transition to a low carbon economy

- Transforming urban and rural spaces

- Improving education and training

- Providing quality health care

- Fighting corruption and enhancing accountability

- Transforming society and uniting the nation

Municipalities are the first point of interaction between the communities and government and therefore stand to benefit from the drive towards radical transformation of the economy.

Figure 1: National Development Plan

At the core of the plan is to eliminate poverty and reduce inequality, promotion of gender equity and addressing the pressing needs of youth.

It is imperative for Makhuduthamaga to take these issues into consideration when reviewing the Integrated Development Plan.

Limpopo Development Plan and its objectives and targets

The Limpopo Provincial Administration has developed the Limpopo Development Plan (LDP) which outlines the contribution from Limpopo Province to the National Development Plan (NDP) objectives and the national MTSF for this period. It further outlines the shared vision of the province along with a Strategy and an Action Plan, focusing on the five-year period from 2014 – 2019. The aim of the Plan is to inform planning and resource allocation at both provincial and municipal levels, and also to provide a strategic partnership between government, private sector & civil society.

Strategic Objectives and Targets

The Limpopo Development Plan (LDP) is an official directive for development planning in the Province of Limpopo for the planning periods 2015- 2019. The main development targets for the Province are summarised below:

- Limpopo’s Growth Trajectory Scenario (Current MTSF) at 3%;

- Increase Matric pass rate  from 72.9% in 2014 to beyond 80%;

- Create 429 000 jobs;

- Reduction of official unemployment rate from 16.9% in 2014 to 14%. (Expanded unemployment rate from 38.4% in 2014 to less than 33%;

- Improve access to basic services (water) from 83% in 2014 to 90%;

- Improve access to electricity supply from 83% in 2014 to 90%;

- Improve access to sanitation from 43% in 2014 to 50%;

- Reduce HIV Incidence from approx. 9% of the total population of Limpopo in 2014 to 5%;

- Increase Life expectancy M = 58.3, F = 62.5 in 2014 to M = 60, F = 65;

- Reduce inequality (Gini-Coefficient) from 0.61 in 2014 to 0.50; and

- Increase GGP contribution to national economy from the current 7.1%.

Convergence of Agenda 63 and the Sustainable Development Goals (SDGs)

| Agenda 2063 (2023 Goals) | SDG | NDP Chapter(s) | LDP Outcome(s) |
| --- | --- | --- | --- |
| Goal1: A High Standard of Living, Quality of Life and Well Being for All | GOAL 1 End poverty in all its forms everywhere in the world GOAL 3 Ensure healthy lives and promote well-being for all at all ages | Chapter 11 Social protection | Outcome 2. Long and healthy life Outcome 3. All people in Limpopo feel safe Outcome 7. Comprehensive rural development Outcome 8. Human settlement development Outcome 13. Inclusive social protection system |
| Goal 2: Well Educated Citizens and Skills revolution underpinned by Science, Technology and Innovation | GOAL 4 Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all | Chapter 9 Improving education, training and innovation | Outcome 1. Quality basic education Outcome 5. Skilled and capable workforce |
| Goal 3: Healthy and Well-Nourished Citizens | GOAL 2 End hunger, achieve food security and improved nutrition and promote sustainable agriculture GOAL 3 Ensure healthy lives and promote well-being for all at all ages | Chapter 10 Promoting health | Outcome 2. Long and healthy life Outcome 3. All people in Limpopo feel safe Outcome 7. Comprehensive rural development Outcome 13. Inclusive social protection system |
| Goal 4: Transformed Economies and Job Creation | GOAL 8 Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all | Chapter 3 Economy and employment | Outcome 4. Decent employment through inclusive growth Outcome 7. Comprehensive rural development |
| Goal 5: Modern Agriculture for increased productivity and production | GOAL 2 End hunger, achieve food security and improved nutrition and promote sustainable agriculture GOAL 12 Ensure sustainable consumption and production patterns | Chapter 6 An integrated and inclusive rural economy | Outcome 2. Long and healthy life Outcome 7. Comprehensive rural development Outcome 10. Environmental protection Outcome 13. Inclusive social protection system |

Alignment of the NDP and LDP priorities into the municipal IDPs

The NDP highlights the need to strengthen the ability of local government to fulfil its developmental role. It calls for Municipal Integrated Development Plans (IDPs) need to be used more strategically to focus attention on critical priorities in the NDP that relate to the mandate of local government such as spatial planning, infrastructure and basic services.

Like provincial planning processes, municipal IDPs should be used to focus on aspects of the NDP that fit within a municipality’s core responsibilities. This would allow the IDP process to become more manageable and the participation process more meaningful, thus helping to narrow the gap between the aspirations contained in these documents and what can actually be achieved. To do this effectively, the IDP process needs to be led by municipal staff, not outsourced to consultants.

The Local Government Back to Basics Strategy

The Local Government Back to Basics Strategy (B2B) its main core services that local government provides i.e. clean drinking water, sanitation,electricity,shelter,waste removal and roads which are the basic human rights enshrined in our constitution and Bill of Rights. This strategy comes after local government facing challenges in rendering services to the communities and majority of municipalities in the country to account mainly in financial management and continuous negative audit outcomes.

The following are Local government programmes which municipalities will work to ensure:

- Basic Service: Creating conditions for decent living

- Municipalities must deliver the basic services (basic water,sanitation,electricity,waste removal etc)In addition to the above, municipalities must ensure that services such as cutting grass, patching potholes, working robots and street lights and consistent refuse removal are provided.

- Council to ensure proper maintenance and immediate addressing of outages or maintenance issues to ensure continuity of service provision

- .Municipalities must improve mechanisms to deliver new infrastructure at a faster pace whilst adhering to the relevant standards

- .Increase of Community Work Programme sites targeting the unemployed youth in informal settlements to render day to day services such as cutting grass, patching potholes, cleaning cemeteries,etc

- .Extend reach of basic services to communities living in informal settlements by providing temporary services such as:(i)potable water,(ii)temporary sanitation facilities,(iii)grading of gravel roads and (iv)refuse removal

- Good governance

- Municipalities will ensure transparency, accountability and regular engagements with communities.

- All municipal structures must be functional and meet regularly.

- Council meetings to sit at least quarterly.

- All Council Committees must sit and process items for council decisions.

- Clear delineation of roles and responsibilities between key leadership structures.

- Functional oversight committees must be in place,e.g Audit committee and Municipal Public Accounts Committees(MPAC)

- Public Participation: Putting people first

- Implement community engagement plans targeting hotspots and potential hotspots areas.

- Municipalities to implement responsive and accountable processes with communities.

- Ward committees must be functional and Councillors must meet and report to their constituencies at least quarterly

- Utilise the Community Development Workers (CDWs), Ward committees and Ward councillors to communicate projects earmarked for implementation.

- PR Councillors need to represent the interests of the municipality as a whole and ensure that effective oversight and leadership functions are performed.

- Municipalities must communicate their plans to deal with backlogs.

- Municipalities to monitor and act on complaints, petitions and other feedback.

- Sound financial management

- All municipalities must have a functional financial management system which includes rigorous internal controls.

- Cut wasteful expenditure.

- Supply Chain structures and controls must be in place according to regulations and with appropriate oversight.

- All Budgets to be cash backed.

- Ensure that Post Audit Action Plans are addressed.

- Act decisively against fraud and corruption.

- Conduct campaigns on “culture of payment for services” led by Councillors.

- Conduct campaigns against “illegal connections, cable theft, manhole covers”etc

- Building capable institutions and Administrations

- All municipalities enforce competency standards for Managers and appoint persons with the requisitive skills, expertise and qualifications.

- All staff to sign performance agreements.

- Implement and manage performance management systems.

- Municipal management to conduct regular engagements with labour

Makhuduthamaga Local Municipality‘s Key Performance Areas (KPAs)

Taking cognizance of the political, national, provincial and district policies and plans, the following KPA’S were identified and adopted by the Makhuduthamaga Municipal Council:

- Spatial Rationale

- Basic Service Delivery and Infrastructure Development

- Local Economic Development

- Financial Viability and Management

- Good Governance and Public Participation

- Municipal Transformation and organizational development

The Key Performance Areas (KPAs) are defined in the following table:

| Key Performance Area | Definition |
| --- | --- |
| KPA 1: Spatial Rationale | To establish economical, socially , environmentally integrated sustainable human settlements around Makhuduthamaga Municipality |
| KPA2:Basic Service Delivery and Infrastructure Development | To ensure provision of efficient infrastructure ( Roads and storm-water) and energy supply that will contribute to the improvement of quality of life for all in Makhuduthamaga To contribute to the safety of communities through the proactive identification, prevention, mitigation, and management of environment, fire and disaster risks. |
| KPA 3: Local Economic Development | To facilitate sustainable economic empowerment for all communities within Makhuduthamaga and enabling a viable and conducive economic environment through the development of related initiatives including job creation and skills development |
| KPA 4: Financial Viability and Management | To ensure the financial viability and sustainability of the municipality and to adhere to statutory requirements |
| KPA 5: Good Governance and Public Participation | To promote proper governance and public Participation To improve public relations thus pledging that our customers are serviced with dignity and care to facilitate the development of the poor and most vulnerable including the elderly, women, people with disabilities, youth and rights of Children |
| KPA6:Municipal Transformation and organizational development | Institutional transformation to provide an effective and efficient workforce by aligning institutional arrangements to the overall municipal strategy in order to deliver quality services |

2.4 Powers and Functions

Makhuduthamaga Local Municipality is a Category B Municipality established to  perform the following functions as bestowed upon by the Constitution in terms of section 156 (1) and the  division of powers:

| Functions | MLM | SDM | Eskom | Description of function performed |
| --- | --- | --- | --- | --- |
| 1.Air pollution | No |  |  |  |
| 2.Building regulations | Yes |  |  | Enforcing the national building regulations |
| 3.Child care facilities | Yes |  |  | To provide support to creches |
| 4.Electricity reticulation |  |  | Yes | Supply and maintain all electricity functions |
| 5.Fire fighting |  | Yes |  | Complete fire fighting services |
| 6.Local tourism | Yes |  |  | To provide LED support and tourism enhancement support |
| 7.Municipal Airport | No |  |  |  |
| 8.Municipal Planning | Yes |  |  | Forward planning. Land use control. Policy development.Environmental.GIS |
| 9.Municipal health Services |  | Yes |  | Provision of municipal health services through inspections, investigations and control |
| 10.Municipal Public transport | Yes |  |  | Provide traffic control and licensing |
| 11.Pontoons and ferries | No |  |  |  |
| 12.Storm water | Yes |  |  | Provide storm water system |
| 13.Trading regulations | Yes |  |  | Regulate trading with support from LEDET |
| 14.Water |  | Yes |  | Water authority and provider |
| 15.Beaches and amusement facilities | No |  |  |  |
| 16.Billboards and the display of advertisements in public places | Yes |  |  | Regulation,control,and display of advertisement and billboards |
| 17.Cemetries,funeral parlors and crematoria | Yes |  |  | Control |
| 18.Cleansing | Yes |  |  | Sweeping streets, picking litter, and emptying of street bins |
| 19.Control of public nuisance | Yes |  |  | Control of public nuisance and inspection thereof issuing of notices |
| 20.Control of undertakings that sell liquor to the public | No |  |  |  |
| 21. Facilities for the accommodation, care and burial of animals | Yes |  |  | Compliance |
| 22. Fencing | Yes |  |  | Fencing of cemeteries and wetlands |
| 23.Licencing of dogs | Yes |  |  |  |
| 24.Licencing and control of undertakings that sell food to the public | Yes |  |  | Quality control. Safety and hygiene regulations |
| 25. Local amenities | Yes |  |  |  |
| 26. Local sports facilities | Yes |  |  | Maintaining and provision of stadia |
| 27. Markets | Yes |  |  | Building of stalls market to the community for revenue enhancement and growing of economy. |
| 28. Municipal abattoirs | Yes |  |  |  |
| 29. Municipal parks and recreation | Yes |  |  | Recreational areas for local communities |
| 30.Municipal roads | Yes |  |  | Maintenance of roads, upgrading roads from gravel to tar |
| 31.Noise pollution | Yes |  |  | Control of noise pollution |
| 32.Pounds | Yes |  |  |  |
| 33. Public places | Yes |  |  |  |
| 34. Refuse removal, refuse disposal sites and Solid waste disposal | Yes |  |  | Waste collection. Waste transport landfill management |
| 35. Street trading | Yes |  |  | Regulate and control |
| 36.Street lighting | Yes |  |  | Provide and maintain |
| 37.Vehicle licensing and registration | Yes |  |  | Provide |
| 38. Learners and Drivers licensing | Yes |  |  | Provide |
| 39.Disaster Management | Yes |  |  | Provide |

Source: COGHSTA, 2016

2.5 Basis for IDP Review Process

Section 32 (1) (a) of the Municipal Systems Act, act 32 of 2000 mandates the Municipal Manager of a municipality to submit a copy of the Integrated Development Plan as adopted by Council of the Municipality, and any subsequent amendment to the plan, to the MEC for Local Government in the Province within 10 days of the adoption or amendment of the plan, for assessment.

Analysis of MEC Opinion on Makhuduthamaga Municipality IDP over the last five years

| Financial year | IDP assessment | IDP-SDBIP alignment | Overall rating |
| --- | --- | --- | --- |
| 2014/15 | High | Aligned | High |
| 2015/16 | High | Aligned | High |
| 2016/17 | High | Aligned | High |
| 2017/18 | High | Not aligned | Low |
| 2018/19 | High | Partially aligned | Medium |

Source: CoGHSTA, Limpopo 2018

The opinion of the MEC assessment panel during 2018/19 IDP/ Budget assessment was that the MLM should maintain the status quo on issues that were clearly indicated in terms of all KPAs and adhere to the process plan in the 2019/20 IDP /Budget review 	and further improve on the issue of SDBIP/ IDP alignment

Process plan

Drafting an IDP requires a comprehensive planning process and the involvement of a wide range of internal and external role players. Such process has to be properly organized and prepared. The preparation is the duty of the Municipal Manager and Senior Managers. The preparation process will be referred to as the process plan and should contribute to the institutional readiness to draft or review the IDP.

The elected Municipal Council is the ultimate IDP decision making authority. The role of participatory democracy is to inform, negotiate and comment on those decisions in the course of the planning process. In terms of the Council approved IDP and Budget process plan, Council must approve the final IDP before the start of the financial year, that is , no later than 31 May 2018 .In order for Makhuduthamaga to prepare a credible IDP, several stakeholders have to be engaged to provide inputs and inform the final IDP.

IDP PROCESS PHASES

Table 2: Municipal IDP Process rollout

| Planning phase | Participation Mechanism |
| --- | --- |
| Analysis phase : Determine local issues , problems, relevant stakeholders, potentials and priorities | - Stakeholders meetings, ward committee meetings ,sectoral engagements - District IDP Managers / Officers forum meetings - Provincial Development Planning Forum Meetings (PDPF) |
| Strategy Phase: Determine vision and objectives, Determine strategies and participate in IGR structures | - Strategic meeting with Senior Management Team - Strategic workshop with municipal EXCO - District and Provincial Government engagements - Municipal Budget Steering Committee |
| Project Phase: Design projects per strategy | - Inter departmental / Sectoral Planning - Municipal Budget Steering Committee |
| Integration phase: Agree on project proposals and compilation of integrated programmes | - Inter- Departmental Sectoral Planning - District IDP Managers / Officers Forums |
| Approval phase: Adoption by Council providing opportunity for stakeholder comments | - Council and stakeholders meetings and interviews - Approval of IDP/ budget - Consolidation of SDBIP |
| Monitoring and evaluation: Ensure economic efficiency and effective use of resources | - Meeting with Senior Management team - Representatives of stakeholders, ward committees, EXCO, Portfolio committees, internal audit, audit committee, Council and public. |

2.6 Institutional arrangements for the IDP process and implementation

In order to manage the drafting of the IDP outputs effectively, Makhuduthamaga Local Municipality institutionalized the participation process thereby giving affected parties access to contribute to the decision making process. The following structures, linked to the internal organizational arrangements have therefore been established:

- The IDP Steering committee which is chaired by the Municipal Manager  and is composed as follows: Senior Managers, Division Mangers and Senior IDP Officer

- IDP Representative Forum which is chaired by the Mayor and composed of the following stakeholders: Councilors, Ward committees,CDWs, Traditional leaders, organized business, Women’s organizations, Youth movements, People with Disabilities, Advocacy Agents of unorganized groups, Sector departments, District municipality, Parastatals, NGOs and CBOs.

## 2.7 Process Overview: Steps and Events

## IDP/Budget review structures and roles clarifications and responsibilities

Roles and responsibilities of government spheres

The Municipal Systems Act, 2000 requires both district and local municipalities to do Integrated Development Planning. The IDP process requires that all role-players are fully aware of their own, as well as other role-players’ responsibilities in the execution of the IDP process.

The roles and responsibilities of the various spheres of government and other relevant stakeholders for IDP review process are as follow:

- The role of the National Sphere of Government is to provide a legal framework, policy guidelines and principles for sectoral, provincial and local government planning.

- The role of the Provincial Sphere of Government is to monitor the IDP process and to ensure vertical / sector alignment;

- District Municipality is also responsible to effect horizontal and vertical alignment of the IDP’s of local municipalities,

- The role of the Local Municipalities is to compile a 5 year IDP aligned with other spheres of government.

Stakeholders’ Consultations

In terms of the Municipal Systems Act, the IDP review process should start ten months before the beginning of the financial year under review

First Phase: September-October –November

This phase of the IDP/Budget review process allows the community to identify broader development needs and priorities.It also allows the community, together with other stakeholders, to input on the analysis phase.

During this phase deliberate efforts must be made to involve ward based organized/community structures/stakeholders/service providers/previously marginalized groups and broader community members through community based planning approach.Sector based consultations will also be conducted during this phase to coordinate alignment in planning process through IDP Managers /Representatives forums.

Second Phase: April- May

The phase will be characterized by comprehensive stakeholders’ consultations, policy review and public submissions.Public participation will be allowed for comments and inputs into the draft IDP/Budget.It is therefore imperative to publish both draft IDP and Budget prior to the commencement of second phase of stakeholders’ consultation.

Other Media for Public Participation

The following mechanisms will also be used for public participation:

- Print media

National and regional newspaper and the municipal newsletter will be used to inform the community of the activities of the process plan and even progress on implementation

- Radio slots

The local radio station and regional stations will be utilized to make public announcements and interviews about IDP process activities and progress on implementation.

- Municipal website

Municipal website will also be utilized to communicate and inform community.Copies of IDP/Budget will be placed on the website for people and other stakeholders to view or download.

Distribution of roles and responsibilities of stakeholders in the IDP scenario

| Stakeholders | Roles and responsibilities |
| --- | --- |
| Makhuduthamaga Local Municipality Council | - Prepare process plan for IDP Revision - Undertake the overall management ,coordination and monitoring of the process as well as the drafting of the local IDP - Approve IDP within the agreed framework - Ensures participatory planning that is strategic and implementation oriented. |
| SDM | - Compile IDP framework for the whole District - Ensures alignment of IDPs in the District |
| Office of the Premier | - Support and monitor CoGHSTA ’s alignment responsibilities - Ensures Medium Term Framework and Strategic Plans of Provincial Sector Departments consider IDPs - Intervene where there is a performance problem of provincial departments - Investigates issues of non performance of provincial government as may be submitted by any municipality |
| CoGHSTA | - Ensure vertical/sector alignment between provincial sector department/provincial strategic plans and IDP process at local level - Ensures horizontal alignment of IDPs of various municipalities |
| Other Sector Departments | - Contribute technical knowledge, ideas and sector expertise to the formulation of municipal strategies, projects and sector plans - Actively participate in the various Task teams established for IDP process - Provide departmental operational and capital budgetary information |
| COGTA | - Issue legislation and policies in support of IDP’s - Issue Integrated Development Planning Guidelines - Provide financial assistance - Provide a National Training Framework |
| IGR Structures (IDP Rep Forum, IDP Managers forum,PDPF,DDPF | - Provide inter-governmental dialogue to agree on shared priorities and interventions - Provide dialogue between sectors for holistic infrastructure development |
| Private sector | - Participate in the formulation of the plan - Provide information on the opportunities that the communities may have in their industry - Submit their projects in the IDP of the municipality |
| Other Stakeholders | - Interest groups such as NGOs, CBOs, Magoshi, and Organizations for Youth, women, and people with disabilities may be involved in the local IDP Representative Forum. Aim is to consult with and respond to various interests in the community. |
| Communities | - Identify and prioritize needs - Participate in the IDP Representative Forum - Discuss and comment on the draft IDP review - Monitor performance in the implementation of the IDP review |
| Ward committees | - Participate in the community consultations meetings - Articulate the community needs - Help in the collection of the needed data /research |
| Community Development Workers | - Help in the generation of the required data, thereby providing requisite support to Ward committees |

The 2018/19 IDP Review and Budget process plan / time schedule is prepared in terms of Section 21 (1) (a) and (b) of the Municipal Finance Management Act. No 56 of 2003 which states the following;

The Mayor of a Municipality must;

(a) Co-ordinate the processes for preparing the annual budget and for reviewing the municipality’s integrated development plan and budget-related policies to ensure that the tabled budget and any revisions of the integrated development plan and budget-related policies are mutually consistent and credible;

(b) At least 10 months before the start of the budget year, table in the municipal council a time schedule   outlining key deadlines for-   i. The preparation, tabling and approval of the annual budget; ii. The annual review of- (aa) the integrated development plan in terms of section 34 of the Municipal Systems Act; and (bb) the budget related policies. iii. the tabling and adoption of any amendments to the integrated development plan and the budgetrelated policies; and iv. any consultative processes forming part of the processes referred to in subparagraphs (i), (ii) and (iii).

The 2018/19 IDP and Budget preparation time schedule articulates the progressive activities and processes which the municipality will embarked on to review its fourth-generation Integrated Development Plan and to prepare the annual budget for the 2018/19 financial-year. The process plan/time schedule enhances integration and alignment between the IDP and Budget, thereby ensuring the development of an IDP-based budget. It fulfils the role of a business plan or an operational framework for the IDP review process outlining the manner in which the review process will be undertaken. The IDP and Budget process plan/time schedule incorporates all municipal planning, budgeting, performance management, performance reporting and public and stakeholder engagement processes.

The process creates its own dynamics since it encompasses the involvement of external role players; therefore it requires accurate logistical planning and arrangements of engagement sessions to ensure that the process is implemented in accordance with the time schedule

Annual revision of the IDP/Budget

According to Section 34 of the Municipal Systems Act,

A municipal council;(a) must review its integrated development plan- (i) annually in accordance with an assessment of its performance measurements in terms of section 41; and

(ii) to the extent that changing circumstances so demand; and (b) may amend its integrated development plan in accordance with a prescribed process. The IDP must be reviewed annually in order to:

- Ensure its relevance as the municipality’s strategic plan;

- Inform other components of the municipal business process including institutional and financial planning and budgeting; and

- Inform the cyclical inter-governmental planning and budgeting cycle.

For the IDP to remain relevant the municipality must assess implementation of performance and the achievement of its targets and strategic objectives. In the light of this assessment the IDP is reviewed to reflect the impact of successes as well as corrective measures to address challenges. The IDP is also reviewed in the light of changing internal and external circumstances that impact on the priority issues, outcomes and outputs of the IDP. The annual review must inform the municipality’s financial and institutional planning and most importantly, the drafting of the annual budget.

The purpose of the annual review is therefore to;

- reflect and report on progress made with respect to the strategy in the 5-year IDP;

- make adjustments to the strategy if necessitated by changing internal and external circumstances that impact on the appropriateness of the IDP;

- determine annual targets and activities for the next financial year in line with the 5-year strategy; and

- inform the municipality’s financial and institutional planning and most importantly, the drafting of the annual budget.

What the review is not

It is important to note that the Review is not a replacement or amendment of the 5-year IDP. The Review is not meant to interfere with the 5-year strategic orientation of the municipality and development horizon set in the mother document. Throughout the 5-year cycle any version of the IDP Review should always be read in conjunction with the approved 5-year IDP document.

Below is the Approved Schedule for the review of IDP/Budget for the 2019/20 F/Y

| Month | Action | Target date |
| --- | --- | --- |
| PREPARATORY PHASE |  |  |
| July 2018 | - Review of previous year’s IDP/Budget process - Exco provides political guidance over the budget process and priorities that must inform preparations of the budget - IDP/Budget Steering Committee meeting - 4th Quarter Performance Lekgotla (2017-18) - Submit IDP/Budget Process Plan for 2019/20 to Council - All Senior Managers and Municipal Manager’s annual performance agreements signed and submitted to MEC for CoGHSTA. | July 2018 |
| August 2018 | - Submit Annual Financial Statements for 2017/18 to AG - Submit 2017/18 cumulative Performance Report to AG and Council Structures - Operational Risk Assessment for 2018/2019 - Ward to Ward based data collection - Collate information from ward based data | August 2018 |
| Month | Activity | Target date |
| ANALYSIS PHASE |  |  |
| September 2018 | - Council determines strategic objectives for service delivery through IDP review processes and the development of the next 3 year budget (including review of sector department plan) - Consult with provincial and national sector departments on sector specific programmes for alignment (libraries, schools, clinics, water, electricity, roads, sanitation, etc.) - Finalise ward based data compilation - Update Council Structures on updated data | September 2018 |
| Month | Activity | Target date |
| STRATEGIES PHASE |  |  |
| October 2018 | - Quarterly (1st ) review of the 2018/19 budget, related policies, amendments (if necessary),any related process - Begin preliminary preparations on proposed budget for 2019/20 financial year - 1st Quarter Performance Lekgotla (2018/19) | October 2018 |
| Month | Activity | Target date |
| PROJECTS PHASE |  |  |
| November 2018 | - Confirm IDP Projects with District and Sector departments - Review and effect changes on the initial IDP draft | November 2018 |
| Month | Activity | Target date |
| INTEGRATION PHASE |  |  |
| December 2018 | - Table Draft 2017/18 Annual Report to Council - Review budget performance and prepare for adjustment - Consolidated Analysis Phase in Place - IDP/Budget Steering Committee meeting - IDP Representative Forum | December 2018 |
| January 2019 | - Table Draft 2017/18 Annual Report to Council - Submit Draft Annual Report to AG,PT and CoGHSTA - Publish Draft Annual Report in the Municipal jurisdiction (website etc.) - Prepare Oversight Report for 2017/18 financial year - Mid-Year Performance Lekgotla - Table Mid-year Performance assessment report to council and submit to National Treasury, Provincial Treasury and Provincial CoGHSTA. Strategic Planning Session (Review of IDP/Budget, related policies) | January 2019 |
| Month | Activity | Target date |
| February 2019 | - Table Budget Adjustment (if necessary) - Submission of Draft IDP/Budget for 2019/20 to Management - Submission of Draft IDP/Budget and other plans to Portfolio committees - Submission of Draft IDP/Budget to EXCO - Conduct Mid-year Performance assessment for Municipal Manager and all Senior Managers for 2018/19 financial Year. - Submit and Present Mid-Year performance assessment report and adjustment budget to Provincial Treasury. | February 2019 |
| March 2019 | - Table 2019/20 Draft IDP/Budget to council for noting. - Prepare and submit Draft SDBIP to Mayor, CoGHSTA, Provincial and National Treasury for inputs. - Prepare and submit draft annual procurement plan to Mayor, Provincial Treasury and National Treasury. - Table Municipal policies and By-Laws to council for noting. - Publish the 2019/20 IDP/Budget, Municipal Policies and By-Laws for public comments. - Table Oversight Report for 2017/18. - Conduct annual Performance assessment for Municipal Manager and all Senior Managers for 2017/18 financial Year. | March 2019 |
|  | APPROVAL PHASE |  |
| April 2019 | - Submit 2018/19 Draft IDP/Budget to the National Treasury, Provincial Treasury , CoGHSTA and SDM in both printed and electronic formats - Consultation with National and Provincial Treasuries, community participation and stakeholder consultation - Submission of Draft IDP/Budget for 2018/19 to Council structures with incorporated comments from the consultative process - Strategic Risk Assessment for 2018/2019 - 3rd Quarter Performance Lekgotla (2018/19) | April 2019 |
| May 2019 | - Table Final Draft of IDP/ Budget for 2019/20 to the Council for approval - Submit final annual procurement plan to Mayor, Provincial Treasury and National Treasury. - Table Municipal policies and By-Laws to council for approval. - Publish the approved 2019/20 IDP/Budget, Municipal Policies and By-Laws. - Prepare SDBIP for 2019/20 - Develop Performance Agreements (Performance Plans) of MM and Senior Managers for 2019/20 Performance year - Prepare operational Risk assessment for 2019/2020 | May 2019 |
| June 2019 | - Submission of the SDBIP to the Mayor for approval. - Submission of approved IDP/Budget and SDBIP to MEC for CoGHSTA / National and Provincial Treasury and to SDM - Publish Notice and summary of approved budget in Gazette and Local Newspaper | June 2019 |

The review process for the development of this IDP was conducted as follows:

- Council approval of the review process plan was done on 31 July 2018.

- IDP District Engagement Session (Analysis Phase) on the 26 September 2018

- Exco First Quarter Lekgotla on the 18th October 2018

- Exco Half yearly / Second quarter Lekgotla on the 15th January 2019

- Strategic Planning from 23-25th January 2018

- IDP District Engagement Session (Strategies and Project Phases)on the 19 Febrauary 2019

- First Draft 2019/20 IDP/Budgt presented to Executive committee on the 25th March 2019

- First Draft 2019/20 IDP/Budget presented to Portfolio committee on the 27th March 2019

- First Draft 2019/20 IDP/Budget presented to Council on the 28th March 2019

- Stakeholders consultation on the First Draft 2019/20 IDP/Budget commenced on the 18th April  to 30th April 2019

- Final Draft 2019/20 IDP/Budget presented to Exco on the 23rd May 2019

- Final Draft 2019/20 IDP/Budget presented to Portfolio committees on the 27th May 2019

- Final Draft 2019/20 IDP/Budget presented to Council for approval on the 29th May 2019

Implementation of the IDP

The IDP drives the strategic development of Makhuduthamaga Municipality. The Municipality’s budget is influenced by the strategic objectives identified in the IDP. The Service Delivery and Budget Implementation Plan (SDBIP) ensure that the municipality implements programmes and projects based on the IDP targets and associated targets. The performance of the municipality is reported in its annual report. In addition to the above, Risk management forms an integral part of the internal processes of a municipality. It is a systematic process to identify, evaluate, and address risks on a continuous basis before such risks can impact negatively on the service delivery capacity of the Makhuduthamaga Municipality. When properly implemented, risk management provides reasonable assurance that the institution will be successful in achieving its goals and objectives

2.8. Outcomes of the IDP Community Consultation Meetings (Community needs)

MLM engaged in an intensive community consultation that was done at ward level in line with the Community Based Planning approach (20.08.2018-13.12.2018). The  municipality employed the community based planning approach to stimulate participatory governance by awarding community members a fair opportunity to deliberate on issues affecting them in their respective wards.Furthermore,this approach was implemented to inevitably include the local community in decision making, planning and generally allowing them to play an active part in their own development

Five year (2016/17-2020/21) identified needs per ward and community prioritized needs

| WARD |  |  | VILLAGE |  |  | PRIORITY NEEDS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  | 1.Ga Tshehla |  |  | - Fencing of graveyard - VIP toilets (115) - RDP houses (15) - Maintenance of 01 borehole,1 jojo tank - Skip bins (3) - Live stock dam - Mast lights 3 - Renovation of Arekhuleng Primary School - Speed humps - Illegal dumping |
|  |  |  | 2.Hlalanikahle |  |  | - Controlling of water stormwater by constructing 2 bridges at Phetla road - Water-10 boreholes and ten jojo tanks - Tarring of road from Bosele to Baromaneng - RDP houses (50) - VIP toilets(1900) - Bridge at Ga-Phetla - Electricity post connections - Skip bins (6) - Mast lights (4) - Secondary school for village (new) - Paving of our internal streets - Building of library - Education –TVET college - Livestock dam - Illegal dumping - Bridge at Ga-Masango - Clinic |
|  |  |  | 3.Kutupu |  |  | - Fencing of graveyard - Water- maintenance of 4 boreholes and 4 jojos - Bridge at Ga-Masango - VIP toilets(2002) - RDP houses(600) - Tarring of road from Zone 1 to Zone 3 - Skip bins (7) - High mast lights(4) - Construction of a bridge from Kutupu to graveyard (Ratanang site) - Fencing of two dams - Storm water control - Paving of road from zone 1 to zone 3 - Clinic - Tarring of road from Kutupu to Ratanang - Tarring of road from Kutupu to Vleiscboom - Livestock dam - Fencing of dam - Electricity post connections - Illegal dumping - Incomplete RDP houses |
|  |  |  | 4.Ratanang Kutupu Extension |  |  | - Bridge from Kutupu to Ratanang - Water - VIP toilets - Electricity post connections - Tarring of road from Kutupu to Ratanang - RDP houses (10) - Skip bins(4) |
| 2 |  |  | 1.Phokoane and Toishi |  |  | - Tarring of roads :Phokoane clinic to Maloka road,Piekie’s corner to Leshalabe Primary school, Toishi to Greenside road, Toishi to Dihlwadieme cemetery,Lekhehla to Leshlabe school,mosate to tribal office - Education :allocation of bursaries,training and learnerships of SMMEs,technical college,multipurpose centre - High mast lights - Sprts complex - Old age centre - CWP and EPWP provision - Funding of SMMEs - Regravelling of streets - Grading of sports ground - Electricity post connections - Water provision - Skip bin |
|  |  |  | 2.Mabintane |  |  | - Tarring of Platklip main street and Ngema Street to Mashishing - VIP toilets - Electricity post connections - Clinic - Mast lights - Funding of SMMEs - Sports complex - Technical college - Library - Park - Fencing of Mashishing and Platklip cemetery - CWP and EPWP provision - Regravelling of streets - Grading of sports ground - Electricity post connections - Water provision - Drilling of boreholes and tanks provision - Skip bin |
|  |  |  | 3.Mogudi |  |  | - Tarring of Tlame main road - Tarring of Mamosadi main street - Mast lights - Sports complex - Water provision - Drilling of boreholes and tanks provision - Park - Electricity post connections - CWPs and EPWP provision - SMMEs support with funding and training - Regravelling and blading of streets - VIP toilets in the new stands |
| 3 |  |  | 1.Mokgapaneng |  |  | - Tarring of main road to Blackhouse - Tarring of road from Mokgapaneng reservoir to Selengwane to Malegale cemetery - Two bridges needed :Reservoir main road and Selengwane - Electricity post connections - Storm water drainage in main road and Matlala shop to Selengwane - Leduma Primary School - Mobile clinic needed - Water - Skip at Blackhouse - Bridge at Maila street to join Selengwane main |
|  |  |  | 2.Makoshala |  |  | - Tarring of road from Makoshala mortogate via Lehwelere and Thotoaneng schools to Phokoane /Nebo Police Station - Storm water drainage at Makoshala Block F - Tarring of road from Lehwelere school to Brooklyn - Electricity post connection - Tarring of road to Makoshala graveyard - Tarring of main road to Nebo Circuit Offices - Bridge needed at Phokoane / Nebo Police station road - Bridge needed at main street block F - Bridge on the road to Phokoane community centre - Storm water drainage on the main street to Phokoane Community Centre - Unfinished storm water drainage at Block C - Electricity post connection at Block C - Water infrastructure needed - Mobile clinic needed - RDP houses - Skip at Motorgate Makoshala and spares - Skip at Thotoaneng and Petloane - Stromwater at Lehwelere school to Makoshala cemetery - Skip between Makoshala corner cemetery and Mogudi - Stormwater from Thotoaneng to Nebo Police Station - Waste collections (household) - Incomplete fencing of cemetery |
|  |  |  | 3.Phokoane(Malegale) |  |  | - No water at all - Storm water drainage needed on Nkoane road - Tarring of main roads via Phokoane clinic and Mogadime street - Mogadime street via Skotiphola an access bridge needed - Storm water drainage on the Phokoane clinic and Malegale grave yard roads - RDP houses - Stormwater at Nkoane to main road to Malegale graveyard - Stormwater from Mogadime tar road to Ntsomane Mashifane main road to Skotiphola acess bridge |
|  |  |  | 4.Phokoane(Mapaeng) |  |  | - Tarring of Leshalabe shop to Selengwane road - Tarring of main road at Magajane to Mapaeng to Malegale cemeteries - Tarring of road from corner Mosoane to Selengwane to Malegale cemetery - Stormwater from Mosoane to main road to Aboo main road - Waste collection - Stormwater fom Mosoane corner street to Malegale cemetery |
|  |  |  | 5.Phokoane(Ramabele Malatji,Lefakong,Masioneng,Skotiphola and Mashifane) |  |  | - Tarring of Ramabele / Malatji from Phokoane clinic via Mashifane and Malegale - Tarring of road from Ga-Malatji street to Skotiphola access bridge - Tarring of road at Masioneng St Engenase Church - Storm water drainage – there is a big donga/pothole at Ga-Malatji - RDP houses - Stormwater from Ga-Ramabele to Phokoane clinic - Stormwater from shortleft main waterhole Leshalabe to Malatji to via Skotiphola acess bridge - Tarring of road at Masioneng via on two parallel road to church - St Engenase church joined on v point main road to Masioneng cemetery via Moriti school to Skotiphola acess bridge to Mohlala Doctor to main road - Tarring of main roads Ga Main street to Skotiphola access bridge |
|  |  |  | 6.Phatametsane |  |  | - Tarring of road from Lekwankwa shop to new Library - Tarring of road from main road to ZCC church - Storm water drainage on the new library road to Lekwankwa shop - Storm water drainage corner Phatametsane school to Boipusho Dam - Phatametsane bridge between Lekwankwa and Phatametsane school - RDP houses - Tarring of main road- Phatametsae corner via ZCC to main road to Phokoane tribal office - Need of two (2)bridges between Phatametsane and tribal office and Boipusho dam to assist learners to school |
|  |  |  | 7.Masioneng /Skotiphola |  |  | - Tarring of St Engenase Church main road - Tarring of road from Masioneng to Skotiphola main road to Skotiphola access bridge - Storm water drainage on main street of Skotiphola - Storm water drainage on Skotiphola Roman Catholic Church - RDP houses - Tarring of road from Masioneng to Skotiphola main road to Skotiphola access bridge to Malatji via Dr Mohlala main road |
| 4 |  |  | 1.Rietfontein |  |  | - Water maintenance/upgrading of reservoir - Fencing of cemeteries (2) - Upgrading of clinic - Speed humps near Mogalatladi School - RDP houses - VIP toilets - Paving of road to clinic - Waste collection program (EPWP) - SASSA satellite office - Library - Culvert bridge near Mogalatladi School - Disabled and Drop centre - Home Affairs satellite office - Secondary school - Storm water control - Electricity post connection (260) - Livestock dam - Grading of sports fields - Electricity post connection - Skip 2 - Tarring of road fronm Rietfontein to Mare - Tarring of road from Rietfontein clinic to Madiba - Waste collection at Rirtfontein clinic - Pedestrian road - Street lights - Donga that divides the village need to be maintained |
|  |  |  | 2.Vierfontein |  |  | - Incomplete RDP houses - RDP houses and VIP toilets - Fencing of graveyards - Tarring of road from Vleescboom to Magukubjane clinic - Clinic - Water phase 2 - Electricity post connection (63) - Sports ground - Paving of road to cemetery - Paving of internal streets - Toilets in graveyards |
|  |  |  | 3.Katlegong 4.Vierfontein E (Mashemong section) |  |  | - Primary school - RDP houses and VIP toilets - Water reticulation - Bridge - Electricity post connections (70) - Fencing of cemetery - Speed humps near taxi rank before Katlegong - Speed humps at Katlegong road - Energisation of taxi rank mast lights - Paving of internal street - Toilets and water in the graveyard - Electricity - Water reticulation - Street paving - RDP and toilets |
| 5 |  |  | 1.Maserumole Park |  |  | - Water Reservoir - Incomplete PHP houses, - Clinic, - Waste collection project - Paving of road to Magistrate offices - Mast lights - Paving of internal streets - Mobile clinic - VIP toilets - Additional classrooms at Tshwatlhakge Primary - Hall - CPWP work opportunities |
|  |  |  | 2.Mohlwarekoma |  |  | - Water yard connection - PHP houses, - Waste collection - Pay point - VIP toilets - Paving of internal streets - Skip bins - Mobile clinic - Mast lights - Fencing of cemetery - Hall |
|  |  |  | 3.Leeukraal |  |  | - Water reticulation, - PHP houses, - Additional classrooms at Phutihlogoana and Moteane Schools - Disabled centre - Tarring of road from Maserumole Park fourways to Leeukraal - VIP toilets - Mobile Clinic - Mast lights - Fencing of cemetery - Hall |
|  |  |  | 4.Matlakakatle A and B |  |  | - Water reticulation - PHP houses, - Matlakatle / Matoseng Bridge - Magale School bridge - Paving of internal roads - Mobile clinic - VIP toilets - Skip bin - Fencing of cemetery - Hall |
| 6 |  |  | 1.Eenzaam Trust |  |  | - Fencing of graveyards - Sports facilitiy - Paypoint - Pre- schools needed - Livestock dam - Bridge to Ponong - RDP houses - Sanitation - Tarring of road to Ponong via Pakaneng - Building of classrooms at Ntshebele Secondary school |
|  |  |  | 2.Patantsoane B 3. Patantshoane A |  |  | - Sports facility - Community hall - Fencing of graveyard at Mabalane - Bridge between Patantshwane A an B next to Maretele Secondary school - Tarring of road from Patantshwane A to Rietfontein (phase 3 of Rietfontein to Eensaam road) - Bridge at Patantshwane old road to Rietfontein - RDPhouses - Streets paving - Pedestrians bridge at Sekhukhuseng - Fencing of graveyard - Sports facility - Street paving - RDP houses - Stormwater drainage at main road - Sanitation both at A and B |
|  |  |  | 4.Eenzaam Kgoloko |  |  | - Community hall - Fencing of graveyard - Bridge between Kgoloko and Ga- Mmaboki - Tarring of road from main road to ZCC - Pay point - Sanitation - Sports facility |
|  |  |  | 5.Mare 6.Ga-Mmaboki 7.Ga-Diago |  |  | - Sports facility - Clinic - RDP houses - Streets paving - Community hall - Fencing of cemetery - Tarring of road from the main road to Mahlaba secondary - Fencing of graveyard - Sanitation - RDP houses - Bridge at Ga-Diago - Tarring of road from Rietfontein main road to Ga-Diago and Madiba - Electricity post connection at Ga-Madiba |
| 7 |  |  | 1.Thoto |  |  | - Clinic - Phase two water reticulation - Tarring of road from Glen cowie via Malaka to Thoto - Community service centre - Outstanding RDP houses (28) - Fencing of cemetery - Seopo School be demolished |
|  |  |  | 2.Malaka |  |  | - Sanitation - Outstanding RDP houses (5) - Clinic - Tarring of road from Glen cowie via Malaka to Thoto |
|  |  |  | 3.Ntoane |  |  | - Fencing of cemetery - Clinic - Tarring of road from Glen cowie via Malaka to Thoto - Bridge between Manotong and Ntoane - Outstanding RDP houses (7) - Extension of water pipeline and erection of reservoir |
|  |  |  | 4.Manthlanyane |  |  | - Fencing of cemetery - Water supply - Clinic - Tarring of road from Glen cowie via Malaka to Thoto |
|  |  |  | 5.Manotong |  |  | - Bridge between Manotong and Setebong - Tarring of road from Glen cowie via Malaka to Thoto - RDP houses - Clinic - Community hall - Fencing of cemetery |
|  |  |  | 6.Dikatone |  |  | - Fencing of cemetery - Clinic - Tarring of road from Glen cowie via Malaka to Thoto - Community hall - Extension of water pipeline to Ga- Mankge and Ga- Mosoma - Sanitation |
|  |  |  | 7.Setebong |  |  | - Fencing of cemetery - Tarring of road from Glen cowie via Malaka to Thoto - Sanitation - Clinic - Community hall - Maintenance of Setebong road - Skip |
| 8 |  |  | 1.Mathousand / Hlahlane |  |  | - Toilets in the cemetery - Paving of road from Hlabje to the cemetery - Stormwater drainage - Water in the cemetery - Mobile clinic - Paypoint - Pavememt from tar road Moloi to Glencowie to Gadieme |
|  |  |  | 2.Pelepele Park / Maswiakae 3.Mochadi |  |  | - Toilets in the sports ground - Primary school - Paving of Malaka to Maswiakae - Mobile clinic - Upgrading of sports facility - Water in the sports ground - Toilets in the cemetery - Water in the cemetery - Humps and stop sign at Devenhuis entrance - Paypoint - Mobile clinic - Poor network |
|  |  |  | 4.Brooklyn |  |  | - RDP houses - Pavement from fourways to Sedibeng community hall - Paypoint - Secondary school - Mobile clinic |
|  |  |  | 5. Leokana |  |  | - Tar road from R579 Moloi to paving (Marumo Tuckshop) - Paving from cemetery to the bridge - Borehole maintenance and jojo tanks - Stormwater drainage to the bridge - Mast lights - RDP houses - Maths and science centre - Water yard connections - Sanitation - Manufacturing centre - Sports facility - Mobile clinic |
|  |  |  | 6.Caprive/ Living waters |  |  | - Water yard connection - Pavement from Ga-Matjomane to the cemetery - Mobile clinic |
| 9 |  |  | 1.Riverside |  |  | - Water reticulation - Paving of road from four ways to Mpumalanga - Paving of road to graveyard (Riverside B) - Electricity post connections - Fencing and toilets (graveyard) - Clinic - PHP houses - Community hall - Street lights - Sports facilities - Mast lights - Pay points - Tarring of road from Riverside water plant to New stands graveyard - VIP toilets - Clinic - Toilets in the cemetery yard - Paving of street to cemetery and from HWY to Mpumalanga - Maintenance of valves/change |
|  |  |  | 2.Caprivi / Photo |  |  | - Water reticulation - Electricity post connections - Bridge and speed humps on R579 road - Sanitation - Waste collection - Clinic - Mast lights - Library - RDP houses - Multipurpose centre - Sports facilities - VIP toilets - Mobile clinic - Tarring of road to Photo - Tolilets in the cemetery |
|  |  |  | 3.Morgenson 4.Magapung |  |  | - Paving of road from ZCC church to Mogapung - Fencing and toilets (graveyard) - Additional PHP houses - Community hall - Street lights - Electricity post connections - Bridge between New stands and Caprive - Sports facilities - Mast lights - Pay points - Tarring of road from New stands graveyards to Riverside water plant - VIP toilets - Mobile clinic - Fencing of cemetery - Maintence (water reticulation and valves,minehalls,paved roads) - Electricity - PHP houses - Water reticulation - Regravelling of streets - Mast light - VIP toilets |
| 10 |  |  | 1.Mogorwane |  |  | - Pedestrian bridge at Mmatoti and Mmotwaneng - Water - RDP houses - Electricity post connection - Tarring of road from Mmatoti section to Ga-Maloa - Speed humps - Clinic - Fencing of cemetery - VIP toilets |
|  |  |  | 2.Moripane A and B |  |  | - Water - Road from Ngwanamatlang to Mogorwane need to be tarred - Electricity post connections - RDP houses - Clinic - Fencing of cemetery - VIP toilets |
|  |  |  | 3.Phushulang |  |  | - Bridge to link Moloi and Phushulang - Repairing of Phushulang and Maloa bridge - RDP houses - Water - Clinic - Tarring of road from Moloi via Phushulang to Marishane - Fencing of cemetery - VIP toilets |
|  |  |  | 4.Ngwanamatlang |  |  | - Water - Access roads need maintenance - Electricity post connection - VIP toilets |
|  |  |  | 5.Ngwanamatlang extension |  |  | - Water - RDP houses - Speed humps - Electricity post connection - Access roads need maintenance - VIP toilets |
|  |  |  | 5.Moloi |  |  | - Tarring of road from Moshate /Legaletlwa to Glen cowie - Water - RDP houses - Mast lights - Electricity post connections - Speed humps - Pedestrian bridge - Clinic - Fencing of cemetery - VIP toilets |
|  |  |  | 6.Moloi extension |  |  | - Electricity post connection - Water - Access roads - Fencing of cemetery - RDP houses - VIP toilets |
| 11 |  |  | 1.Molepane |  |  | - Electricity post connection - Water (RDP level 2) - Sanitation - Health centre - Work opportunities for youth e.g. CWP and EPWP - Waste management program to address the issue of waste littering |
|  |  |  | 2.Mokwete |  |  | - Access road from Mahlomola to Ngwaritsi need tarring - Water and sanitation - Work opportunities for youth e.g. CWP and EPWP - RDP houses - Regravelling of road - clinic |
|  |  |  | 3.Vergelegen A |  |  | - water and sanitation - RDP houses - Regravelling of access roads - Work opportunities for youth e.g. CWP and EPWP |
| 12 |  |  | 1.Moretsele |  |  | - Water-the whole village and extension - Roads- tarring of road from Kgagara bricks to Moshate - Electricity post connection – next to Bonega-Madikubung and Leruleng New stands - Tribal Office –Ga- Moretsele - Clinic-at Ga-Moretsele |
|  |  |  | 2.Makgeru |  |  | - Roads-tarring of road from Moshate to Kgabe cemetery - Bridge- from Moshate to Kgabe cemetery - Roads –tarring of road from Lerutla to graveyard, from Sefogole Sepeke High School to Matekane - Roads from Magoshi to Mookeng river |
|  |  |  | 3. Ratau |  |  | - Roads-tarring of road from Paile to Letamong la Tshipi,from Paile to Molakeng Primary,from Moshate to Komane, from Lutheran church to Batshweneng - Bridge – on the road from the river to Ga-Komane |
|  |  |  | 4.Makgane |  |  | - Electricity post connections at Maboneng |
|  |  |  | 5.Senamela |  |  | - Bridge- from Moshate to Ga-Magaba - Roads-from Moshate to Ga-Magaba - Tribal Office at Senamela |
|  |  |  | 6.Maphopha |  |  | - Roads – from Maphopha Moshate to Ga-Magolego - Bridge – from Maphopha to Ga-Magolego - Tribal office at Maphopha |
| 13 |  |  | 1.Tshehlwaneng (Mashengwaneng) |  |  | - Electricity post connection (400) - Water borehole needed - Water pumping machine at Section A needed - Water - Regravelling of road from Dannie scattering to Peter Nchabeleng - RDP houses - Sanitation (1500) |
|  |  |  | 2.Mogashoa Manamane |  |  | - Toilets - Bridge - RDP houses - Electricity post connections(100) - Shortage of water |
|  |  |  | 3.Mogashoa Dithlakaneng |  |  | - Bridge - Toilets - RDP houses - Capion wall next to St Engenase ZCC - Shortage of water |
|  |  |  | 4.Phase Four |  |  | - Tarring of road from Mnisi Cross to Mountain view - Electricity post connection(10) - High school needed - RDP houses - Sanitation - Shortage of water- a borehole needed |
|  |  |  | 5.Mabonyane |  |  | - RDP houses - Toilets (400) - Two bridges needed - Shortage of water - Electricity transformer to augment the current on |
| 14 |  |  | 1.Sekele |  |  | - Inaccessible roads - Incomplete RDP houses - Additional RDP houses - Inadequate water supply - Poor school infrastructure - Sports facilities - Fencing of cemetery - Sanitation - Communication problems (Poor cell phone network) - Funding of SMME and cooperatives - Mast lights |
|  |  |  | 2.Moela |  |  | - Inaccessible roads - RDP houses needed - Inadequate water supply - Poor school infrastructure - ECD building - Clinic needed - Sports facilities - Fencing of cemetery - Sanitation - Communication problems (Poor cell phone network) - Funding of SMME and cooperatives - Mast lights |
|  |  |  | 3.Kgopane |  |  | - Inaccessible roads - RDP houses needed - Inadequate water supply - Poor school infrastructure - ECD building - Clinic needed - Sports facilities - Fencing of cemetery - Sanitation - Communication problems (Poor cell phone network) - Funding of SMME and cooperatives |
|  |  |  | 4.Maloma |  |  | - Inaccessible road to Makatane High School - RDP houses needed - Inadequate water supply - Bridges needed (link bridge between Maloma village and Dingwane) - Additional classrooms at Makatane High School - Sports facilities - Sanitation - Funding of SMME and Cooperatives - Mast lights |
|  |  |  | 5.Seopela |  |  | - Tarring of road and erection of bridge on the road from Seopela Tribal Office and SASSA - Tarring of road from Seopela Tribal Office to Ga-Mohlala Lenamaneng Section - Water reticulation pipe from Mashegwana Legare pump station to Mokgoneng Section. Four tanks to store water in area also needed. - Tarring of road and erection of bridge on the road from Maripans Hotel to Mokgoneng section. - Water pumping machine and operator for Seopela - Mast lights |
|  |  |  | 6.Legapane 7.Tshesane |  |  | - Inaccessible roads - RDP houses needed - Inadequate water supply - Poor school infrastructure - ECD building - Clinic needed - Sports facilities - Fencing of cemetery - Sanitation - Communication problems (Poor cell phone network) - Funding of SMME and cooperatives - Mast lights |
|  |  |  |  |  |  | - RDP houses needed - Inadequate water supply - Bridge that links Tshesane and Dingwane - Sports facilities - Sanitation - Funding of SMME and cooperatives - Access road to royal kraal - Mast lights - EPWP opportunities |
|  |  |  | 8.Dingoane |  |  | - Inaccessible roads - RDP houses - Inadequate water - School infrastructure - Sports facilities - Sanitation - Funding of SMME and cooperatives - Bridge needed |
|  |  |  | 9.Matiloaneng B |  |  | - Inaccessible roads - RDP houses - Inadequate water - Sports facilities - Sanitation - Funding of SMME and cooperatives - Bridge needed - Mast lights - Speed hump |
|  |  |  | 10.Mabule |  |  | - Inaccessible roads - RDP houses - Inadequate water - School infrastructure - Sports facilities - Sanitation - Funding of SMME and cooperatives - Bridge needed |
|  |  |  | 11.Tsopaneng |  |  | - Inaccessible roads - RDP houses - ECD building - Sports facilities - Sanitation - Funding of SMME and cooperatives - Communication problems (Poor cell phone network) |
| 15 |  |  | 1.Mohlakaneng/Tswele |  |  | - Electricity - Water - Main road upgrading - Sanitation - ECD building - Access road to Tswele - RDP houses - Mast lights |
|  |  |  | 2.Houpakranz |  |  | - Clinic - Access roads - Water - Additional classrooms (school) - Sanitation - ECD building - Fencing of cemetery - Mast lights |
|  |  |  | 3.Mohlake |  |  | - Electricity - Water - Access roads - Fencing of cemetery - School classrooms - RDP houses - Sanitation - ECD building - Fencing of wetlands - Mast lights |
|  |  |  | 4.Magolego |  |  | - RDP houses - Electricity post connection - Water - Fencing of cemetery - Access roads - Bridges - Clinic - School classrooms - Sanitation - ECD building - Mast lights |
|  |  |  | 5.Maila Mapitsane 6.Dlamini |  |  | - Electricity post connection - Sanitation - Clinic - Water in extension - RDP houses - Bridges (low level bridge) - ECD building - Fencing of cemetery - Mast lights - RDP houses - Sanitation - Rod from Dlamini Primary School to Moela - Water - Fencing of cemeteries - Fencing of wetlands - ECD building - Clinic - Mast lights |
| 16 |  |  | 1.Dihlabaneng A |  |  | - Water- change of plastic pipe on the mainline to steel pipe to avoid illegal connections - Water reticulation to other areas - Electricity post cionnections - Clinic and paypoint - Skip bins - Speedhumps on the main road - Signage on the roads |
|  |  |  | 2.Dihlabaneng B |  |  | - High school - Three (3)hand pumps at Ngwanakwena - Two (2) bridges at Ngwnakwena - Electric pump machine and 8 jojos - Regravelling of the main street from Manganeng clinic to Dihlabaneng - Fencing of the cemetery - Sanitation - Mast lights |
|  |  |  | 3.Mashegwana Legare |  |  | - Tarring road from Mashegwana / Legare access road via Chabadietla Secondary School (Phase 3) - Tarring of road from Modipadi Bottle Store to Malatsane Dihlabaneng Section - Tarring of road from Fetakgomo Bus stop to Dihlabane Primary School - Electric water pumping machine and 8 jojo tanks |
|  |  |  | 4.Kotsiri 5.Mashegwana Tswaledi |  |  | - Tarring of road from Kotsiri to Mashegwana Tswaledi / Legare access road - Electric water pumping machine and 4 jojo tan |
| 17 |  |  | 1.Manganeng |  |  | - Access road from main road (Ramphelane) to Moshate - Manganeng/Maila Mapitsane access bridge - Mast lights - Road from Manganeng to Madirane,to Tjatane and a bridge - Fencing of cemetery - Skip bins - RDP houses - in progress - Access road from Manganeng to the purification house - Access road from Madirane to Mokadi - Work opportunities e.g. CWP and EPWP - Building of extra classrooms at Manganeng Primary School |
|  |  |  | 2.Ramphelane |  |  | - Electricity post connection - Sanitation - Water - in progress - RDP houses –in progress and still a need - Access roads - Mast lights - Skip bins - Work opportunities e.g. CWP and EPWP - Fencing of cemetery and toilets - Building of a primary school - Access road from Manganeng main road to Madibong via clinic - Community hall - Community library - Sport complex |
|  |  |  | 3.Mashite |  |  | - Access road from Dihlabaneng to Maila Mapitsane and a bridge - Access road from Ga-Seopela to Maila Mapitsane - Water - Electricity post connection - Mast lights - RDP houses - in progress - Water - in progress - Internal Access roads - Skip bins - Sanitation - Work opportunities e.g. CWP and EPWP - Community library - Access road from Mashite to Manganeng - Sports complex - Clinic / container used mobile - Maintenance of sports fields |
|  |  |  | 4.Mathibeng(Ga Toona) |  |  | - RDP houses – in progress - Sanitation - Mast lights - Skip bins - Water yard connections and maintenance - Work opportunities e.g. CWP and EPWP - Fencing of cemeteries with toilets - Road from Mathibeng to Dihlabaneng |
|  |  |  | 5.Kgolane |  |  | - Water - Electricity post connections - RDP houses- in progress and still a need - Health centre - Internal Access roads - Sanitation - Fencing of cemetery and toilets - Mast lights - Skip bins - Work opportunities e.g. CWP and EPWP - Building of crèches :Dihobolong and Sepeke creches |
| 18 |  |  | 1.Jane Furse RDP |  |  | - Access road from R579 road to Moripane - Access road from Jane Furse Comprehensive School to Jane Furse RDP - Maintenance of mast lights - RDP Primary School (Emis no 996606203)as approved in 2010 - Regravelling of Gwede Mantashe road - Regravelling of internal roads - Maintenance of sewerage system - Issueing of title deeds - RDP cemetery |
|  |  |  | 2.Vergelegen B |  |  | - Access road from Mapogo a Mathamaga Offices to Helpmekaar funeral parlor - Access road from Kwena Midas to Hlatlolanang - High mast lights - Tarring of road between Morena complex and Galitos - Patching of Kalafong road - Completion of fencing of Vergelegen B cemetery and erection of gate - Skip next to St Marks School |
|  |  |  | 3.Dicheoung |  |  | - Kgapamadi bridge that links Moraba, Moretsele and Dichoeung village with clinic,Matsebong High and Eskom sub station - Moletsi bridge that link Dichoeung village with clinic,Matsebong High - Maintenance of mast lights at Jane Furse taxi rank - Access road from Bafedi Primary to Eskom substation - Access road from Mohloba Driving School to join Bafedi to Jane Furse Eskom Sub-station - Road from Rakgoadi Bakery to new Municipal Offices - Access roads - Water crisis at zone 5 - Electricity and mast lights - Fencing of Dicheoung cemetery - Tarring of road to the cemetery - RDP houses needed - VIP toilets - Community hall - Road from Bogopa shop to old Ratseke shop be tarred |
|  |  |  | 4.Moraba |  |  | - Access road from old post office to manepu river - Access road from the new bridge to grave yard - Access road from old post office to Kgapamadi - High Mast lights - Fencing of wetland - Finishing of Moretsele Dicheoung link road - Tribal hall |
| 19 20 |  |  | 1.Madibong (Malaeneng,Sechabeng,Ga- Mokgwatsane,Sekhutlong and Masiolong) |  |  | - Malaeneng section:Water,electricity post connection, access roads, mast lights,RDP houses, Sanitation and skip - Sechabeng section: water and RDP houses - Mokgwatsane section:Water,electricity post connections, access roads, mast lights,RDP houses, sanitation and skip - Sekhutlong section:Water,electricity post connection, access roads,RDP houses and skip - Maswiolong section:water,access roads, mast lights,RDP houses and skip |
|  |  |  | 2.Mamone (Matsoke) |  |  | - Water - Access roads - Sanitation - Work opportunities e.g. CWP and EPWP - RDP houses - Skip |
|  |  |  | 1.Tisane |  |  | - Clinic at Belabela - Water system upgrade - Community office at Moshate - Bridge on the road from Belabela to Makgopong river (Ngwaritsi) - Sign boards on R579 road - Tarring of road from Mankoane Trading Store to Tisane Mohlakaneng - Factory centre - VIP toilets (1000) - Tisane community park - Electricity post connection (700) - EPWP and CWP work opportunities - Skip bins (02) - Low level bridge on the road from Belabela to Mohlahedi Primary School - Low level bridge from Tisane Extension to Tisane Motel - RDP houses (50) - Tarring of road from Sebaka shop to Lobethal - Mast lights (02) - Speed humps from Seraki shop to Ngwaritsi river (R579) |
|  |  |  | 2.Mamone(Rantho) |  |  | - RDP houses (200) - VIP toilets (200) - Mast lights (02) - Skip bins (02) - EPWP &CWP work opportunities - Fencing of cemetery at Manyeleti - Tarring of roads from R579 to cemetery (Seraki shop to Manyeleti cemetery,Malapela shop to Manyeleti) - Tarring of road fro CJC church to moshate (Rantho) - Rantho and Magolaneng Multi-purpose centre - Electricity post connections (200) |
|  |  |  | 3.Magolaneng |  |  | - RDP houses (150) - VIP toilets (300) - Mast lights (02) - Skip bins (02) - EPWP &CWP work opportunities - Tarring roads (roads from Sebaka to Magolaneng cemetery,Matlala to Mgolaneng,Mapoteng to Mgolaneng cemetery - Building of Primary school |
|  |  |  | 4.Mamone (Manyeleti) |  |  | - RDP houses (150) - VIP toilets (200) - Mast lights (02) - Skip bins (02) - EPWP&CWP work opportunities - Tarring of roads (Manyeleti to fourways supermarket,road from Super Market to Manyeleti cemetery,road from ZCC church to Manyeleti, - Upgrading of level bridge from Manyeleti to Makubarate School |
|  |  |  | 5.Mamone centre extension |  |  | - RDP houses (1000) - VIP toilets (1000) - Mast lights (02) - Skip bins (04) - EPWP&CWP work opportunities - Electricity post connection (200) - Extending of Pedi Mamone Community hall - Mini stadium in Mamone - Tarring of roads (Mamone clinic to Ngwanatshwane Secondary School,ZCC church to Sekwati Sports Ground |
| 21 |  |  | 1.Mamone- Matsoke |  |  | - High mast lights - 205 VIP toilets - Electricity post connection (15) - RDP houses (15) - Skip bin - Stromwater drainage control between Matsoke graveyard passing Tenyane High School and Motlokwe Primary School - Extension of pipelines and community water taps - Fencing of Matsoke graveyard - Work opportunities e.g CWP and EPWP - Access bridge between Matsoke to Ntswelemotse |
|  |  |  | 2.Mamone –A 1 Bothas (Ga-Mohlala) |  |  | - 405 VIP toilets - RDP houses (8) - Waste collection - Water - Equipped Malekutu borehole - Fencing of Thapedi graveyard - Maintain internal roads - Access bridge between Bothas- Ntswelemotse - Regravelling of road from Malekutu High School o Magoro cafe |
|  |  |  | 3.Mamone –A 2 (Ga-Mohlala) 4.Mamone –A3 (Ga-Manyaka) 5.Mamone –A4 (Tanzania) |  |  | - Water - Electricity post connections next to Makubarete Primary School - RDP houses (15) - VIP toilets (380) - Equip borehole and install water tank on Makabjane borehole and make sure purification plant works - Maintain internal roads - Water - VIP toilets (618) - Internal roads maintenance - Electricity post connection (130) - RDP houses (25) - Work opportunities - Clinic /mobile mobile - Fencing of Kgomogoroga gaveyard - Build water reservoir next to steeltank - Waste collection - Water - VIP toilets (200) - RDP houses (05) - Access road and bridge to new graveyard - Waste collection - Work opportunities - Bursaries and opportunities - Burasries and internship - Maitanence of sports ground |
| 22 |  |  | 1.Malegale (Sebitje) |  |  | - RDP houses (20) - Clinic - Electricity post connections - Water reticulation - VIP toilets - EPWP work opportunities |
|  |  |  | 2.Sebitjane |  |  | - RDP houses (20) - Electricity post connections - Water reticulation - VIP toilets - EPWP work opportunities |
|  |  |  | 3.Lekgwareng |  |  | - RDP houses (15) - Access road to Tjatane - Clinic - Community hall - VIP toilets - EPWP work opportunities |
|  |  |  | 4.Tjatane |  |  | - RDP houses (20) - Clinic - Bridge at Mmadirane - Access road to Mmadirane - Community hall - VIP toilet - Access road from Seraki High School to Lekgwareng - EPWP work opportunities |
|  |  |  | 5.Tjatane Extension |  |  | - RDP houses (20) - Tarring or paving of main streets - Clinic - Primary and Secondary schools - VIP toilets - Electricity - Water reticulation - Reservoir - EPWP work opportunities |
|  |  |  | 6.Madibaneng (Matolokwaneng) |  |  | - RDP houses (20) - Electricity post connection - Bridge - Secondary school - VIP toilets - Clinic - Tarring/paving of road from Matolokwaneng to Lehlabile - Water reticulation - EPWP work opportunities |
|  |  |  | 7.Greater Madibaneng |  |  | - Cell phone network (tower needed) - Bridge to Pebetse school - Tarring or paving of Access road to Ga- Mphakane - Electricity post connection - Water reticulation - Bridge from Moshate to Lekentle school - Community hall - EPWP work opportunities |
| 23 |  |  | 1.Maila Segolo |  |  | - Road from Madibong to Maphanama - Clinic - Renovation of Maila Primary and Mphele Secondary School - RDP houses - Fencing of cemetery - High mast lights - Water pump machine (big) - Renewal of tribal office - Sports facilities e.g tennis court - Community hall - ECD building - Skip Bin - Electricity post connection - Access road to Sebitlole village - Access road from Maila Taxi Rank to Dinotji village be tarred - Demacartion of sites - Bridge from Maila to Dinotji be improved - Water reticulation - VIP toilets - Education :multi purpose centre community library - Acknowledgement of heritage sites - Storm water drainage at Taxi rank - Disabled and Drop centre - Livestock dam at Leseleseleng site - Funding of SMME and corporatives |
|  |  |  | 2.Dinotji |  |  | - Senior secondary school - Big bridge to Maila Segolo village across Pshirwa river - Access road from Mathibeng via Dinotji to Maila Segolo be tarred - Electricity post connection - ECD building - Mast lights - Community paypoint - Additional classrooms to Dinotji Primary School - Renovation of old building blocks at Dinotji Primary School - School furniture - A bridge to new cemetery - Fencing of old cemetery with mash wire(1.8m) - Sanitation - Work opportunities e.g corporatives - Paving access road to old cemetery - Access road to Sebitlole - Clinic - Fencing of agricultural land - RDP houses - Access road from Dinotji to Sebithome be graded |
|  |  |  | 3.Mathibeng |  |  | - Access road from Mathibeng to Matolokwaneng village - Access road from Mathibeng to Maseleseleng village access road from Mathibeng to Dinotsi village - Crush pen - Animal water catchment dam - Pensioners paypoint - Sanitation (VIP toilets) - Windmill operated borehole - High mast lights - Water - Electricity post connection - Clinic - Access road to Sebitlole - RDP houses - New water reservoir - Community hall - Work opportunities e.g EPWP - Recreational facilities |
|  |  |  | 4.Marulaneng |  |  | - Electricity post connection - Water supply (Difahlane ) reservoir - RDP houses (additional) - Streets paving - Primary school (Sekgwarapaneng) - Work opportunities - High mast lights - Sanitation toilets - Water infrastructure old(new water reticulation needed) - Access road to new clinic be tarred - Fencing and extension of cemetery - Community hall - Access bridge to Thulare Primary School - Access bridge be built between new clinic and Maila Segolo main road - Access road from Marulaneng to Manganeng be graded and tarred - ECD building - Incomplete RDP houses |
|  |  |  | 5.Mashupye |  |  | - Sanitation - Access road - Work opportunities e.g CWP and EPWP - Skip - Electricity post connection - High mast lights - Cemetery fencing - RDP houses - ECD building - Water pumping machine (big) - Bridge to new stands - Sports facilities - Mobile clinic - Additional classrooms (block)at Maphale Primary School - Community hall |
|  |  |  | 6.Maseleseleng /Sebitlule |  |  | - Access road from Maila Segolo main road to Maseleseleng village be tarred - Access road from Sebitlol to Maila Segolo - Access road from Sebitlole to Dinotji village - Access road fro Maseleseleng to Mathibeng village - A bridge to Mathibeng - Electricity post connection - Water reticulation to new stands - Revival of old water hand pumped borehole - Culvert bridge at Maseleseleng entrance - Revival of SASSA services - Sanitation - High mast lights - Work opportunities e.g CWP and EPWP - Skip - Community library |
| 24 |  |  | 1.Diphagane |  |  | - Water - VIP toilets - Electricity post connection - RDP houses - Mast lights - Regravelling of road from Rantobeng crossing joining Maololo access bridge - FBE - Food parcels - Skip bins - Work opportunities e.g. CWP and EPWP - Mobile clinic - Fencing Moretlwaneng cemetery |
|  |  |  | 2.Phaahla |  |  | - Water - Tarring of Phaahla to Masehlaneng - VIP toilets - Mast lights - Work opportunities e.g. CWP and EPWP - Electricity post connections - FBE - Social worker stationed in clinic - RDP house |
|  |  |  | 3.Masehlaneng 4.Lobethal |  |  | - Roofing of community hall - Water - Fencing of cemetery - Electricity post connections - RDP houses - VIP toilets - Mobile clinic - Tarring of road from Masehlaneng to Vlaka - Skip bin - Mast lights - EPWP opportunities - VIP toilets - High mast lights - Regravelling of main road to Ngwaritsi river - Fencing of cemetery - Food parcels - Tarring of road from Lobethal to Tisane - Skip bin |
|  |  |  | 5.Mamoshalele |  |  | - Low level bridge at Sedibeng - RDP houses and VIP toilets - Regravelling of road from Busstop to new bridge joining the Old Lobethal road - Mast lights - Matsebe road to new bridge be taken care of - Toilets needed in the civic hall - Food parcels - FBE - Road from new clinic to Matete Tuck Shop need to be taken care of - Work opportunities e.g EPWP and CWP |
|  |  |  | 6.Porome |  |  | - Electricity post connection - VIP toilets - Mast lights - Regravelling of road from main road to the river and primary school - Work opportunities e.g EPWP and CWP - Food parcels - FBE |
|  |  |  | 7.Mamatjekele |  |  | - Fencing of cemetery - Water reticulation - Regravelling of road from Moshate to Mamatjekele road - RDP houses - Network for cellphones - Mast lights - FBE - Food parcels - Work opportunities e.g EPWP and CWP - Mobile clinic |
| 25 |  |  | 1.Maololo |  |  | - Tarring of road from Diphagane-Maololo until Mamatjekele/Mohloding - Water - State of the art clinic - Community hall - Sports complex - Fencing of graveyard - ECD centre - Sanitation to qualifying households - RDP houses to all indigents households - Electricity post connection at new stands - VIP toilets - Road from Mphanama cross to Masetlwe to Maololo - Electrification of borehole |
|  |  |  | 2.Mashabela (Malegasane) |  |  | - RDP houses - Mast lights - Regravelling of access roads in all villages - Construction of small bridge at Phaswane - Developing of all sports grounds - Construction of water outlet pipe - Mobile clinic at Ga-Kgari - Water to households in all villages - Sanitation in all households that has no toilet - Regravelling of Kgari road - Community hall - Drilling of new borehole |
|  |  |  | 3.Mohwelere |  |  | - Water in all households - Roads from Modipadi to Kelekele need to be tarred with small bridge around new stand - Sanitation in all households - RDP houses to indigent households - Internal roads need to be regravelled /tarred and bridge near the clinic - Electricity post connection - Sports complex needed - Speed humps from Ntompi-Molebeledi - Community hall - Fencing of graveyard - VIP toilets - Blading /Grading of Mohwelere- Marodi road |
|  |  |  | 4.Molebeledi |  |  | - Water - Road from Makataneng (Molebeledi cross) to Mohloding passing all the way to Masehlaneng need to be tarred /regravelled - Sanitation - Road from Mohwelere via Magate to Molebeledi need to be tarred - RDP houses to indigents - ECD centre - Community hall - Clinic - Sports complex - Electricity post connections - Three small bridges at Tswetleng - Electrification of borehole |
|  |  |  | 5.Machacha |  |  | - Tarring of road from Mphanama cross to Machacha Moshate - Water - Electrification of borehole - State of the art clinic - Community hall - Sports complex - Fencing of graveyard - Sanitation - ECD centre - RDP houses - Electricity post connection at new stands - Road from Machacha Moshate to Mashabela (Mogofele /Lepellane) - Road from Machacha to Thabampshe |
|  |  |  | 6.Ga Selepe |  |  | - Sanitation - Water - Road from Mamone via Selepe all the way to Talane need Regravelling - ECD centre - Sports complex - Community hall - Road from Selepe to Mashabela need constructed - RDP houses - Electrification of borehole |
|  |  |  | 7 Ga Marodi |  |  | - Water - Sports complex - Clinic - Small bridges on Talane and Marodi roads - Electricity post connections - Sanitation - State of the art school at Madikalepudi Secondary School - ECD centre - RDP houses - Road from Marodi to Mampe (Mohwelere) need regravelling |
|  |  |  | 8.Mapulane /Talane |  |  | - Tarring of Mphanama cross road to Machacha - Extention of reticulation - Construction of bridge to Kgari - Electrification of households - Fencing of graveyard - Clearing of dams - Sports centre - VIP toilets |
|  |  |  | 9.Mahlakanaseleng |  |  | - Regravelling of internal road - RDP houses - Sanitation - EPWP - Water – improving reticulation - Fencing of graveyard - VIP toilets |
| 26 |  |  | 1.Mathapisi |  |  | - Water –extension of pipes - Access road - Tarring of Mathapisa to Vlak road - RDP houses (25) - VIP toilets - Electricity post connection (50) - Pay point - Fencing of Moeding wa Mahea cemetery |
|  |  |  | 2.Thabeng |  |  | - Water –extension of pipes - RDP houses (15) - Electricity post connection - VIP toilets - Tarring of Soetveld to Thabeng road (6,4km) - Fencing of wetland |
|  |  |  | 3.Kgarethuthu |  |  | - Water – replacement of diesel pump to electricity - Roads- tarring of Soetveld to Thabeng road - VIP toilets - RDP toilets - Electricity post connection - Renovation of Kgaruthuthu Primary - Fencing of cemetery |
|  |  |  | 4.Soetveld |  |  | - Water-extension of pipes - Road –tarring Soetveld to Thabeng road (6.4km) - VIP toilets - RDP houses (25) - Electricity post connection - Crèche at Mabuke - Soetveld bridge |
|  |  |  | 5.Marishane |  |  | - Mast lights at Luka four ways stop - Electricity post connection - RDP houses (240) - VIP toilets - Road – tarring Makgopho to Phaahla Machollele road -Seloane to Pholosho café - Water – extension of pipes |
|  |  |  | 6.Marishane (Bothaspruit) |  |  | - Water-extension of pipes - Mohlakaneng bridge - Electricity – new extensions - VIP toilets - RDP houses (10) - Fencing of cemetery at Mohlotlane - Tarring of Bothaspruit road to Ga-Moloi |
|  |  |  | 7 Makgophong /Porome |  |  | - Access road - Electricity post connection - RDP houses - Water reticulation |
| 27 |  |  | 1.Mabopane |  |  | - Regravelling of Masemola clinic to Thabampshe cross road - Road from Molomoatau Secondary to Machasdorp also need to be regravelled /tarred / paved - Fencing of graveyard - Water reticulation - RDP houses - Road from Moshidi Bottle store to Moshate needs regravelling / some section of the road - Grading of roads |
|  |  |  | 2.Manare |  |  | - Water reticulation - RDP houses - Grading of communal roads - Water pipes between Ga-Mokalapa/Lepule or pedestrian crossing bridge |
|  |  |  | 3.Mohloding |  |  | - Fencing of graveyard - Water reticulation (very critical and need urgent attention) - Regravelling of Moshate to Mohloding road - RDP houses - Electricity extension at Mohloding - Water pipes next to school |
|  |  |  | 4.Masemola (Moshate) |  |  | - Road from Masemola clinic to Masemola tribal office needs speed humps - Water reticulation - Grading of communal streets - RDP houses - Electricity extension at Maripane - Fencing of Mapoteng cemetery - 06 waste bins (Moshate,Mohloding and Manare) - Building of new classrooms at Mahwetse Secondary |
|  |  |  | 5.Thabampshe Cross extension (Mabopane) |  |  | - Apollo lights at Thabampshe cross,Old Moshate tribal office and Masemola clinic - Electricity - Water reticulation - Grading of roads - Sanitation |
| 28 |  |  | 1.Thabampshe |  |  | - Dithabeng bridge - FBE - Vodacom network - High Mast lights - Fencing of cemetery (3) - Post office - Upgrading and fencing of Sehlale dam - Fencing of Sehloaneng wetland - Communty hall - Intervention on all community projects |
|  |  |  | 2.Tswaing |  |  | - High Mast lights - Vodacom network - Water - Skip load next to clinic - Community hall - FBE - Electricity post connection - Regraveling of streets |
|  |  |  | 3.Ga- Maphutha |  |  | - Tarring of road from Ga-Maphutha to Pitgouws dam - Water reticulation - Fencing of cemetery and toilets - High Mast lights - FBE - RDP houses (15) - Community hall - Tarring of road from Ga-Maphutha to Mahubitswane |
|  |  |  | 4.Wonderboom |  |  | - Fencing of Mabodibeng wetland - Clinic - Water - Electricity post connection (100) - High Mast lights - Vodacom network - Tarring of road to gate one |
|  |  |  | 5.Maroge |  |  | - Water - Fencing of wetlands (2) - High Mast lights - RDP houses (40) - Primary school - Electricity post connection - FBE - Intervention on all community projects |
|  |  |  | 6.Mahubitswane |  |  | - Mast lights - Community hall - Vodacom network - Water reticulation - Electricity post connection - RDP houses (40) - Skip |
|  |  |  | 7.Mahlakole |  |  | - Fencing of wetlands (2) - Water - High Mast lights - Skip - RDP houses (15) - Community hall - Intervention on all community projects |
|  |  |  | 8.Vlakplaats |  |  | - Mast lights - Fencing of cemetery - Vodacom network - Water - Primary school - RDP houses |
| 29 |  |  | 1.Malope |  |  | - Tarring of road from Malope to Phokoane - Fencing of graveyard - Water shortage - Clinic - RDP houses (30) - Irrigation scheme funding |
|  |  |  | 2.Molelema |  |  | - Shortage of water - RDP houses (20) - Regravelling of road - Administration Office needed at Khudutseka Primary School |
|  |  |  | 3.Mahlolwaneng |  |  | - Regravelling of road from Masemola clinic to Mahloloaneng - Electricity post connection (new stands) - Fencing of graveyard - Clinic needed - RDP houses - Road from Mahloloaneng to Pitjaneng need tarring - Fencing of camp - Mahloloaneng Primary School need new building - Mathume high school need new building |
|  |  |  | 4.Mashoanyaneng |  |  | - Fencing of graveyard - Road from Mashonyaneng to Pitjaneng - Pay point - Shortage of water - RDP houses (35) - Clinic - Matshele high school need new building - Sushu Primary School need new building - Electricity post connections |
|  |  |  | 5.Maraganeng |  |  | - Shortage of water - RDP houses (7) - Clinic - Regravelling of road - Electricity post connections |
|  |  |  | 6.Pitjaneng |  |  | - RDP houses (15) - Shortage of water - Fencing of graveyard - Road from Pitjaneng to Mahloloaneng need tar - Electricity post connections |
|  |  |  | 7.Machasdorp |  |  | - Shortage of water - Electricity post connection - RDP houses (16) |
|  |  |  | 8.Mphane |  |  | - Road from Mphane to Makgwabe need to be tarred - Electricity post connection (new stands) - Shortage of water - Clinic - RDP houses (14) - Fencing of camp - Irrigation scheme need funding - Mampurutseka school need new building |
|  |  |  | 9.Makgwabe |  |  | - Road from Makgwabe to Mphana need tarring - Electricity post connections - Shortage of water - Clinic - RDP houses (10) - Fencing of camp - Makgwabe Primary School need new building - Maphadime High School need new building |
| 30 |  |  | 1.Krokodile |  |  | - Water - Mast lights - RDP houses - Access road from tarred road to Motsatsi - Windmill - Pay point - Clinic - Revival of agricultural fields - Cleaning of livestock dams |
|  |  |  | 2.Setlaboswane |  |  | - Mast lights - Paving of roads - Pay point - Fencing of graveyard |
|  |  |  | 3.Legotong |  |  | - Tarring of road from Legotong to Mogaladi - Access road from Mogaladi to Legotong - Access road from Legotong to Makhutso - Clinic - Fencing of graveyard |
|  |  |  | 4.Serageng |  |  | - Tarring of road from Motseleopo to Mogaladi New stands - RDP houses - Mast lights - Pay points - Network (cell phone) - Fencing of graveyard |
|  |  |  | 5.Masanteng |  |  | - Water - Tarring of road from Mariri dam to Mogaladi tar road - Bridge - Mast lights - Community hall - Paving of one street in the village - RDP houses - Fencing of graveyard - Pay point - clinic |
|  |  |  | 6.Mogaladi |  |  | - water - pay point - fencing of graveyard - library - windmill - mast lights - access road from Molwetsi Secondary School to Phaahla Moshate - satellite police station |
| 31 |  |  | 1.Kome |  |  | - Mmotwaneng and Kome main street need to be tarred - Road from Ga-Mapurunyane to Kome Ga- Copper need to tarred - VIP Toilets needed - RDP houses - Work opportunities e.g CWP and EPWP - Extension of water pipe to the new stands - Community hall - Fencing of cemetery - Electricity post connection - Mamokgasefoka clinic be build |
|  |  |  | 2.Ntshong |  |  | - RDP houses - VIP Toilets - Community hall - Fencing of cemetery - Livestock dams - Electricity post connection - Tarring of road from Good Hope to Masakeng paypoint - MTN aerial - Work opportunities e.g CWP and EPWP - Regravelling of internal roads |
|  |  |  | 3.Mmotwaneng |  |  | - Water pipe extension to new stands - Community hall - Refilling of sol within street of Kome and Mmotwaneng - Malope to Phokoane road need to be tarred - Mamokga Sefoka clinic - Fencing of cemetery - Electricity post connection - Work opportunities e.g CWP and EPWP |
|  |  |  | 4.Masakeng |  |  | - RDP houses - VIP toilets - Community hall - Regravelling of internal streets - Regravelling of road from Motseleope to Phokoane road - Fencing of cemetery - Electricity post connection - Drilling of water borehole - Small bridge from Mapurunyane (Lebesane bridge)between Motoaneng and Masakeng |
|  |  |  | 5.Mangwanyane |  |  | - Bridge between Mangwanyane and Good hope - RDP houses - VIP Toilets - Fencing of cemetery - Extension of water pipes to new stands - Livestock dams - Electricity post connection - Community hall - Paypoint - Tarring of road from Malope to Phokoane - Work opportunities e.g CWP and EPWP - Small bridge from newsstands to Mangwanyane - Regraveling of internal streets - 3 RDP houses incomplete |
|  |  |  | 6.Vlakplaas |  |  | - RDP houses - VIP toilets - Bridge on the road from Vlakplaas to Mantsi cemetery - Electricity post connection - Tarring of road from Kome to Vlakplaas - Tarring of road from Mathapisa to Vlakplaas village - Bridge on Mohlarong river - Sustainable water supply - Supplement of existing RDP houses - Construction of bridge from Vlakplats to Manchi to the graveyard - Community hall - Fencing of cemeteries - Work opportunities e.g CWP and EPWP - Mamokgasefoka clinic - Maintenance of internal roads - Mini post office |
|  |  |  | 7.Eenkantaan |  |  | - Fencing of cemetery - Extension of water pipe - VIP toilets - RDP houses - Electricity post connection - Skip bins - High mast lights - Multi purpose centre - Tarring of road fro Mampane Tribal Office to Sehuswane T junction - Work opportunities e.g CWP and EPWP - Rgravelling of internal roads - Livestock dam - Drilling water borehole |
|  |  |  | 8.Motseleope |  |  | - RDP houses - VIP toilets - Work opportunities e.g CWP and EPWP - Tarring of road from Kome to Motseleope - Regravelling of internal roads - Extension of water pipe - Electricity post connection - Mobile clinic - Skip bins - Bridges (Senyane,Mashikare and Thope - Community hall |
|  |  |  | 9.Makhutso |  |  | - Access road from Eenkantaan to Makhutso need tarring - Road fromMakhutso to Semahlakole - RDP houses - High mast lights - Extension of water pipe - Community hall - Work opportunities e.g CWP and EPWP - VIP toilets - Paypoint - Access road from Makhutso to Mogaladi - Electricity post connections - Bridge between Makhutso and Legotong - Mobile post office - Skip bin - Road from Makhutso to Kome |
|  |  |  | 10.Semahlakole /Sehuswane |  |  | - Community hall - Paypoint - Regravelling or soil filling - Fencing of Semahlakole cemetery - Fencing of Sehuswane cemetery - Road from Semahlakole water reservoir to Makhutso bridge via Bodimong - Water boreholes 3 - RDP houses 20 - VIP toilets 40 - Water reticulation at Semahlakole and Sehuswane |

## CHAPTER 3: SITUATIONAL ANALYSIS

### 3.1 Introduction

### This chapter provides a situational analysis of the existing trends and conditions in Makhuduthamaga Municipality, in accordance with the requirements of the Municipal Systems Act in developing an IDP.

### 3.1.1 Geographical Location

The Makhuduthamaga Municipality is a Category B4 municipality that is located within Sekhukhune District Municipality (SDM) of the Limpopo Province. Category B4 municipalities  are municipalities which are mainly rural with communal tenure and with, at most, one or two small towns in their area.( COGTA 2009) The Municipality is completely rural in nature, dominated by traditional land ownership and comprises of a land area of approximately 209 695 ha (at a low average density of 1, 3 persons per ha). It is made up of 189 settlements with a population of 274 358 (Census 2011) or 283 958 (Community Survey 2016) people and 65 217 (Census 2011) or 64 769(Community Survey 2016) households, which amounts to more than 24% of the District 1169 762 (Community Survey 2016).Like most rural municipalities in the Republic of South Africa, Makhuduthamaga is characterized by weak economic base, poor infrastructure, major service delivery backlogs, dispersed human settlements and high poverty levels

Makhuduthamaga is linked with Elias Motsoaledi and Ephraim Mogale Municipalities to the south via routes R579 and R33, and with Fetakgomo Tubatse Municipality to the north-east via route R555. The R579 - a provincial road - is currently the main route used for passengers and goods to support economic activities in the municipality.

History behind the name

Makhuduthamaga: Literally means “executives”, this was a term used to denote members of the Fetakgomo movement in the 1950s.

### Makhuduthamaga Local Municipality Geographic Location

3.1.2 Population Trends

The MLM has a total population of 274 358 (Census 2011) or 283 958 (Community Survey 2016) people, or 65 217 (Census 2011) or64 769 (Community Survey 2016) households.  It is the second largest municipality in the Sekhukhune District in terms of population figures, with 24% of the District population living in the MLM (Community Survey 2016)

According to Census 2011 figures, the MLM has a fairly young population, with 38% being younger than 15 years, 54% between 15 and 64 years of age, and only 8% being older than 65.  This age spread in the population means that the dependency ratio in the MLM is fairly low, with 85, 4 dependants per 100 economically active people.  The area is experiencing very low population growth. In 2001, the annual growth rate was -0, 55%, which has increased to 0, 46% in 2011, which is still very low. However, the number of households have increased from 52 978 households in 2001 to 65 217 households in 2011.  This trend is partly due to a decrease in household size (i.e. it could be a sign of households splitting up, resulting in a higher number of households despite very low total population growth). The average household size has decreased from 4.9 in 2001 to 4.2 in 2011.  A growth in household numbers is significant for planning purposes as each household has needs such as housing and basic services.

Levels of education in the MLM community are low, with 23,4% of persons 20 years and older having had no schooling, 20.6% having completed some level of high school, and 5.5% completing high school (Matric).  The schooling situation has improved since 2001, when 44.3% of people older than 20 never attended school.

Migration

There is significant out-migration of people from Makhuduthamaga to urban areas for reasons, inter alia: access to better opportunities such as jobs, access to better social amenities and facilities in urban areas such as higher educational facilities, universities, schools, hospitals (better health care services), good roads, water etc

Table: MLM Distribution of population by age and sex

| Age group | 1996 |  |  | 2001 |  |  | 2011 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Total | Male | Female | Total | Male | Female | Total |
| 0-4 | 18 135 | 18 346 | 36 481 | 15 549 | 15 752 | 31 301 | 19 333 | 18 891 | 38 224 |
| 5-9 | 21 067 | 20 674 | 41 741 | 19 041 | 18 985 | 38 026 | 17 032 | 16 998 | 34 030 |
| 10-14 | 20 915 | 21 271 | 42 186 | 20 109 | 20 354 | 40 463 | 16 582 | 15 600 | 32 187 |
| 15-19 | 16 748 | 17 391 | 34 139 | 18 048 | 18 976 | 37 024 | 16 840 | 16 451 | 33 292 |
| 20-24 | 9 574 | 12 627 | 22 201 | 9 483 | 12 275 | 21 758 | 11 129 | 12 426 | 23 555 |
| 25-29 | 5 316 | 8 829 | 14 145 | 5 116 | 9 133 | 14 249 | 7 073 | 10 605 | 17 679 |
| 30--34 | 4 141 | 7 992 | 12 133 | 4 022 | 7 346 | 11 368 | 5 191 | 8 808 | 14 000 |
| 35-39 | 3 660 | 6 834 | 10 494 | 3 671 | 7 220 | 10 891 | 4 510 | 7 998 | 12 508 |
| 40-44 | 3 054 | 5 995 | 9 049 | 3 289 | 6 266 | 9 555 | 4 043 | 7 114 | 11 157 |
| 45-49 | 2 594 | 5 312 | 7 906 | 2 811 | 5 781 | 8 592 | 3 538 | 6 863 | 10 401 |
| 50-54 | 1 997 | 4 685 | 6 682 | 2 644 | 5 341 | 7 985 | 3 188 | 5 780 | 8 968 |
| 55-59 | 2 082 | 4 081 | 6 163 | 1 980 | 4 551 | 6 531 | 3 125 | 5 326 | 8 451 |
| 60-64 | 1 657 | 3 854 | 5 511 | 2 264 | 4 275 | 6 539 | 2 811 | 4 969 | 7 780 |
| 65-69 | 1 940 | 3 940 | 5 880 | 1 672 | 3 599 | 5 271 | 2 056 | 4 895 | 6 950 |
| 70-74 | 1 180 | 2 058 | 3 238 | 1 730 | 3 617 | 5 347 | 2 134 | 3 540 | 5 674 |
| 75-79 | 1 103 | 2 104 | 3 207 | 958 | 1 696 | 2 654 | 1 082 | 2 533 | 3 515 |
| 80-84 | 513 | 1 105 | 1 618 | 763 | 1 763 | 2 526 | 802 | 2 165 | 2 966 |
| 85+ | 355 | 980 | 1 335 | 458 | 1 456 | 1 914 | 663 | 2 057 | 2 721 |
| Total | 116 038 | 148 082 | 264 120 | 113 613 | 148 392 | 262 005 | 121 133 | 153 021 | 274 154 |

Source: Census 2011

Table: Population by functional age group and sex – 1996, 2001 and 2011

| MLM | 1996 |  |  | 2001 |  |  | 2011 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Total | Male | Female | Total | Male | Female | Total |
| 0-14 | 60 534 | 60 747 | 121 282 | 54 700 | 55 093 | 109 793 | 52 967 | 51 500 | 104 466 |
| 15-64 | 51 085 | 77 981 | 129 065 | 53 332 | 81 167 | 134 499 | 61 579 | 86 385 | 147 964 |
| 65+ | 5 108 | 10 234 | 15 342 | 5 582 | 12 132 | 17 714 | 6 737 | 15 191 | 21 928 |
| Total | 116 727 | 148 962 | 265 689 | 113 614 | 148 392 | 262 005 | 121 283 | 153 076 | 274 358 |

Source: Census 2011

Table: Population growth rates – 1996–2011, 2001–2011 and 2011-2016 (CS)

| Total Population |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1996 | 2001 | % change | 2011 | % change | 2016 CS |
| 269 313 | 262 005 | - 0;6 | 274 358 | 0;5 | 283 956 |

Source: Census 2011 and Community Survey 2016

Employment profile for Makhuduthamaga

| Employed | 19534 |
| --- | --- |
| Unemployed | 32780 |
| Discouraged work seeker | 13657 |
| Other not economically active | 81993 |
| Not applicable | 126 394 |
| Grand Total | 274 358 |

Source: Census 2011

MLM Population aged between 15 and 64 years by employment status – 1996, 2001 and 2011

| Employed |  |  | Unemployed |  |  | Unemployment rate |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 |
| 12 409 | 10 686 | 19 254 | 29 370 | 32 174 | 32 662 | 70,3 | 75,1 | 62,9 |

Source: Census 2011

Makhuduthamaga Local Municipality annual Income levels

| Wards | No income | R 1 - R 4800 | R 4801 - R 9600 | R 9601 - R 19 600 | R 19 601 - R 38 200 | R 38 201 - R 76 400 | R 76 401 - R 153 800 | R 153 801 - R 307 600 | R 307 601 - R 614 400 | R 614 001 - R 1 228 800 | R 1 228 801 - R 2 457 600 | R 2 457 601 or more |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 206 | 195 | 387 | 597 | 530 | 189 | 115 | 102 | 50 | 12 | 5 | 2 |
| 2 | 74 | 109 | 227 | 534 | 499 | 153 | 41 | 25 | 5 | 1 | 0 | 0 |
| 3 | 226 | 194 | 308 | 637 | 587 | 216 | 208 | 139 | 39 | 9 | 4 | 1 |
| 4 | 255 | 156 | 386 | 452 | 395 | 102 | 41 | 25 | 6 | 1 | 0 | 0 |
| 5 | 346 | 128 | 284 | 532 | 480 | 154 | 116 | 69 | 23 | 1 | 1 | 3 |
| 6 | 204 | 131 | 278 | 489 | 502 | 134 | 36 | 16 | 5 | 0 | 1 | 0 |
| 7 | 185 | 111 | 206 | 386 | 370 | 69 | 35 | 18 | 13 | 2 | 0 | 0 |
| 8 | 519 | 264 | 517 | 704 | 624 | 257 | 224 | 143 | 50 | 10 | 6 | 5 |
| 9 | 477 | 177 | 429 | 495 | 429 | 168 | 163 | 145 | 37 | 12 | 4 | 1 |
| 10 | 275 | 148 | 322 | 374 | 313 | 82 | 50 | 57 | 19 | 0 | 0 | 1 |
| 11 | 190 | 68 | 182 | 343 | 356 | 149 | 120 | 78 | 27 | 1 | 2 | 2 |
| 12 | 192 | 142 | 277 | 542 | 557 | 231 | 61 | 30 | 15 | 1 | 2 | 2 |
| 13 | 321 | 180 | 451 | 633 | 561 | 229 | 121 | 66 | 19 | 5 | 1 | 1 |
| 14 | 149 | 87 | 181 | 362 | 389 | 138 | 129 | 60 | 22 | 4 | 5 | 3 |
| 15 | 190 | 88 | 222 | 367 | 412 | 105 | 36 | 34 | 8 | 1 | 0 | 1 |
| 16 | 219 | 124 | 245 | 412 | 388 | 129 | 61 | 29 | 13 | 0 | 1 | 0 |
| 17 | 238 | 166 | 386 | 569 | 552 | 120 | 51 | 38 | 17 | 2 | 5 | 2 |
| 18 | 528 | 197 | 429 | 630 | 593 | 296 | 197 | 110 | 29 | 11 | 1 | 1 |
| 19 | 208 | 121 | 310 | 569 | 586 | 151 | 63 | 41 | 12 | 1 | 2 | 2 |
| 20 | 295 | 143 | 206 | 600 | 610 | 176 | 88 | 52 | 24 | 7 | 0 | 3 |
| 21 | 281 | 157 | 383 | 558 | 540 | 213 | 175 | 134 | 50 | 12 | 6 | 5 |
| 22 | 268 | 153 | 229 | 445 | 450 | 119 | 40 | 39 | 7 | 3 | 4 | 3 |
| 23 | 209 | 254 | 333 | 709 | 675 | 151 | 98 | 38 | 20 | 4 | 2 | 4 |
| 24 | 316 | 120 | 245 | 574 | 468 | 111 | 45 | 44 | 11 | 0 | 2 | 0 |
| 25 | 252 | 173 | 347 | 610 | 638 | 145 | 63 | 41 | 7 | 4 | 1 | 0 |
| 26 | 301 | 118 | 261 | 632 | 526 | 146 | 145 | 123 | 48 | 7 | 2 | 9 |
| 27 | 316 | 153 | 251 | 554 | 529 | 106 | 78 | 51 | 18 | 2 | 2 | 0 |
| 28 | 493 | 216 | 423 | 755 | 644 | 142 | 105 | 51 | 21 | 2 | 0 | 1 |
| 29 | 290 | 170 | 251 | 473 | 365 | 72 | 60 | 29 | 12 | 1 | 2 | 2 |
| 30 | 314 | 132 | 261 | 525 | 472 | 142 | 70 | 35 | 15 | 1 | 2 | 1 |
| 31 | 232 | 179 | 212 | 573 | 440 | 106 | 26 | 31 | 11 | 0 | 0 | 1 |

Source: Census 2011

People with Disabilities

There are six categories: seeing, hearing, self-care, communication, walking and remembering

- Seeing

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | 10925 | 10892 | 201 | 140 | 35 | 37 | 187 | 170 | 60 | 59 | 7230 | 6929 | 36866 |
| 05 - 09 | 16080 | 16178 | 355 | 253 | 51 | 38 | 18 | 15 | 4 | 9 | - | - | 33001 |
| 10 - 14 | 15645 | 14664 | 349 | 299 | 57 | 37 | 18 | 11 | 3 | 2 | - | - | 31085 |
| 15 - 19 | 15855 | 15284 | 327 | 331 | 36 | 39 | 11 | 5 | 2 | - | - | - | 31890 |
| 20 - 24 | 10476 | 11684 | 242 | 290 | 41 | 36 | 7 | 14 | 6 | 1 | - | - | 22796 |
| 25 - 29 | 6701 | 9930 | 174 | 313 | 17 | 26 | 5 | 6 | 1 | 2 | - | - | 17174 |
| 30 - 34 | 4900 | 8216 | 139 | 303 | 22 | 38 | 9 | 10 | 1 | 1 | - | - | 13639 |
| 35 - 39 | 4216 | 7422 | 149 | 324 | 21 | 33 | 8 | 12 | - | 3 | - | - | 12187 |
| 40 - 44 | 3720 | 6440 | 197 | 463 | 24 | 50 | 8 | 3 | 2 | - | - | - | 10908 |
| 45 - 49 | 3120 | 5833 | 296 | 767 | 39 | 89 | 11 | 4 | 1 | 1 | - | - | 10160 |
| 50 - 54 | 2689 | 4690 | 358 | 850 | 53 | 98 | 10 | 13 | - | 6 | - | - | 8767 |
| 55 - 59 | 2553 | 4338 | 427 | 760 | 58 | 111 | 9 | 6 | 1 | 2 | - | - | 8265 |
| 60 - 64 | 2254 | 4025 | 422 | 749 | 74 | 95 | 12 | 16 | - | 4 | - | - | 7651 |
| 65 - 69 | 1546 | 3758 | 374 | 870 | 62 | 129 | 17 | 17 | 2 | 2 | - | - | 6777 |
| 70 - 74 | 1554 | 2461 | 423 | 792 | 90 | 169 | 19 | 27 | 1 | 3 | - | - | 5540 |
| 75 - 79 | 727 | 1586 | 249 | 696 | 68 | 162 | 21 | 29 | - | 4 | - | - | 3542 |
| 80 - 84 | 471 | 1237 | 226 | 653 | 67 | 168 | 18 | 44 | 2 | 4 | - | - | 2890 |
| 85+ | 342 | 1064 | 205 | 622 | 64 | 235 | 26 | 74 | 2 | 9 | - | - | 2643 |
| Total | 103772 | 129700 | 5114 | 9474 | 881 | 1589 | 411 | 476 | 90 | 114 | 7230 | 6929 | 265781 |

- Hearing

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | 10749 | 10742 | 327 | 284 | 73 | 72 | 288 | 225 | 90 | 76 | 7102 | 6861 | 36890 |
| 05 - 09 | 16182 | 16154 | 285 | 275 | 50 | 41 | 20 | 13 | 6 | 7 | - | - | 33034 |
| 10 - 14 | 15820 | 14837 | 188 | 173 | 34 | 24 | 17 | 6 | 5 | 2 | - | - | 31108 |
| 15 - 19 | 16009 | 15393 | 181 | 202 | 22 | 29 | 11 | 10 | 1 | 2 | - | - | 31859 |
| 20 - 24 | 10662 | 11882 | 115 | 130 | 17 | 23 | 5 | 8 | - | 4 | - | - | 22846 |
| 25 - 29 | 6795 | 10143 | 82 | 117 | 8 | 24 | 3 | 12 | 1 | 1 | - | - | 17188 |
| 30 - 34 | 4981 | 8433 | 70 | 126 | 13 | 19 | 5 | 6 | 1 | - | - | - | 13653 |
| 35 - 39 | 4295 | 7639 | 84 | 125 | 18 | 19 | 4 | 5 | - | 2 | - | - | 12191 |
| 40 - 44 | 3831 | 6787 | 87 | 125 | 18 | 22 | 7 | 1 | 1 | - | - | - | 10877 |
| 45 - 49 | 3330 | 6493 | 87 | 177 | 14 | 27 | 2 | 3 | - | - | - | - | 10133 |
| 50 - 54 | 3000 | 5392 | 93 | 203 | 15 | 33 | 2 | 10 | - | 1 | - | - | 8749 |
| 55 - 59 | 2917 | 4935 | 106 | 228 | 22 | 37 | 7 | 4 | - | 1 | - | - | 8258 |
| 60 - 64 | 2623 | 4585 | 113 | 273 | 18 | 27 | 2 | 3 | - | - | - | - | 7645 |
| 65 - 69 | 1858 | 4319 | 122 | 413 | 19 | 51 | 4 | 5 | - | - | - | - | 6792 |
| 70 - 74 | 1864 | 2975 | 177 | 392 | 35 | 81 | 10 | 14 | - | 3 | - | - | 5550 |
| 75 - 79 | 927 | 1960 | 105 | 399 | 30 | 93 | 5 | 11 | - | 1 | - | - | 3531 |
| 80 - 84 | 632 | 1562 | 119 | 421 | 29 | 115 | 3 | 15 | 1 | 1 | - | - | 2898 |
| 85+ | 467 | 1306 | 136 | 488 | 39 | 173 | 3 | 27 | 1 | 5 | - | - | 2646 |
| Grand Total | 106943 | 135538 | 2477 | 4551 | 474 | 910 | 399 | 377 | 108 | 108 | 7102 | 6861 | 265848 |

- Self-care

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | - | - | - | - | - | - | 4402 | 4260 | 602 | 649 | 13750 | 13409 | 37073 |
| 05 - 09 | 8435 | 8441 | 2044 | 2085 | 1313 | 1323 | 1515 | 1430 | 235 | 218 | 3047 | 3029 | 33115 |
| 10 - 14 | 14760 | 13963 | 788 | 682 | 238 | 154 | 238 | 166 | 35 | 31 | - | - | 31054 |
| 15 - 19 | 15967 | 15412 | 126 | 110 | 46 | 39 | 39 | 48 | 11 | 9 | - | - | 31806 |
| 20 - 24 | 10658 | 11896 | 61 | 65 | 34 | 24 | 23 | 20 | 3 | 1 | - | - | 22786 |
| 25 - 29 | 6832 | 10166 | 35 | 66 | 11 | 12 | 26 | 12 | 2 | 3 | - | - | 17167 |
| 30 - 34 | 4991 | 8442 | 34 | 56 | 15 | 14 | 16 | 18 | 3 | 3 | - | - | 13593 |
| 35 - 39 | 4300 | 7704 | 52 | 44 | 22 | 13 | 20 | 13 | - | 5 | - | - | 12173 |
| 40 - 44 | 3857 | 6878 | 32 | 27 | 18 | 14 | 16 | 16 | 3 | 2 | - | - | 10864 |
| 45 - 49 | 3366 | 6590 | 48 | 46 | 21 | 22 | 10 | 9 | - | 2 | - | - | 10114 |
| 50 - 54 | 3014 | 5543 | 56 | 53 | 13 | 21 | 20 | 15 | 3 | - | - | - | 8739 |
| 55 - 59 | 2960 | 5082 | 46 | 70 | 23 | 27 | 19 | 9 | 1 | 2 | - | - | 8239 |
| 60 - 64 | 2662 | 4707 | 45 | 104 | 21 | 23 | 21 | 20 | 4 | 4 | - | - | 7613 |
| 65 - 69 | 1916 | 4542 | 55 | 130 | 12 | 35 | 15 | 34 | 3 | 4 | - | - | 6746 |
| 70 - 74 | 1936 | 3150 | 90 | 202 | 29 | 62 | 17 | 32 | - | 3 | - | - | 5521 |
| 75 - 79 | 946 | 2102 | 68 | 232 | 21 | 77 | 17 | 56 | 3 | 3 | - | - | 3526 |
| 80 - 84 | 638 | 1637 | 84 | 257 | 34 | 112 | 23 | 91 | 1 | 7 | - | - | 2885 |
| 85+ | 465 | 1259 | 97 | 353 | 49 | 212 | 26 | 155 | 3 | 23 | - | - | 2642 |
| Grand Total | 87702 | 117513 | 3760 | 4583 | 1920 | 2185 | 6464 | 6404 | 914 | 972 | 16797 | 16438 | 265653 |

4. Communication

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | 7422 | 7395 | 1542 | 1505 | 736 | 704 | 1180 | 1143 | 295 | 315 | 7501 | 7183 | 36921 |
| 05 - 09 | 15416 | 15380 | 648 | 664 | 242 | 205 | 94 | 98 | 47 | 39 | 53 | 61 | 32946 |
| 10 - 14 | 15786 | 14752 | 122 | 114 | 54 | 43 | 47 | 38 | 12 | 9 | - | - | 30976 |
| 15 - 19 | 16068 | 15527 | 80 | 67 | 21 | 22 | 22 | 17 | 5 | 3 | - | - | 31832 |
| 20 - 24 | 10690 | 11928 | 47 | 44 | 21 | 14 | 16 | 27 | - | 7 | - | - | 22794 |
| 25 - 29 | 6835 | 10206 | 33 | 41 | 11 | 18 | 8 | 16 | 4 | 1 | - | - | 17173 |
| 30 - 34 | 5008 | 8500 | 41 | 29 | 10 | 11 | 15 | 11 | - | - | - | - | 13625 |
| 35 - 39 | 4315 | 7732 | 42 | 36 | 16 | 9 | 16 | 12 | 3 | 3 | - | - | 12186 |
| 40 - 44 | 3867 | 6893 | 33 | 22 | 11 | 12 | 8 | 8 | 3 | 1 | - | - | 10858 |
| 45 - 49 | 3383 | 6627 | 36 | 32 | 19 | 20 | 6 | 9 | - | 1 | - | - | 10134 |
| 50 - 54 | 3056 | 5553 | 27 | 39 | 13 | 19 | 13 | 7 | - | - | - | - | 8727 |
| 55 - 59 | 2995 | 5145 | 22 | 44 | 14 | 13 | 4 | 3 | - | 1 | - | - | 8241 |
| 60 - 64 | 2700 | 4802 | 39 | 62 | 7 | 14 | 4 | 3 | - | - | - | - | 7632 |
| 65 - 69 | 1955 | 4673 | 30 | 77 | 3 | 18 | 3 | 6 | - | 1 | - | - | 6766 |
| 70 - 74 | 2028 | 3291 | 39 | 119 | 10 | 23 | 5 | 16 | 1 | 4 | - | - | 5537 |
| 75 - 79 | 1026 | 2315 | 31 | 122 | 5 | 17 | 3 | 10 | - | 3 | - | - | 3532 |
| 80 - 84 | 731 | 1931 | 34 | 124 | 9 | 41 | 1 | 5 | - | 1 | - | - | 2878 |
| 85+ | 577 | 1739 | 49 | 198 | 12 | 47 | 3 | 15 | - | 6 | - | - | 2646 |
| Grand Total | 103859 | 134388 | 2895 | 3339 | 1215 | 1251 | 1450 | 1444 | 371 | 396 | 7554 | 7243 | 265404 |

5. Walking

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | 9921 | 9854 | 452 | 426 | 172 | 156 | 935 | 870 | 170 | 152 | 7048 | 6795 | 36949 |
| 05 - 09 | 16211 | 16147 | 190 | 219 | 62 | 66 | 52 | 38 | 10 | 11 | 49 | 55 | 33110 |
| 10 - 14 | 15976 | 14957 | 66 | 66 | 19 | 12 | 36 | 26 | 5 | 4 | - | - | 31168 |
| 15 - 19 | 16164 | 15606 | 64 | 62 | 20 | 19 | 19 | 21 | 4 | 1 | - | - | 31981 |
| 20 - 24 | 10735 | 11948 | 48 | 51 | 14 | 19 | 9 | 14 | - | - | - | - | 22839 |
| 25 - 29 | 6858 | 10212 | 35 | 72 | 12 | 20 | 9 | 13 | 2 | - | - | - | 17235 |
| 30 - 34 | 5010 | 8486 | 56 | 64 | 14 | 19 | 7 | 10 | - | 4 | - | - | 13670 |
| 35 - 39 | 4321 | 7697 | 60 | 90 | 24 | 20 | 9 | 11 | 1 | 1 | - | - | 12234 |
| 40 - 44 | 3828 | 6819 | 67 | 99 | 23 | 21 | 8 | 9 | 2 | - | - | - | 10875 |
| 45 - 49 | 3341 | 6479 | 89 | 181 | 30 | 27 | 6 | 7 | - | 2 | - | - | 10162 |
| 50 - 54 | 2966 | 5409 | 118 | 204 | 31 | 43 | 5 | 10 | - | 1 | - | - | 8787 |
| 55 - 59 | 2850 | 4832 | 147 | 285 | 48 | 81 | 7 | 6 | 1 | 2 | - | - | 8259 |
| 60 - 64 | 2539 | 4437 | 164 | 360 | 38 | 67 | 14 | 12 | - | 1 | - | - | 7632 |
| 65 - 69 | 1800 | 4237 | 156 | 409 | 35 | 124 | 10 | 17 | - | 1 | - | - | 6790 |
| 70 - 74 | 1796 | 2841 | 219 | 475 | 67 | 135 | 6 | 15 | - | 2 | - | - | 5557 |
| 75 - 79 | 867 | 1836 | 157 | 461 | 32 | 148 | 11 | 29 | 1 | 3 | - | - | 3544 |
| 80 - 84 | 567 | 1443 | 160 | 474 | 45 | 162 | 12 | 35 | - | 2 | - | - | 2899 |
| 85+ | 396 | 1158 | 168 | 536 | 64 | 235 | 12 | 74 | 2 | 12 | - | - | 2658 |
| Grand Total | 106147 | 134399 | 2416 | 4533 | 750 | 1372 | 1167 | 1218 | 199 | 201 | 7096 | 6850 | 266347 |

6. Remembering / Concentration

| Age Group | No difficulty |  | Some difficulty |  | A lot of difficulty |  | Cannot do at all |  | Do not know |  | Cannot yet be determined |  | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | F | M | F | M | F | M | F | M | F | M | F |  |
| 00 - 04 | 5765 | 5668 | 1719 | 1694 | 1171 | 1122 | 1614 | 1549 | 350 | 386 | 8125 | 7882 | 37044 |
| 05 - 09 | 14103 | 14059 | 1474 | 1460 | 550 | 559 | 186 | 205 | 67 | 51 | 210 | 179 | 33103 |
| 10 - 14 | 15725 | 14783 | 249 | 189 | 83 | 45 | 49 | 40 | 14 | 3 | - | - | 31179 |
| 15 - 19 | 16085 | 15530 | 117 | 116 | 37 | 33 | 15 | 18 | 10 | 3 | - | - | 31963 |
| 20 - 24 | 10676 | 11946 | 65 | 66 | 38 | 17 | 16 | 16 | 3 | 2 | - | - | 22843 |
| 25 - 29 | 6830 | 10207 | 59 | 63 | 27 | 29 | 10 | 10 | 3 | - | - | - | 17240 |
| 30 - 34 | 4978 | 8491 | 48 | 59 | 37 | 28 | 17 | 13 | 2 | 3 | - | - | 13676 |
| 35 - 39 | 4286 | 7688 | 70 | 70 | 35 | 24 | 12 | 11 | 1 | 2 | - | - | 12200 |
| 40 - 44 | 3841 | 6843 | 54 | 70 | 23 | 13 | 9 | 14 | 3 | - | - | - | 10871 |
| 45 - 49 | 3357 | 6538 | 70 | 110 | 28 | 26 | 2 | 5 | - | 4 | - | - | 10139 |
| 50 - 54 | 3021 | 5500 | 60 | 120 | 22 | 31 | 12 | 5 | - | - | - | - | 8771 |
| 55 - 59 | 2952 | 5040 | 71 | 154 | 20 | 29 | 7 | 10 | 3 | 2 | - | - | 8288 |
| 60 - 64 | 2651 | 4638 | 87 | 200 | 13 | 35 | 2 | 6 | 2 | 2 | - | - | 7637 |
| 65 - 69 | 1908 | 4467 | 87 | 247 | 12 | 45 | 3 | 13 | 1 | 2 | - | - | 6784 |
| 70 - 74 | 1941 | 3100 | 117 | 283 | 22 | 65 | 6 | 12 | - | 4 | - | - | 5551 |
| 75 - 79 | 963 | 2082 | 78 | 302 | 18 | 76 | 4 | 16 | - | 2 | - | - | 3541 |
| 80 - 84 | 669 | 1661 | 83 | 314 | 27 | 113 | 3 | 22 | - | 4 | - | - | 2896 |
| 85+ | 516 | 1369 | 95 | 398 | 31 | 185 | 6 | 38 | 1 | 10 | - | - | 2648 |
| Grand Total | 100266 | 129608 | 4602 | 5914 | 2194 | 2473 | 1975 | 2005 | 461 | 482 | 8335 | 8060 | 266374 |

3.2 KPA 1: SPATIAL RATIONALE

Land ownership is predominantly under the South African Development Trust but under the custodianship of local traditional authorities. The MLM SDF found that 98% of land in the municipal area is in the custodianship of traditional authorities. Approximately 2% of the land is under the hands of private owners, i.e. land for Jane Furse Plaza, Jane Furse Crossing and Moratiwa Shopping Complexes. The municipality own hectors of land where Jane Furse and Moji RDP houses were built since 1996.

3.2.1 Land use

Land use within Makhuduthamaga is characterized by a mixed use of subsistence farming and residential uses. The land issue is potentially a source of tension in the area. There is a latent tension between the traditional (tribal council) and modern (legalized) land use management systems. There is also a number of competing land claims in the area, which have not been resolved by the Department of Rural Development and Land Reform as yet. Approximately 39.8% or 83,537 ha (51 land claims) of the Makhuduthamaga Local Municipality is subject to land claims.  Most of these claims are not likely to be resolved soon as they are on tribal land and need tenure reform rather than restitution.

Land restitution has the potential to alter the spatial pattern and to contribute significantly in agriculture development and job creation.  Many people would obtain access to land that could result in improved living standards and quality of life.

The Makhuduthamaga villages are characterized by poor accessibility, low density and large distances between settlements. This makes it challenging for the municipality to provide the required infrastructure and basic services. Lack of coordination between the Municipality, traditional authorities and the provincial Department of Cooperative, Human Settlement and Traditional Affairs (COGHSTA) has resulted in unplanned residential development taking place in the area.

Some of the key challenges facing the municipality include, inter alia:

- Uncertainty about the status of land ownership especially with reference to state and tribal land prohibits future development and investments.

- Unresolved and competing land claims in the area threaten to destabilize future development.

- Competing land uses (i.e. mining and agriculture, commercial, etc.) may cause spatial, social, environmental and economic constraints in future.

- Lack of environmental management

- Communal land use management

- Sprawled development

- Lack of adequate water to supply all settlements

- Some nodal points like Jane Furse have not yet been planned and proclaimed thereby limiting the growth potential of the node.

Map showing the Spatial Perspective of the municipality

3.2.3 Macro land use and Municipal Planning in Makhuduthamaga Municipality

| Land Use | Size(Ha) | Total (Ha) |
| --- | --- | --- |
| Irrigation farms | 2719 |  |
| Game farms | 0 |  |
| Other Arable /Grazing | 177748 |  |
| Subtotal Agriculture |  | 180467 |
| Nature Reserves |  | 0 |
| Settlement/Towns |  | 29228 |
| Other |  | 0 |
| Total |  | 209695 |

Source: Genis, Geographic and Environmental Systems

The municipality does not have a zoning scheme. A process has been embarked upon to develop an integrated zoning policy. The first phase will consist of the Jane Furse regeneration and the development of a zoning mapping system.

3.2.4 Growth/ Nodal points and hierarchy of settlement

Settlement Growth

| Settlement type | Settlements | Description | Development |
| --- | --- | --- | --- |
| First order settlements and housing focus areas | Ga-Marishane, Ga-Masemola, Ga-Moloi, Ga-Phaahla, Ga-Ra-Ntobeng, Glen Cowie, JaneFurse,Kopjeng,Malaita,Maletse,Maserumole,Matlakatle,Mohlarekoma,Mohwelere,Mokwete,Nebo,Ngwaritsi,Phatametsane,Phokwane, Sekwati,Takataka | This is the cluster of settlements located around the main node of Jane Furse. This is one of the most accessible areas in the MLM due to its close location to the R579 and three district routes, and has the largest concentration of services and facilities. One of the main population concentrations. Identified as the municipal growth point in District planning, the highest order node in the MLM | Growth: The settlements abutting the Jane Furse node will come under increased pressure for development with growth direction probably along the D2219, D4828 and D4190.These areas need to be formalised to ensure sustainable growth. Intensification, infill and densification should occur within the Jane Furse nodal boundary. The growth abutting the R579 ought to be managed in terms of the planning for the R579 corridor, the Growth focus area and the Apel Cross and Glen Cowie nodes. Accessibility: Provide public transport facilities along the D2219, D4828, and D4190 routes. This include pedestrian amenities at stops e.g. shade or shelters, lighting, sidewalks etc. Economic activities: The main economic activities need to be focused in the Jane Furse node with settlements’ services e.g. convenience stores, hair dressers etc to be provided in the settlements surrounding the node. Economic activities should preferably be clustered as per the strategic local development framework Social and community facilities: High level regional type facilities to be provided in the Jane Furse node with community and mobile service provided in the surrounding settlements preferably at or close to transport facilities. Existing school sites can also be used to cluster community facilities. This clustering will also assist with the accommodation of markets or sales points (e.g. pension day markets) at accessible points. |
| Second order settlements and housing infill and consolidation area | Ga-Mashegwana, Ga- Mogashoa, Manganeng, Schoonord,Tsatane | These areas are clustered around the D4226 and D4241 routes. It is served by Magnet heights and Schoonoord services nodes | Growth: Growth of these settlements will be stable with no economic activity to drive migration. The economic base are very narrow and the sprawl of settlements need to be prohibited in order to support in fill and densification as means of creating economies of scale for the two service nodes. The escarpment area to the east should be protected against further intrusion of residential development. Accessibility: Provide public transport facilities in the nodes and along the D4226 and D4241 routes. This include pedestrian amenities at stops e.g. shades or shelters, lighting, sidewalks etc.Local collector streets need to be tarred. Economic activities: The main economic activities need to be focused in the two nodes and including settlements’ services e.g. convenience stores, hair dressers etc.The are government services that can support the development of administrative type businesses Social and community facilities: Existing facilities ought to be maintained. Existing school sites can also be used to cluster community facilities. This clustering will also assist with the accommodation of markets or sales points (e.g. pension day markets)at accessible points |
| Third order settlements | Ga-Maila,Ga-Malaka,Ga-Mampane,Ga-Masemola,Ga-Molepane,Ga-Phala,Ga-Sefoka,Good Hope,Kome,Kopjeng,Makhutso,Malope,Mamohlakane,Manganeng,Marulaneng,Masanteng,Masehlaneng,Matlakatle,Makgwabe,Mmotwaneng,Mogaladi,Mohlarekoma,Mohwelere,Ngwaritsi,Ntwelemushi,Patantshwane,Sehuswane,Serageng,Thabanapitsi,Thoto,Tsatane,Tswaing,Tswatago | Relatively more isolated / inaccessible in local context than other settlements types. No strong local nodes at present. These settlements are scattered with fragmented configurations that do not support viable service provision. Service provision will be expensive if a full package of services is to be provided | Growth: Growth of these settlements will be limited with no economic activity to drive in migration. The economic base are very narrow and the sprawl of settlements need to be prohibited in order to create limited economy of scale of small scale and convenience type of businesses. Accessibility: Provide public transport facilities in the nodes and along the 4310, D4150, D4100 and D4480 routes. This includes pedestrian amenities at stops e.g. shade or shelters. Local collector streets need to be tarred. Economic activities: The main economic activities need to be focused at intersections with the D4310, D4150, D4100 and D4480 routes e.g. convenience stores, hair dressers etc. Social and community facilities: Existing facilities ought to be maintained. Existing school sites can also be used to cluster community facilities. This clustering will also assist with the accommodation of markets or sales points (e.g. pension day markets)at accessible points |

Source: MLM Reviewed SDF, 2015

The table below identifies the nodal points and hierarchy of settlements

Nodal Points and Hierarchy of Settlements

| Classification | Function |
| --- | --- |
| Jane Furse Primary growth point | - Provides a mix of activities - Centre of business and services for the immediate district - Promote pedestrian friendly environment - Accommodate public transport facilities and adequate parking |
| Apel Cross and Glen Cowie Secondary nodes | - Centre of business and services for the immediate district - Promote pedestrian friendly environment - Accommodate public transport facilities and adequate parking - Address illegal access points and put in place an appropriate road network - Location of community related services |
| Local Services nodes: - Vierfontein / Takataka - Moratiwa - Tshehlwaneng / Magnet Heights - Phokoane - Schoonoord | - Centre of local business and services for immediate community - Accommodate public transport facilities and adequate parking - Address illegal access points and put in place and appropriate road network - Location for temporary or movable community related services if permanent services are not available |
| Manufacturing, commercial areas | - There is currently no area earmarked for manufacturing or industrial uses. Manufacturing and commercial areas ought to include small scale and clean manufacturing, processing warehousing and supporting facilities, transport companies, and offices. Where possible, developments need to seek to minimize waste generation, energy use and other environmental impacts |
| Apel cross agric-node | - The focus is on agriculture production and processing - Operations and production should however comply with environmental friendly practices - Provide good transport facilities and promote regional transport services - Provide accommodation and residential opportunities |
| Future nodes | - There is an opportunity to develop a future nodal points that can serve the proposed development focus area |

Source: MLM Reviewed SDF, 2015

MLM Map showing Growth / Nodal points / Hierarchy of Settlement

Land for LED /Agriculture Opportunities

| Project | Description | Location | Land Ownership |
| --- | --- | --- | --- |
| Organic food production | Dry land sorghum / mabele farming currently taking place at Lepellane and Makgane- Moretsele area. This has potential for secondary production, raw storage and export | Makgane and Moretsele till Marulaneng (500 000 ha) | Traditional land |
| Bio Diesel / Nebo Plateau | Rehabilitation of old farming areas for the purpose of planting sunflower, maize and soya beans. | Nebo area (400 000 ha) | Traditional land |
| Poultry farming | This is a viable white meat cluster. The poultry farming opportunity includes poultry broiling, hatching and abattoir. |  | Traditional land |

Source: MLM Reviewed SDF 2015

Map showing areas used for Agricultural Purposes within Makhuduthamaga

3.2.5 Current land claims in Makhuduthamaga municipal area

The Land Claims Commissioner in Limpopo has only one record of a restituted claim in Makhuduthamaga Local Municipality as reflected in the table below. Outstanding claims are depicted below. They are many and their resolution is protracted, because the claims are mostly community on community and without accurate property descriptions. Almost 80% of the farms in Makhuduthamaga Local Municipality are under land claim.

Land claims in Makhuduthamaga Municipal area

| Claim Ref Number | Claimant | Farms Names |  |
| --- | --- | --- | --- |
| 2426 | Bakoni Ba Maimela Community | Buffelshoek 368 KT, Wildebeest kraal 354 KT, Belvedere 362 KT | Buffelshoek 368 KT settled, and others in research |
| 12171 | Tisane Tribe | Mooifontein 806 KS, Goedehoop 824 KS, Eensgevonde 825 KS, Weltevreden 822 KS, Bothaspruit 820 KS | Further Research |
| 9591 | Maleka KF | Masemola Village | Further Research |
| 9253 | Morena Tribe | Pains Hill 271 KT | Further Research |
| 10972 | Monareng SP | Selale Village (Unclear Property) | Further Research |
| 1965 | Baroka Ba Phelane Community | R/E of The Shelter 121 KT | Further Research |
| 2358 | Mnisi LB | Paradys 773 KT | Further Research |
| 1504/1510/2027/4556 | Marutleng Tribe/Maloma MG | Goedetrouw 860 KS | Research report approved |
| 1876/1611 | Manaswe RS | Vierfontein 871 KS | Gazetted and Further Research |
| 1530 | Jibeng Community | Jagdlust 410 KS, Winterveld 417 KS, Moijesluk 412 KS, Zwartkoppies 413 KS | Further Research |
| 1598/6170 | Pedi Mamone Tribe | Kanaan 783 KS, Leeukraal 877 KS, Goede Trouw 860 KS, Rietfontein 852 KS, | Further Research |
|  |  | Roodepoort 880 KS, Tweefontein 848 KS, Boschpoort 843 KS, Spitskop 874 KS |  |
| 1643 | Baroka ba Maila of Segolo | Eensaam 811 KS | Further Research |
| 892 | Magokubjane Community | Spitskop 874 KS | Further Research |
| 5094 | Tshehla MD | Paradys 773 KS, Steelpoort, Nooitverwacht 324 KT | Further Research |
| 10714/2549/4508 | Moretsele AM/MC | Mooimeisjesfontein 363 KT | Further Research |
| 10173 | Mosehla KB | Unclear Property | Further Research |
| 10289 | Malaka Tribe | Tweefontein 848 KS, Roodepoort, Goedgedacht, Eensaam 811 KT | Further Research |
| 11722 | Bakone Ba Mmanakana | Ontevreden 838 KS,Tweefontein 848 KS,Leeukraal 877 KS, Uitkyk 851 KS | Further Research |
| 10552 | Magakwe RM | Mooihoek 808 KS,Eezaam 811 KS | Further Research |
| 5530 | Makola JM | Goedverwacht 511 KS | Further Research |
| 1431/1412 | Maphosa SP/Maphosa JM | Vlakfontein 130 JS | Further Research |
| 1577 | Maserumule M | Uitkyk 815 KS | Further Research |
| 11637 | Mokalapa MJ | Kannan 783 KS | Further Research |
| 1833 | Tau Tribe | Mooiplaats 516 KS, Strydkraal 537 KS | Further Research |
| 3806 | Mokwena E | Balmoral 508 KS | Further Research |
| 1553 | Marota MarulanengTribe | Goedgemeend 815 KS, Lords kraal 810 KS, Korenvelden 812 KS, Groenland 813 KS | Further Research |
| 1495 | Mashupi K | Mooihoek 808 KS | Further Research |
| 1939 | Selepe MT | Brakfontein 464 KS | Gazzeted and further research |
| 1444/5328 | Mashabela NJ | Heerlyheid 768 KS | Gazzeted and further research |
| 1851/2497 | Kwena Madihlaba Community | R/E,Ptn 1, R/E of Ptn 2,3,4,5,6 & 7 of Spitskop 874 KS, R/E, Ptn1,2,3,4,8,9,11 & 12 of Rietfontein 876 KS, R/E of Ptn 0, R/E of Ptn 1, R/E of Ptn 2 & R/E of Ptn 3 | Gazzeted and further research |
|  |  | of Roodepoort 880 KS, r/e OF Ptn 1, R/E of Ptn 2, R/E of Ptn 3, R/E of Ptn 4, R/E of Ptn 5, R/E of Ptn 6, R/E of Ptn 7, R/E of Ptn 8 & R/E of Ptn 9 of |  |
| 1556/2012 |  | Eensaam 875 KS, Leeukraal 887 KS, Stad Van Masleroem 841 KS, Morgenson 849 KS, R/E, Ptn 1 & 2 Rietfontein 880 KS |  |
| 866/4599/2365/1911 | Bengwenyama Ya Maswati community | Eerstegeluk 327 KT, Winterveld 293 KT, Doornbosch 294 KT | Gazzeted and further research |
| 998 | Mdluli Community | Rietfontein 876 KS, R/E of Ptn 1 & R/E of Ptn 7 of Luckau 127 JS | research completed and Negotiations |
| 1493 | Kwena Mashabela Tribe | R/E, 1,2, 3,4,5 & 8 of Proberen 785 KS,R/E, Ptn 1,2 & 3 of Loopspruit 805 KS, R/E of Meerlust 804 KS, R/E, Ptn 1 & 2 of Vooruitzicht 787 KS, R/E, Ptn 1,2 & 3 of Rustplaats 788 KS, R/E of Drakenstein 784 KS | Gazzeted and further research |
| 11120 | Roka Mashabela Community | Hackney 116 KT, Twickenham 114 KT, Djsjate 249 KT, Quartzhill 542 KT, Fernkllof 539 KT | Gazzeted and further research |
| 1447 | Phokoane Tribe | R/E, R/E of Ptn 1, R/E of Ptn 2, R/E of Ptn 3, R/E of Ptn 4 & R/E of Ptn 5 of Klipspruit 870 KS,R/E of Mooiplaats 516 KS, R/E,R/E of Ptn 1, R/E of Ptn 4 & R/E of Ptn 5 of Strydkraal 537 KS,Uitkyk 851 KS, Rietfontein 852 KS,Doornspruit 397 KS, Platklip 867 KS,Vleeschboom 869KS,Rietfontein 876 KS,Leeukraal 877 KS, | Gazzeted and further research |
| 1169 | Mutsweni BW | Eensaam 811 KT | Gazzeted; Further Research |
| 1439 | Roka Phasha Makgalanoto Tribe | R/E, Ptn 1,2, R/E of 3, 4,5 OF Mecklenburg 112 KS, Ptn 0 & 1 of Waterkop 113 KT, Ptn 0 of Wismar 96 KT, Ptn 0 of De Paarl 97 KT, Ptn 0 of Schwerin 95 KT | Gazzeted; Further Research |
| 1440 | Mampane Tribe | R/E of Ptn 1,3, R/E of 4, 5, 6 of Roodewal 678 KS, R/E of Pnt 1 of Kwarriehoek 710 KS, De oude Stad 765 KS,Ptn 4 of Rooibokkop 744 KS, R/E, Ptn 1,2 & 3 of Weltevreden 799 KS, R/E, Ptn 1 & 2 of Eenkantaan 798 KS. | Gazzeted Further Research |
| 1652 | Monama CW | R/E of Boschpoort 843 KS,Vergelegen 819 KS,R/E of Ptn 1 & R/E of Ptn 2 of Goedgedacht 878 KS, R/E of Duizendannex 816 KS, R/E of Groenland 813 KS, R/E of Lords kraal 810 KS, R/E Hoeglegen 809 KS | Gazzeted; Further Research |
| 11996/12068/2344 | Batlokwa Ba Mogodumo Community | Goedgedacht 878 KS,Vergelegen 819 KS,Boschpoort 843 KS, Hoeglegen 809 KS | Gazzeted and further research |
| 1602 | Kwena Mashabela Community | R/E, Ptn 1 & 2 of Vooruitzicht 787 KS,R/E, Ptn 1,2 & 3 of Loopspruit 805 KS, Kamaan 322 KS,R/E of Meerlust 804 KS,R/E of Drakenstein 784 KS, R/E, Ptn 1 & 2 of Rust plaats 788 KS, R/E, Ptn 1,2,3,4 & 8 of Proberen 785 KS | Gazzeted and further research |
| 1508 | Makunyane Community | Hok | Gazzeted and further research |

Source: Limpopo Land Claims Commissioner, 2015

Settled restitution claims for Makhuduthamaga local municipality

| Date | Name of claimant | Classification | Landsize (Ha) | Land cost |
| --- | --- | --- | --- | --- |
| 2004/02/16 | The Diocese of Saint Marks the Evangelist | Vergelegen 819KS R/E and Ptn 1,2 and 4 | 89 | State land |
| 2005/09/06 | Mamashiana Community | 65 KT | 2778 |  |

Source: Limpopo Land Claims Commissioner, 2015

| Status quo /Baseline | Backlog /Outstanding |
| --- | --- |
| Number of claims settled = 02 | 0 |
| Number of claims awaiting final settlement = 02 | 0 |
| Number of claims gazetted = 11 | 0 |
| Number of Researched Claims Approved = 04 | 42 claims awaiting approval |

Source: Limpopo Land Claims Commissioner, 2015

| MLM tenure status and population group of head of household |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other |
| Rented | 2909 | 9 | 57 | 13 | 47 |
| Owned but not yet paid off | 2250 | 1 | 3 | - | 3 |
| Occupied rent free | 12604 | 1 | 2 | 11 | 18 |
| Owned and fully paid off | 4422 | 7 | 20 | 24 | 21 |
| Other | 2983 | 2 | - | 1 | 1 |

Source: Census 2011

Demarcated sites within Makhuduthamaga villages since 2003

| Village/area | Number of sites/Erven allocated | Year of Demarcation |
| --- | --- | --- |
| - Krokodel | 210 Site + 2 Parks = 211 | August/October 2003 |
| - Mamatjekele | 218 Erven + 6 Parks = 224 | August 2004 |
| - Mohloding Ext 1 | 194 Erven + 6 Parks = 200 | February 2004 |
| - Marishane | 201 Erven + 4 Parks = 205 | April 2004 |
| - Masemola | 88 Erven + 1 Park = 89 | August 2004 |
| - Tswaing | 207 Erven | January & February 2004 |
| - Tjatane | 300 Erven | April 2004 |
| - Sehuswane | 208 Erven + 1 Park = 209 | March 2004 |
| - Tisane | 300 Erven | April & June 2004 |
| - Ga –Maboke | 256 Erven + 5 Parks = 261 | August 2007 |
| - Kgaruthuthu Ext 1 | 405 Erven + 9 Parks = 414 | October 2006 &June 2007 |
| - Ga Masemola (Apel Cross) | 509 Erven + 2 Parks = 512 | October 2009 |
| - Mohlarekoma | 500 Erven | 2010/2011 |
| - Makgane | 1000 Erven | 2013/2014- 2014/2015 |
| - Manganeng | 1000 | 2015/16-2016/17 |
| - Mohlarekoma Ext | 500 | 2015/16-2016/17 |

Source: COGHSTA, 2016

Sites demarcated in the 2016/17 f/y

| Village/area | Number of sites / Erven allocated | Year of Demarcation |
| --- | --- | --- |
| Marishane | 500 | 2016/17 |
| Tshehlwaneng | 500 | 2016/17 |
| Diphagane | 500 | 2016/17 |

Source: MLM Spatial Planning Division 2016

Number of sites planned

| # Municipality | # Financial year |  |  |
| --- | --- | --- | --- |
|  | 2017-2018 | 2018-2019 | 2019-2020 |
| # Makhuduthamaga | # - | # - | # Ga-Masemola - Apel Cross and Jane Furse-Vergelegen |

Source: Department of Cooperative governance, human settlements and traditional affairs (COGHSTA)

Number of township applications approved

| # Municipality | # Financial year |  |  |
| --- | --- | --- | --- |
|  | # 2014-2015 | # 2015-2016 | # 2016-2017 |
| # Makhuduthamaga | # - | # Ga-Masemola - Apel Cross | # - |

Source: Department of Cooperative governance, human settlements and traditional affairs (COGHSTA)

3.2.6 Illegal Occupation of Land (land invasion)

## The Municipality is experiencing challenges of illegal occupation of land especially in Jane Furse Central Business District, along the R579 road reserve, and at the Jane Furse and Moji Integrated Human Settlements. The other major challenge relates to street advertising that is done without taking into account other national and provincial legislation.

Informal settlements within MLM

| Municipality | No of human settlements | No of structures | Total Human Population in informal settlements |
| --- | --- | --- | --- |
| Makhuduthamaga | 01 | 1500 | 6000 |

Source: Draft Informal Settlement Upgrading Strategy for Limpopo, 2014

| Challenge |  | Action |
| --- | --- | --- |
| Illegal occupation of Municipal Land | X | To embark on a programme of removing illegal land occupants |

## 3.2.7 Environmental analysis

Climate

Makhuduthamaga municipal area is characterized by a hot climate, with the average temperature shows moderate fluctuation with average summer temperatures of 23C, as well as a maximum of 28C and a minimum of 18C.In winter, the average is 13,5C with a maximum of 20C and a minimum of 7C Climate

Biodiversity

Biodiversity describes the variety of life in an area including the number of different species, the genetic wealth within each species, the interrelationships between them and the natural areas in which they occur. Sensitive vegetation and watercourses should be maintained for both the conservation of biodiversity and for their ecological functioning in water quality improvement and flood control.

The Makhuduthamaga Municipality is rich in biodiversity.  The region is rich in ultramafic-induced endemic plant species, which make it a treasure house for biodiversity (e.g lewang and protea found in the Leolo mountains).

The role of biodiversity in agricultural and natural ecosystems is to ensure food security and sustainable agricultural production through direct or indirect provision of food for humans and their livestock, provision of raw materials and services, such as fibre, fuel and pharmaceuticals and the maintenance of ecosystem functions. Any agricultural plan must therefore take the biodiversity of the region into consideration

Topography

The topography of the municipality varies between flat and rolling slopes, sometimes interrupted by small hills that make the area prone to erosion.

Heritage sites within the municipality that are linked to cultural tourism:

- Hlako Tisane Conservation Camp –Khoi/San Rock Art

- Matjeding Fortress

- Manche Masemola heritage site

- Musical stones- Thabampshe

- Mabje Mabedi Maramaga –Leolo Mountains

- God’s Foot print – Molebeledi

- The God’s Bed

- Archaeological sites

- Borishane

- Rain making pots

The challenge is to develop these cultural sites to increase the contribution of cultural tourism to the MLM‘s Gross Geographical products

Geology

The soil types include dolomite, limestone, iron formation, shale and quartzite. Various water sources transverse the municipal area. They flow during rainy seasons and dry out when it does not rain.

Climate change

Changes in climate patterns are natural phenomena.However,there is increasing concern about the impact of climate change that has been brought as a result of human activities (such as burning fossil fuels of energy, use of motor vehicles,etc)Human induced changes in climate have acknowledge as a current global reality and are the subject of significant global attention. Global changes in climate have already been observed that are generally consistent with model projects and are likely to continue to occur for many decades to come even if mitigation efforts are successful due to lays and inertia in the global biosphere response.

South Africa is a country of extraordinary natural beauty, outdoor lifestyle and activities, warm weather and diversity in terms of culture and is known as an affordable destination. The broad range of tourism activities, including ecotourism, cultural sporting activities, historical and geological attractions and business tourism make it a premier destination for domestic and local tourism.

Pollution

Air pollution in the area emanates from the use of fire wood for energy purpose, burning of refuses and dust from gravel roads.   Water pollution is caused by the cumulative impact of the insufficient solid waste removal, lack of sanitation infrastructure, sewerage effluent, etc.

Water resources

Various water sources transverse the municipal area. They flow during rainy seasons and dry out when it does not rain.  Nonetheless, the area suffers from a water scarcity, which constraints both economic and social activities.  This challenge is further exacerbated by insufficient and variable rainfall, inequitable water resources management and the absence of drinking water, and the lack of bulk water and irrigation infrastructure

The Municipality has identified wards and villages that have wetlands that need to be preserved.

Structures that facilitate public participation and engagement around Environmental Management and Planning that Makhuduthamaga Municipality is part of:

- District Environmental Forum

- District Waste Management Forum

- Provincial Municipal Air Quality Officers Forum

- Landfill site monitoring committee

- Provincial climate change working group

List of wetlands fenced in the past four years

| Ward no | Village | Financial year | Status quo |
| --- | --- | --- | --- |
| 06 | Phatantswane | 2014/15 | Completed |
|  | Eenzaam | 2015/16 | Completed |
| 20 | Ga –Marishane Mothopong | 2016/17 | Completed |
| 24 | Diphagane | 2013/14 | Completed |
| 25 | Mashabela Phase 1& phase 2 | 2014/15 and 2015/16 | Completed |
| 07 | Malaka | 2016/17 | Completed |
| 14 | Dlamini | 2017/18 | Completed |

Source: MLM Environmetal Division, 2017

An awareness campaign was also conducted in these areas

Water scarcity

Water scarcity is a huge developmental challenge within the Sekhukhune District, and constraints both economic and social activities in the area. The issue is a manifestation of climate variability. However; it is also the result of a number of other factors, which include insufficient and variable rainfall, inequitable water resources management and the absence of drinking water, bulk water and irrigation infrastructure that would aid the distribution of water to rural villages.Water scarcity affects a range of other developmental issues in Makhuduthamaga – municipal service delivery, subsistence farming activities and commercial agriculture.

Environmental management

As part of environmental management the MLM has a licensed authorized landfill site, Jane Furse landfill site. However, livestock management and control is a key problem within MLM.There is a lack of fences in some crop farming areas and along main roads, which results in wandering livestock. These livestock damage crops and cause vehicle accidents along Makhuduthamaga main roads. To worsen the challenge is that some of the communities destroy or steal fence in areas that was erected.The Municipality has a promulgated Waste Management By-law. There is also a Draft Integrated Waste Management Plan (IWMP).

Environmental impact assessments done in Makhuduthamaga

| Provincial Ref No. | Project Description | Status | Sector | Decision Date | Stage |
| --- | --- | --- | --- | --- | --- |
| 12/1/9/1-GS32 | The proposed activity involves the construction of a Milling facility on 4 ha land of the Farm Nebo 872 KS within Makhuduthamaga Local Municipality, Sekhukhune District. | Finalised Authorised | Agriculture and Forestry(including Agri-industry: Agriculture; etc) |  | Granted Authorisation Wholly |
| 12/1/9/1-GS31 | The proposed activity involves the construction of a poultry abattoir on 2ha land at Nebo within Makhuduthamaga Local Municipality, Sekhukhune District | Finalised Authorised | Agriculture and Forestry(including Agri-industry: Agriculture; etc) |  | Granted Authorisation Wholly |
| 12/1/9/1-GS107 | The proposed establishment of township with 500 stands on the farm Groblersdal 844KS at Ga-Ratau | Finalised Authorised | Basic Services (Local Government)-Housing |  | Granted Authorisation Wholly |
| 12/1/9/1-GS108 | The proposed establishment of the new magnet height filling station in Ga Mogashoa village within Makhuduthamaga Local Municipality. The proposed filling station will have 5 underground petroleum tanks with the capacity of 23000 liters per tank and combined capacity of 115 cubic meters | Finalised Authorised | Energy Infrastructure |  | Granted Authorisation Wholly |
| 12/1/9/1-GS112 | The proposed establishment of a diesel depot in Jane Furse on portion 3 of the farm Vergelegen 819 KS |  | 1.3 Oil and Gas | Friday, June 26, 2015 | Granted Authorisation Wholly |
| 12/1/9/1-GS33 | Proposed construction of a vegetable pack-house at Dichoeung village on the farm Duizendannex 816 KS |  | Agricultural Value Chain + Agro-processing (linked to food security and food pricing imperatives) | 19.09.2013 |  |
| 12/1/9/2-GS9 | The proposed demarcation of 500 sites on portion 1 of the farm Uitkyk 851 KS at Mohlarekoma |  | Recreation and Hospitality Industry related infrastructure | 1/13/2012 | Granted Authorisation Wholly |

Source: LEDET 2016

Finalised EIAs in Makhuduthamaga in the 2018 finacial year

| Action Status | Project Title | Provincial Reference Number | Decision Date | Company Name |
| --- | --- | --- | --- | --- |
| Finalised Authorised | The proposed construction of a 55 m high telecommunication mast at Ga Moela village | 12/1/9/3-GS13 | 13/Apr/2018 | Ace Environmental Solutions |
| Finalised Authorised | The proposed construction of a 55 m high telecommunication mast at Lebading (BS139640) | 12/1/9/3-GS14 | 13/Apr/2018 | Ace Environmental Solutions |
| Finalised Authorised | The proposed construction of a filling station and associated infrastructure with a combined underground storage capacity of 490 cubic meters on the farm Vergelegen 819 KS | 12/1/9/1-GS164 | 16/May/2018 | She Efficiency Consultants (Pty) Ltd |
| Finalised Authorised | The proposed construction of an access bridge at Cabrieve/Khayelitsha village within Makhuduthamaga local municipality | 12/1/9/1-GS163 | 27/Aug/2018 | UFEFE Environmental Consulting |
| Finalised Authorised | The proposed development of a new filling station and associated infrastructure at Masemola village Apel Cross Pick n Pack building on farm Veeplaats KS | 12/1/9/1-GS169 | 14/Jan/2019 | SHEQ and Enviro Projects |

Environmental management challenge

| Challenges |  | Action Plan |
| --- | --- | --- |
| Non enforcement of bylaws | X | To ensure compliance to the bylaw |
| Community has little education on environmental issues | X | Develop and implement a environmental awareness programme for communities |
| The municipality has insufficient capacity on environmental management issues | X | To provide relevant training to the environmental officials |
| Rainfall pattern are highly variable, disrupting agricultural production and causing related socio economic stresses. | X | Investigate the possibility to harvest rain water |

### Environmental problems and associated development constraints

| Environmental issues | Status quo and environmental impact |
| --- | --- |
| Environment |  |
| Urban greening | - The Department of Public Works has launched the concept of Greening Sekhukhune District. There are also greenery programmes that are initiated by Dept. Of Agriculture that target governmental issues. |
| Alien Plant Spices | - Depleted water from the water sources. The National Department of environment is managing the programme of eradication of alien vegetation in the municipal area. Projects are being implemented in wards 12,13,14 and 16 - There is an invasion of land (mountains, flat land for grazing and agricultural usage) by foreign plants. These plants suffocate indigenous plants, denying them of water, fertile soil substances and space. These make livestock grazing space smaller. The indigenous plants get slowly depleted. |
| Pollution |  |
| Air Pollution | - Air pollution resulting from the use of fire wood for energy purpose, burning of refuses and dust from gravel roads are environmental problems. |
| Fires | - Uncontrolled fires are element of concern as far as the environment is concerned. |
| Water pollution | - Water pollution is the result of the calmative impact of the insufficient solid waste removal, lack of sanitation infrastructure, sewerage effluent etc. |
| Conservation |  |
| Erosion | - Informal and subsistence agriculture activities present particular problems. A typical; example is lack of arable land that forces communities to cultivate on steep slopes and other environmentally unsuitable area, which increases the occurrence of erosion with the resultant of fertile soil. - Wood is still one of the main sources of energy for households |
| Deforestation | - There is uncontrolled massive cutting of trees for sale, creating loss of vital trees and vegetation. This adds to the problem of soil erosion and inability of remaining poor soil to preserve water. Water simply just runs off. This worsens the aridity more. |
| Overharvesting of medicinal vegetation | - Some plants like aloes, dagga and’lewang” and others are overharvested by people from other areas for medicinal purposes. |
| Over utilization /overgrazing | - Overgrazing resulting from too many livestock units per area of land is a problem - One of the major environment problems in the area is incorrect agriculture methods, which leads to overgrazing, and denuding of trees. |
| Cultural Heritage | - The tourism potential of the Makhuduthamaga Municipality relates directly to the cultural heritage assets. |
| Waste | - There is formal waste collection at Jane Furse which covers Jane Furse, Phokoane and Schoonoord. The MLM has one waste recycling centre at Madibong. |
| Medical waste | - Two hospitals and about 21 clinics are found within the MLM. Currently, the Local and District Municipality conduct no medical waste collection. No facility for the management and disposal of medical waste exist. However, a private company, Buhle Waste Limpopo collects from all health institutions within the Municipality. Private surgeries have private companies to collect and dispose medical waste |
| By- laws | - Lack of bylaws to regulate environmental matters in the municipality |

## GIS Assesment

## The MLM has installed a Geographic Information System (GIS) located within the Economic   Development Planning Department. Complimentary to the System, the municipality has developed GIS Policy as a guiding mechanism for the effective running of the system.The policy was approved in the 2018/19 financila year. The system is however currently underutilised due to lack of capacity and expertise in the municipality.The municipality will employ officials in the 2019/20 financial year.

## Integrating with the everyday business database, GIS can represent inter alia;

## • Rate payer profiles by location, demography and income;

## • Service delivery by service, site, service provider and backlogs;

## • Site locations of stores, factories, and warehouses;

## • Assets location (e.g., utility poles, pipes, reservoirs and cables);

## • Resource locations of staff, products, and equipments; and

## • Emergency response routes

SPATIAL RATIONALE SWOT ANALYSIS

| STRENGTHS | - Fully complemented departmental HR - Sen. Manager appointed to lead the team - SDF in place - SMME support policy in place - LED Strategy in place - SMME database in place |
| --- | --- |
| WEAKNESSES | - No legal land ownership by Municipality - None availability of land use management system - None availability of building control regulation - None availability of spatial policies and by-laws - Staff component not gender balance |
| OPPORTUNITIES | - Jane Furse declared as a town(main economic node) - The town is identified as an administrative hub of the district - Clear spatial linkages with the surrounding areas - Several economic zones (nodes) identified - Potential of large scale maize and sorghum production - Potential of Economic growth |
| THREATS | - Poorly planned demarcation and allocation of sites by traditional authorities - Slow process to finalise SPLUMA by-law - No LUS and proper land use management - Dispersed settlements - Poor management of business development - Un-finalised land claims |

CHALLENGES

- Continuous demarcation of poorly planned sites by tribal authorities

- Poor LUMS

- Poor management of business development

- None availability of policies and by-laws

- No municipal land ownership

- Incomplete land claims

- No building control by-laws

- No spluma by-law

## 3.3 KPA 2:  Basic Service Delivery and Infrastructure development analysis

The chapter undertakes an analysis of infrastructure and basic services such as water, sanitation, electricity, housing, refuse removal, roads and storm water drainage system, public transport and telecommunication.

3.3.1 Water Infrastructure

Makhuduthamaga Municipality is neither a Water Services Authority nor a Water Services Provider .These functions were assigned to the Sekhukhune District Municipality

Settlements that are identified as hotspots (areas that need attention in terms of water challenges)

| Settlement name | Hot spot |
| --- | --- |
| 1.Ga Marishane | Service delivery protests and health risk (water quality) |
| 2.Maseshegwane | Service delivery protests and health risk( water quality) |
| 3.Matlakatle | Service delivery protests and health risk (water quality) |
| 4.Molebeledi | Service delivery protests and health risk (water quality) |
| 5.Thoto | Health risk (water quality) |
| 6.Dikathon | Service delivery protests and health risk (water quality) |

Source: DWS 2016

Makhuduthamaga Local Municipality New Water Schemes Development

| Settlement name | Hotspot | Project Description |
| --- | --- | --- |
| 1.Dihlabeng | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 2.Dinotsi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 3.Ga Machacha |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 4.Maila Segolo |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 5.Mogashoa Manamane | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 6.Mogashoa Dithlakaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 7.Ga Ratau |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 8.Hwafeng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 9.Kgaruthuthu |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 10.Makgeru |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 11.Malaeneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 12.Maololo |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 13.Mathapisa |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 14.Mamatsekele |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 15.Mohloding |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 16.Schoonoord | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 17.Thabeng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 18.Tsopaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 19.Zoetvelden |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |

Source: DWS 2016

Makhuduthamaga Local Municipality Water Schemes Refurbishment /Extension

| Settlement name | Hotspot | Project Description |
| --- | --- | --- |
| 1.Apel Cross | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 2.Apel Cross Low Cost Housing | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 3.Brooklyn |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 4.Disesane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 5.Eenzaam |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 6.Ga Madiba |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 7.Ga Magolego |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 8.Maila Mapitsane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 9.Ga Masemola | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 10.Ga Mohlala |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 11.Ga Mokadi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 12.Molepane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 13.Ga Moloi | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 14.Glen Cowie | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 15.Glen cowie Ext 1 |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 16.Glen Cowie Ext 2 |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 17.Goodhope |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 18.Hlahlane | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 19.Jane Furse | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 20.Jane Furse LCH |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 21.Kgwaripe |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 22.Klip |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 23.Klipspruit farm |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 24.Kutupu | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 25.Legotong |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 26.Lehlakong |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 27.Mabintwane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 28.Madibaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 29.Mahlolwaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 30.Mahlomola |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 31.Malegale |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 32.Manganeng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 33.Mangoanyane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 34.Maraganeng | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 35.Mare |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 36.Marulaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 37.Maseleseleng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 38.Maserumole Park |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 39.Mashite |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 40.Mathibeng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 41.Mmotwaneng |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 42.Mochadi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 43.Modiketsi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 44.Mogodi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 45.Mohlarekoma |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 46.Mokwete |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 47.Molapong |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 48.Nebo |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 49.Ngwaritsi |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 50.Nkotokwane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 51.Phelindaba |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 52.Phokwane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 53.Ramphelane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 54.Riverside | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 55.Sebetha | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 56.Sebetole |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 57.Sebitsane | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 58.Sekwati |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 59.Sekwati |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 60.Stoking | Service delivery protest /Health risk(water quality) | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 61.Takataka |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 62.Thabaleboto North |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 63.Thabampshe |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 64.Tlame |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 65.Tsatane |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 66.Tsatane Ext 1 |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 67.Tswaing |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 68.Vlakplaas A |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |
| 69.Vlakplaas B |  | Refurbishment O&M Water resources and extension interventions to ensure WS to villages in the water supply scheme |

Source: DWS 2016

Makhuduthamaga Local Municipality Water Conservation and Demand Management status

MLM receive water from the following schemes

- Arabie / Flag Boshielo RWS Central

- Arabie / Flag Boshielo RWS East Group 1

- Arabie / Flag Boshielo RWS East Group 2

- De Hoop Group 2 Upper Ngwaritsi

- De Hoop Group 3 Vergelegen Dam – Jane Furse

- De Hoop Group 4 Middle Ngwaritsi

- De Hoop Group 6 Nkadimeng

- De Hoop Group 7 Schoonoord Ratau

- De Hoop Group 8 Mampuru

- De Hoop Group 9 Spitskop Ngwaritsi

- De Hoop Group 10 Mahlangu

- Leolo Local Sources and

- Piet Gouws

| Municipality sources of water by population group of head of household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| Regional / local water scheme (operated by municipality or other service provider | 33 302 | 9 | 37 | 18 | 55 | 0 |
| Borehole | 5 759 | 2 | 28 | 13 | 15 | 0 |
| Spring | 2 876 | 0 | 3 | 2 | 1 | 0 |
| Rain water tank | 1 487 | 1 | 2 | 0 | 1 | 0 |
| Dam / pool / stagnant water | 5 847 | 2 | 2 | 2 | 4 | 0 |
| River /Stream | 11 045 | 4 | 5 | 12 | 9 | 0 |
| Water vendor | 1 905 | 0 | 2 | 0 | 2 | 0 |
| Water tanker | 1 758 | 2 | 1 | 1 | 1 | 0 |
| Other | 994 | 0 | 1 | 1 | 1 | 0 |

Source: Census 2011

MLM Households access to pipe water and backlog

| MLM | 2011 Census | Community Survey 2016 |
| --- | --- | --- |
| Households receiving water | 47 801 (73.4%) | 31 458 (48.6%) |
| Households not receiving water /Backlog | 17 416 | 33 312 |

Source: 2011 Census and Community Survey 2016

Source: Census 2011

Bulk water infrastructure analysis

Flag Boshielo dam has been raised by five meters to allow the dam to increase its supply to communities. Construction of De Hoop dam and erection of bulk water pipe to Jane Furse is completed and to Lobethal at an advanced stage. The two dams will improve state of water provision in the municipality and this will boost other development opportunities in the area. The pipe will supply water to greater parts of Makhuduthamaga which recently experience shortages of water due to poor water sources. The District is also currently investigating the development of a Community Water Supplies Master Plan. This will enable the District and its implementing agents to achieve its WSDP objectives. The intention is also to investigate alternative technical options for supplying specific areas with water and to ensure coordinated and implementation of the water supply infrastructure. Early findings of these studies reveal that groundwater is a major water resource for most households in Sekhukhune and will continue to do so in the future.

Developmental challenges:

- Water deficit within municipal area

- Stealing of both electric and diesel engine pipes

- Stealing of electricity transformers (it occurred several times in areas of ward 22 and 23)

- Breakdown of machines, illegal connections and extensions of settlements.

- Unable to access water at RDP standard in major areas of the municipality

National government‘s target was to eradicate all water supply backlogs by 2008.The target was not met. At the current rate of progress it will take another four to five years before all households have access to water within 200 meters.

3.3.2. Sanitation

The Sekhukhune District Municipality is responsible for sanitation provision .The provision of sanitation in Makhuduthamaga is also a major challenge to the municipality.

State of Sanitation infrastructure in MLM

MLM households by type of toilet facility - 1996, 2001 and 2011

| Flush /Chemical toilet |  |  | Pit toilet |  |  | Latrine |  |  | No toilets /Backlog |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 |
| 1 274 | 2 176 | 3 009 | 38 532 | 41 918 | 58 561 | 188 | 372 | 224 | 9 545 | 8 512 | 2 552 |

Source: Census 2011

The National government‘s target is to attain hundred percent of households with sanitation facilities at the RDP standard by 2010.With only 13043 (20%) households access to Sanitation at RDP and a backlog of 80% it is evident that the target will not be met. (Source SDM 2016)

Developmental challenges:

- Mountainous areas

- Budgetary constraints

- High backlog figures

### 3.3.3 Energy Efficiency and Electricity

Eskom is currently managing the electrification distribution networks in Makhuduthamaga.  The municipality is responsible for the provision of priority lists that are drawn in consultation with communities.There has been progress with respect to the provision of electricity to households in the municipality.  The progress could be attributed to effectiveness of INEP as a programme for eradication of electricity backlog. 93, 1 % of households (61 636) in Makhuduthamaga have access to electricity (2016 CS) as compared to 25, 1% in 1996.

Makhuduthamaga local municipality electricity backlog

| MLM | Households | Backlog |
| --- | --- | --- |
|  | 65 217 | 4565 |

Source: Eskom 2017

Number of connections completed per municipalities in the Sekhukhune District Municipality

| Municipality | 2014-2015 | 2015-2016 | 2016-2017 |
| --- | --- | --- | --- |
| Fetakgomo/Tubatse | 2370 | 2067 | 781 |
| Ephraim Mogale | 1061 | 1197 | 50 |
| Elias Motsoaledi | 1003 | 1470 | 584 |
| Makhuduthamaga | 1254 | 2706 | 628 |
| Total | 5688 | 7440 | 2043 |

Source: Eskom 2017

Number of connections planned in municipalities of Sekhukhune

| Municipality | 2017-2018 | 2018-2019 | 2019-2020 |
| --- | --- | --- | --- |
| Fetakgomo/Tubatse | 3195 | 1857 |  |
| Ephraim Mogale | 682 | 625 |  |
| Elias Motsoaledi | 1342 | 648 |  |
| Makhuduthamaga | 3694 | 1495 |  |
| Total | 8913 | 4625 |  |

Source: Eskom 2017

Number of post connections done per municipality in the District

| Municipality | 2014-2015 | 2015-2016 | 2016-2017 |
| --- | --- | --- | --- |
| Fetakgomo/Tubatse | 1920 | 1444 | 1729 |
| Ephraim Mogale | 303 | 408 | 340 |
| Elias Motsoaledi | 632 | 1066 | 968 |
| Makhuduthamaga | 943 | 901 | 1079 |
| Total | 3798 | 3819 | 4116 |

Source: Eskom 2017

Sources of Energy within Makhuduthamaga Municipal area

| Table: Energy or fuel for cooking by population group of head of the household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| Electricity | 32 114 | 14 | 59 | 27 | 80 | 0 |
| Gas | 572 | 1 | 12 | 3 | 2 | 0 |
| Paraffin | 3 371 | 2 | 1 | 2 | 4 | 0 |
| Wood | 27 106 | 3 | 7 | 16 | 4 | 0 |
| Coal | 803 | 0 | 1 | 0 | 1 | 0 |
| Animal dung | 811 | 0 | 1 | 0 | 0 | 0 |
| Solar | 86 | 0 | 0 | 1 | 0 | 0 |
| Other | 8 | 0 | 0 | 0 | 0 | 0 |
| None | 103 | 0 | 1 | 0 | 0 |  |

Source: Census 2011

| Table: Energy or fuel for heating by population group of head of the household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| Electricity | 23 548 | 13 | 66 | 23 | 66 | 0 |
| Gas | 481 | 0 | 1 | 0 | 1 | 0 |
| Paraffin | 931 | 1 | 1 | 0 | 4 | 0 |
| Wood | 29 015 | 4 | 8 | 21 | 7 | 0 |
| Coal | 3 312 | 0 | 1 | 1 | 1 | 0 |
| Animal dung | 741 | 0 | 1 | 0 | 0 | 0 |
| Solar | 58 | 0 | 0 | 0 | 0 | 0 |
| Other | 3 | 0 | 0 | 0 | 0 | 0 |
| None | 6 884 | 2 | 3 | 5 | 12 | 0 |

Source: Census 2011

| Table: Energy or fuel for lighting by population group of head of the household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| Electricity | 58 723 | 18 | 78 | 42 | 89 | 0 |
| Gas | 90 | 0 | 1 | 0 | 0 | 0 |
| Paraffin | 359 | 1 | 0 | 0 | 1 | 0 |
| Candles | 5 518 | 1 | 3 | 7 | 0 | 0 |
| Solar | 163 | 0 | 0 | 0 | 0 | 0 |
| Other | 0 | 0 | 0 | 0 | 0 | 0 |
| None | 121 | 0 | 0 | 0 | 0 | 0 |

Source: Census 2011

MLM Electricity priority list

| VILLAGES FOR ELECTRIFICATION IN 2016/17 FINANCIAL YEAR (2530 UNITS) | UNITS |
| --- | --- |
| 1.Mashishing | 100 |
| 2.Mashite | 25 |
| 3.Manganeng | 20 |
| 4.Manotong | 10 |
| 5.Mosehla | 120 |
| 6.Maila Segolo | 120 |
| 7.Dihlabaneng | 123 |
| 8.Mampane / Eenkantaan | 30 |
| 9.Mahlolwaneng | 105 |
| 10.Pelepele Park | 698 |
| 11.Moloi | 250 |
| 12.Moripane /Ngwanamatlang | 86 |
| 13.Mogorwane | 80 |
| 14.Diphagane | 96 |
| 15.Bothaspruit | 95 |
| 16.Makgane | 45 |
| 17.Mashengwaneng | 200 |
| 18.Kotsiri | 30 |
| 19.Kgolane | 27 |
| 20.Tisane | 50 |
| 21.Lobethal | 10 |
| 22.Machacha | 40 |
| 23.Mohwelere | 50 |
| 24 Makhuduthamaga Infills | 120 |
| VILLAGES FOR ELECTRIFICATION IN 2017/18 FINANCIAL YEAR (2728 UNITS) |  |
| 1.Kgarethuthu | 30 |
| 2.Mathapisa | 46 |
| 3.Kome | 46 |
| 4.Mangwanyane | 10 |
| 5.Mahwibitswane | 110 |
| 6.Hlalanikahle | 70 |
| 7.Semahlakole | 40 |
| 8.Stocking | 150 |
| 9.Ga- Moraba | 20 |
| 10.Serageng | 50 |
| 11.Lemating / Tsopaneng | 20 |
| 12.Molebeledi | 20 |
| 13.Nkotokwane | 15 |
| 14.Wonderboom | 20 |
| 15.Riverside / Maleetse | 100 |
| 16.Riverside / Lehwelere | 120 |
| 17.Khulwane / Lekurung | 60 |
| 18.Mokgapaneng | 260 |
| 19.Phushulang | 40 |
| 20.Moretsele | 73 |
| 21.Mangamolane / Mokgwatjane | 90 |
| 22.Patntshwane A &B | 40 |
| 23.Molelema / Machasdorp | 100 |
| 24.Sebitjane | 15 |
| 25.Maololo | 20 |
| 26.Soetveld | 15 |
| 27.Marishane | 60 |
| 28.Mohloding | 20 |
| 29.Leeukraaal | 28 |
| 30.Mogaladi | 50 |
| 31.Mashonyaneng | 30 |
| 32.Maraganeng | 20 |
| 33.Pitjaneng | 10 |
| 34.Phaahla | 100 |
| 35.Makalaneng | 15 |
| 36.Mare | 10 |
| 37.Vierfontein | 50 |
| 38.Masehlaneng | 45 |
| 39.Skotiphola | 10 |
| 40.Caprive | 550 |
| 41.Makhuduthamaga infills | 150 |
| VILLAGES FOR ELECTRIFICATION IN 2018/19 FINANCIAL YEAR (672 UNITS) |  |
| 1.Sekale / Apel Cross | 100 |
| 2.Thabampshe | 70 |
| 3.Mogudi | 115 |
| 4.Makoshala Ext 3 | 20 |
| 5.Ga- Maboki | 20 |
| 6.Mantlhanyane | 15 |
| 7.Malaka | 15 |
| 8.Ntoane | 10 |
| 9.Dikatone | 12 |
| 10.Setebong | 14 |
| 11.Khayeleitsha / Glen cowie | 81 |
| 12.Makhuduthamaga infills | 200 |
| VILLAGES FOR ELECTRIFICATION IN 2019/20 FINANCIAL YEAR (953 UNITS) |  |
| 1.Molepane | 100 |
| 2.Mogashoa Manamane | 100 |
| 3.Mmoteng Ext 5 | 195 |
| 4.Marulaneng | 75 |
| 5.Dinotji | 13 |
| 6.Kolokotela | 28 |
| 7.Vlakplaas | 27 |
| 8.Motseleope | 15 |
| 9.Ga- Sekele | 10 |
| 10.Dicheoung | 20 |
| 11.Mogorwane | 100 |
| 12.Masemola Police Station Extension | 50 |
| 13.Mamatjekele | 20 |
| 14.Makhuduthamaga infills | 200 |

Source: MLM 2016

Eskom Sekhukhune / Makhuduthamaga Electricity Network expansion Plan

Eskom has capacity and funding challenges in areas of Leolo due to nature of the area. As such Eskom was unable to electrify villages of Greater Komane as previously planned but designs for the area are completed and negotiations on additional funding with Department of Energy are at advanced stage. There are also minor incidents of lack of capacity from feeder lines in other areas of Makhuduthamaga and as a result some areas were taken out of the electrification priority list since 2011. But Eskom is working on the matter by upgrading Jane Furse substation and building 3 new substations (Mamatjekele, Uitkyk & Tjatane) to provide capacity for growth and electrification.

Below is map by Eskom showing new sub-stations to strengthen capacity in Sekhukhune / Makhuduthamaga Municipal area

| Challenges |  | Action plan |
| --- | --- | --- |
| Lack of capacity from feeder lines | x | Eskom erecting sub- station at Mamatjekele, Tjatane and Uitkyk and upgrading Jane Furse |
| Illegal connections to households | x | Community awareness and law enforcement |
| New extensions of residential sites for post connections | x | To include settlements in the priority list |
| Budgetary constraints | x | Request more funding from Department of Energy |

### 3.3.4 Refuse removal / waste management

The Waste Management function is performed by the MLM.There is a partial formal refuse removal service rendered by the municipality.The Municipality has a licensed authorized landfill site, Jane Furse landfill site.  There is also one waste recycling centre located in the landfill site.

Only 2% of the households in MLM have access to refuse removal services from the municipality.  About 89% of the households in the area use their own refuse dump.   There are 7% of the households with no access to rubbish disposal services.  The municipality has no drop-off, garden sites, transfer station, material recovery facilities and buy-back centres for recycling.

The larger number of households (89%) without access to refuse removal poses a threat to environmental quality.   Lack of provision of refuse removal services in the rural communities is mainly driven by land unavailability and inadequate financial resources since there is no cost recovery in these areas.

Below is a diagram for waste disposal and skips distribution:

| Place /Village | Quantity of Skips | Collection Frequency |
| --- | --- | --- |
| Vleeschboom | 1 | Once per week |
| Nebo | 2 | Once per week |
| Phokoane | 2 | 3 times a week |
| Glen Cowie | 3 | 3 times a week |
| Moloi | 1 | Once a week |
| Riverside | 2 | Twice a week |
| Jane Furse Old Hospital | 1 | Daily |
| Jane Furse New Hospital | 2 | Daily |
| Jane Furse Taxi ranks | 5 | Daily |
| Municipal Offices | 1 | Twice a week |
| Schoonoord | 2 | Twice a week |
| Tshehlwaneng | 2 | Twice a week |
| Mamone | 2 | Once a week |
| Marishane taxi rank | 2 | Twice a week |
| Ga Mashabela taxi rank (Mphanama Cross ) | 1 | Once a week |
| Masemola taxi rank / clinic | 2 | Once a week |
| Apel Cross | 1 | Twice a week |
| Jane Furse Crossing complex | 3 | Twice a week |

Source: MLM Community Services Department 2016

Table: Refuse disposal for Households within MLM – 1996, 2001 and 2011 and backlog

| Removed by local authority |  |  | Communal refuse dump / Backlog |  |  | No rubbish disposal /Backlog |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 |
| 3 073 | 463 | 1 639 | 39 323 | 46 992 | 58 636 | 6 572 | 5 523 | 4 631 |

Source: Census 2011

Waste water facilities within Makhuduthamaga

| Municipality | Facility | License status | Compliance status |
| --- | --- | --- | --- |
| MLM | Jane Fuse RDP oxidation ponds | Not licensed | Poorly managed |
|  | Jane Furse Old Hospital Oxidation ponds | Not licensed | Poorly managed |
|  | Jane Furse New Hospital Oxidation ponds | Not licensed | Poorly managed |
|  | Jane Furse Plaza Oxidation ponds | Not licensed | Poorly managed |
|  | Nebo oxidation ponds | Not licensed | Poorly managed |
|  | Phokoane oxidation ponds | Not licensed | Poorly managed |
|  | St Rita Hospital Oxidation Ponds | Not licensed | Poorly managed |
|  | St Mark College Oxidation Ponds | Not licensed | Poorly managed |

Source: LEDET 2016

State of Disposal site in Makhuduthamaga

| Disposal site | Permitted/Not Permitted | Absolute Location | Access | Operational hours | Security availability | Equipment | Cover material | Compaction | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jane Furse Landfill Site | Permitted as a GCB- | S24º 42’42.70″ E29º 53’2.71″ | The site is well fenced with lockable gate There are security personnel on site | 08h00-16h00 Monday - Friday | Security is available 24hrs Monday to Sunday | TLB | Stockpiled | No compaction | Management of the site is outsourced to Leolo Waste Management |

Table: State of Recycling sites within Makhuduthamaga Municipal Area

| NAME OF FACILITY | RECYCLABLES HANDLED(tons/month) | FINDINGS | ACTION REQUIRED |
| --- | --- | --- | --- |
| - Leolo( Office Suppliers & Services cc. | 318 of cardboard | - Not licensed but has registered as a business entity - Operate within Jane Furse landfill site - No storage facilities - Not reporting to the Department | - Need to provide storage area - Need to report quantities monthly to the Department |
|  | 169 of glass bottle |  |  |
| - Mmashadi Recycling trading as Jane Furse Recycling | 1.2 of cans | - Not licensed but has registered as a business entity - Operate within Jane Furse landfill site - Storage area available - Operational equipment available although not in use due to non availability of electricity - Not reporting to the Department | - Availability of electricity - Need to report quantities monthly to the Department |
|  | 8.9 of cardboard |  |  |
| - Molapowanotong Recycling | Not recorded | - Not licensed but has registered as a business entity with CIPC - Operates from rented site - No infrastructure - Not reporting to the Department | - Need to provide storage area - Need to report quantities monthly to the Department Acquisition of own site |
| - Phaahla Support Development Services former Letsema la Mmakadikwe | Not recorded | - No waste management license - No operational plan nor designated storage area - Not reporting to the Department | - Need to provide storage area - Need to report quantities monthly to the Department |
| - Thabampshe Youth Development Resource and Information Centre | Not sold | - Not licensed but has registered as a business entity with CIPC - Not fenced - No infrastructure - Not reporting | - Need to provide storage area - Fencing of the site - Need to report quantities monthly to the Department |
| - Marula Environmental Club | Not sold | - Not registered as a business entity - Operate from a rented site - No infrastructure - Not reporting | - Need to provide storage area - Fencing of the site - Need to report quantities monthly to the Department |

Source: LEDET, Waste Management 2016

Refuse Removal / Waste Management Challenges within Makhuduthamaga Local Municipality

| CHALLENGES | ACTION PLAN |
| --- | --- |
| No cost recovery | To implement cost recovery in 2019/20 |
| Refuse removals do not cover all villages | To extend service to all areas per financial year when funds permits |
| Informal disposal of waste | Continuous awareness campaigns |
| Maintenance of existing land fill site | Appointment of a service provider/ staff to maintain landfill site |
| Companies and communities utilizing municipal land fill site not paying for the service and this affects revenue collection negatively | To implement tariffs in 2019/20 |

### 3.3.5 Roads and Storm water drainage system

### Makhuduthamaga Municipality as a local municipality is responsible for the maintenance of all the internal roads in the residential areas and villages. The Provincial and District road network is currently the responsibility of the Roads Agency Limpopo and the provincial Department of Public Works, Roads and Transport.

The Municipality has a road network of 452 kilometres which include both provincial and local roads.  The local access roads are gravel and predominantly utilised for commuting.The condition of these roads is below standard and they require upgrading and improved storm water management

Storm water drainage system is needed in all gravel roads because all roads as only a few portions of the paved/tarred roads have storm water drainage.  Some of the key challenges identified include: high cost of tarring of roads; grading of internal access roads; construction of bridges; budgetary constraints; and high storm water drainage backlog

State of roads infrastructure and backlogs within Makhuduthamaga local municipality in terms of the MLM road and storm water master plan

| Village serviced | Type of road | Length (km) | State | General remarks |
| --- | --- | --- | --- | --- |
| Ka-Mabule | Only access | 3.6 | Unpaved | The only access to this village, currently inaccessible with a normal vehicle. Needs immediate action |
| Ga-Sekele | District | 3 | Unpaved | This road has been earmarked for upgrade by the provincial government but it is deemed that more immediate action is required. |
| Emkhondweni | District | 2.5 | Unpaved | Further down the road from Ga-Sekele. Situation is the same as for the previous village. |
| Ga-Mokgoadi | District | 4.3 | Unpaved | The furthest away from Schoonoord so it must be handled after the previous two villages. Action is required very soon though. |
| Geluk | Only access | 4.3 | Unpaved | The road has been constructed and for the most part is still in very good condition, but some areas have become eroded and almost impassable with a normal vehicle. Also provides access to two other villages. |
| Sekele | Only access | 3.4 | Unpaved | Next in line from Geluk. Road situation is the same however and it is the only access to Hoepakrantz |
| Hoepakrantz | Only access | 3.3 | Unpaved | Last village in this road. The road is worse for this last section and need immediate action. |
| Kanaan A | Only access | 0.6 | Unpaved | The current road is very small and needs to be upgraded. Only serves a small number of the population though. |
| Tsopaneng | District | 3.5 | Unpaved | This is a district road but is currently not earmarked by the provincial or district government for upgrading even though it needs to be upgraded urgently. |
| Soupiana | District | 7.6 | Unpaved | Gets access through Tsopaneng. Some very steep areas that needs immediate attention and upgrading. Also a district road. |
| Malaka B, Mantlhanyane, Botshabelo, Ntoane | District | 10.3 | Unpaved | This is a provincial road with these villages scattered along it. This road has not been earmarked by any of the other authorities but it needs action soon as it is impassable in some places. |
| Pitjaneng | Only access | 2.3 | Unpaved | For the most part this road is adequate for the amount of traffic, but some boulders are exposed and some bad areas are present at the start of the road. |
| Maseleseleng | Only access | 1.3 | Unpaved | Access to the village from the provincial road. Small road that needs to be upgraded soon as erosion are fast becoming a problem. |
| Matlakatle B&C | District | 3.2 | Unpaved | The road is washed away between B and C but both villages can be accessed from different locations. This road is not earmarked for upgrade by the other authorities. |
| Maololo | Only access | 5.6 | Unpaved | Currently easily accessible but there are signs that the road are deteriorating. This is the only access to this village. |
| Kanaan B | District | 12.4 | Unpaved - Bridge Required | This road is impassible but a bridge is busy being constructed. Further upgrading of the road needs to be done soon. |
| Moripane | District | 1.4 | Unpaved - Bridge Required | The road has deteriorated so the only access is from the D4045 road. This will however be impassible during the rainy season as it crosses a stream. Needs to be upgraded soon but it is not earmarked by the other authorities. |
| Phokoane | Internal roads | 8 | Unpaved and paved - Good | A good network of paved and unpaved roads currently exists. Some provision has been made to fill in the gaps. The length given is for this internal road only. |
| Jane Furse | Internal roads | 22 | Unpaved and paved - Good and average | The situation is the same as for Phokoane. Jane Furse and Phokoane have also been recognized by the provincial government as growth points within the municipal area. |
| Makgeru, Ga-Mogashoa, Senkgapudi, Ga-Ratau, Manamane | Internal roads | 12 (D 4.5) | Unpaved, paved and blocks - Good | Same as for the previous two villages. These villages have been grouped together due to their close proximity to each other. |
| Kapaneng, Ga-Marishane, Ga-Phaahla | Internal roads | 4 | Unpaved and paved - Good | Paved and unpaved roads cross through these villages to provide a good network of roads. Provision has been made for filling in the gaps. |
| Ga-Masemola | Internal roads | 7 (D 6) | Unpaved and paved - Good | Once again the district roads provide a good network but some internal roads have been identified as being necessary. In general the roads are in good condition. |
|  | roads |  | paved - Good | Houses further away from the paved road. |
| Schoonoord | Internal | 9 | Unpaved and | Build mostly along the D4190 but some internal roads need to be upgraded to provide access to the |
| Apel Cross LCH | Internal roads | 3 | Unpaved and paved - Good | The district roads cross through this village but additional internal roads is required to provide very good access. |
| Mogaladi, Mogaladi Ext 3 | Only access | 1.7 | Unpaved | The road passing through Mogaladi is paved but access to Ext 3 of the village need to be upgraded as it is currently not a very good road. |
| Klipspruit | Only access | 1.8 | Unpaved | A small village which gains access through Ga-Madiba. Upgrading this road will benefit both theses villages. This is the only access to this village. |
| Disesane | Only access | 1.8 | Unpaved and under construction | Final section of this road is currently being upgraded. The rest also needs to be improved as it also provides access to Molapong and Ga-Magolego. |
| Molapong | Only access | 1.5 | Unpaved | Also serves as an access to Ga-Magolego. Pipe laying next to the road have narrowed the road significantly but it is predicted that this will be rectified as soon as construction is finished. |
| Ga-Magolego | Only access | 2.1 | Unpaved and concrete - Bad | For the most part this road is a concrete path leading up to the village. This footpath does however require maintenance as it has started to break up in some areas. The rest of the road is drivable. |
| Mashite, Modiketsi, Ga-Maila | District | 0.9 | Unpaved | This 0.9 km is in addition to the district road already passing through these villages. The current district road is in good condition. |
| Semahlakole | District | 0.7 | Unpaved | The road passing through this village is a lower order district road as can be seen on the photos. This road is the only access road to this village so must be upgraded. |
| Kome | Internal roads | 2.5 | Unpaved | This is quite a long and narrow village so this road will provide access to the entire village. Currently a very narrow and winding road. The district road nearby have been earmarked to be upgraded. |
| Ga-Malaka | Internal roads | 1 (D 3.8) | Unpaved - Bridge Required | The district road has been earmarked for upgrade by the higher authorities. The 1 km internal road will provide greatly improved access throughout the village. |
| Vleescboom | Internal roads | 1 | Unpaved and paved - Good | This village is not indicated on the map but it runs alongside the D4295 near Nebo. The proposed road forms a loop going through the centre of the village. |
| Glen Cowie | Internal roads | 1.2 | Unpaved | Well maintained district roads running parallel to each other enclose this village on two sides. The proposed road running through the village will provide a link between these roads. |
|  | District | 7.6 | Unpaved | The road is in good condition, but might need some maintenance especially near Madibaneng. This is a district road but no plans for upgrading of this road by the higher authorities have been identified. |
| Kgwaripe | District | 0.8 | Unpaved | The district road passing through the village is in bad condition but it has been earmarked by the provincial government for upgrading. Currently a paved road pass near the village and this is seen as adequate access. |
| Sephoto | Only access | 0.8 (D 3) | Unpaved | The 0.8 km provides access internal to the village. This is however not in immediate need of an upgrade. The district road has been identified to be in need of an upgrade by the higher authorities. |
| Ga-Moloi | Internal roads | 2.4 | Unpaved | Situation is the same as for Glen Cowie. This road will pass through the village and provide a link to the two district roads passing close by. |
| Ga-Maila-Segolo | Internal roads | 1.8 (D 1.5) | Unpaved and paved - Very bad | Currently the provincial road is not in good condition but it has been identified as being in need of a upgrade. The 1.8 km internal road is important as some of the houses are far from the provincial road |
| Thamagane | Only access | 0.8 | Unpaved | Important because it is the only access to the village but is currently in good condition. |
| Maraganeng | Only access | 0.6 | Unpaved | Village is close to the D 4260 which has been identified to be upgraded to a paved road. This access road shows signs of erosion but it is not yet critical. |
| Mapitsane | Only access | 0.9 | Unpaved | Access from the district road. Currently not a well constructed road but for the time being it has an acceptable driving standard. |
| Mahloloaneng | District | 1.2 (D 4.6) | Unpaved | Access to the village is good via Malope but the road deteriorates in the village and is not easily drivable and very winding pass the dam. Upgrading of this section is not seen as critical but must be done in the near future. |
| Sebetsane, Mathibeng, Dinotsi | District | 4.7 | Unpaved | No action is required from the local municipality as this road have been identified for upgrading by the provincial government. If this action however take too long to be implemented the state of this road will become critical. |
| Makhutso | District | 4.5 | Unpaved | The district road serves the entire length of the village before ending at a reservoir at the end of the village. The current condition is not great however but it still provides an acceptable driving experience. |
| Malope | Internal roads | 2.4 | Unpaved | Close to a paved road but the internal roads need to be upgraded as they are currently not in a good condition. |
| Riverside | Internal roads | 2.6 | Unpaved | A paved road pass through the centre of the village but good internal roads to provide access to the furthest away houses is not existent. |
| Thoto | Internal roads | 1 (D 2.8) | Unpaved | The 1 km section of internal road pass through mountainous terrain and erosion is a problem. This road has to be upgraded to provide access to a school. |
| Serageng | District | 1.6 | Unpaved | The district road nearby have been identified to be upgraded by the higher authorities. Access from that road to this village has a lot of very loose material and erosion will become a problem. |
| Tshatane | Internal roads | 3 | Unpaved and under construction | A district road provides access to this village but internal access roads have to be upgraded to provide the link to another adjacent district road. |
| Polaseng | Only access | 3.5 | Unpaved | Village is close to a main road. Road have been changed previously due to erosion being a problem. Currently the road is in good condition. |
| Kgaruthuthu | Only access | 1.1 | Unpaved | Road is in good condition and provides an acceptable driving experience. |
| Ga-Madiba | Internal roads | 1.5 | Unpaved | Runs along the D 1547 which is a paved road. Additional access must in future be provided to service more of the inhabitants. |
| Setlaboswane | Internal roads | 1.6 | Unpaved | Adjacent to a paved road. Internal roads must be constructed to provide better access to the village. |
| Brooklyn | Internal roads | 0.5 | Unpaved | Needs additional internal roads to provide complete access to the village. |
| Hwafeng | District | 3 | Unpaved and paved - Very bad | Road is in good condition. Some bad sections where previous efforts to pave the road have deteriorated to form a lot of potholes. |
| Mahlomola | District | 0.8 (D 2.7) | Unpaved | District road is in bad condition and must be upgraded along with an internal section to provide internal access to the village. |
| Mphanama | District | 6 | Unpaved | Access provided by provincial road which has been identified as one that needs to be upgraded. No further action required by the municipality. |
| Nkotokwane | Internal roads | 0.8 | Unpaved | Close to the district road but the internal roads have to be upgraded to provide access to and from the district road. |
| Matlakatle | Internal roads | 1.3 (D 5.9) | Unpaved | Close by district road have been earmarked for upgrading. An internal road will ease the access for the further away houses. |
| Ramphelane, Tjatane ext 1 | Internal roads | 3.3 | Unpaved | Village is located all along the west of road D 4190 but an internal road is required to run through the centre of the village. |
| Ga-Masehlaneng | Internal roads | 3.5 | Unpaved and paved - Bad | Very rocky area. The main road is paved but is severely deteriorated. A district road provides good access to the village but internal roads is in bad condition. |
| Ga-Machacha | District | 4 | Unpaved | Gets access via a district road that pass through the village. The current condition is satisfactory but maintenance will have to be done in the future. No additional internal roads are required. |
| Patantshwane, Patantshwane B, Lekorokorwaneng,Lehlakong,Eensaam, Eensaam LCH | District | 18.5 | Unpaved | This is an access road to a lot of villages. It is a district road but maintenance needs to be done urgently to fix the couple of bad sections along this road. |
| Ga-Tisane | District | 1.7 | Unpaved | Two access via two different district roads. Some bad sections but in general a good driving experience. |
| Mohwelere | Internal roads | 1 | Unpaved and paved - Good | Mountainous on the edge of the village. Rest of the roads is winding and very uneven. Paved road pass through the centre of the village. |
| Mogodi | Internal roads | 1 | Unpaved | Internal road will provide access to the houses furthest away from the district road. This district road has been identified as one that needs upgrading. |
| Maseshegoane | Internal roads | 0.7 | Unpaved | Village is linked to Ga-Machacha via a small road. This road needs to be upgraded to provide an acceptable access road. |
| Ga- Mashabela | Internal roads | 1 | Unpaved | Close to a paved road. Very rocky internal roads that must be upgraded to provide access to the furthest houses. |
| Manganeng | Internal roads | 1.3 | Unpaved | A well maintained district road provides access to most of the village. Some internal roads need to be upgraded to provide the subserviced households. |
| Thabeng | Internal roads | 2.6 | Unpaved | The district road passing close by has been earmarked for upgrading by the higher authorities. Internal access needs to be upgraded as it is currently limited to a narrow road. |
| Sebetha | Internal roads | 1.5 (D 2.1) | Unpaved and paved - Good | A small section of the road needs to be upgraded urgently, but the rest is in good condition and need not be upgraded in the near future. |
| Mampe | Internal roads | 0.3 | Unpaved | Only a short non critical section of road needs to be upgraded to provide access for the inhabitants of this village. |
| Masanteng | Internal roads | 1.7 | Unpaved | On one side the village is bordered by a well maintained district road. The upgrading of the ring road currently situated within the village will provide good access. |
| Lobethal | District | 2 | Unpaved | The current access is via a district road. The road is in good condition and no urgent upgrading or maintenance is required. |
| Sehuswane | District | 2.4 | Unpaved | Also serves as an access to Semahlakole. Currently the road is in good condition. |
| Ga-Mampane | District | 0.9 | Unpaved | This small section of the district road is sufficient to provide access to the village. It is also key to providing access for Makhutso. |
| Mamatjekele | District | 1.2 | Unpaved and paved - Average | The district road has been paved inside the village. This paved road needs maintenance as potholes are forming on the surface. The approach from either side is in good condition. |
| Mare | District | 2.8 | Unpaved | The road leading up to this village has been earmarked for upgrade by the provincial government so no further action is required. |
| Zoetvelden | Internal roads | 1.1 | Unpaved | Access from the district road is in good condition. Minor upkeep and maintenance required. |
| Manotou | Internal roads | 0.9 (D 3.8) | Unpaved | The district road has been identified by provincial government for upgrading. The internal road is not a necessity but will provide better access |
| Thabampshe | Internal roads | 2 (D 5.8) | Unpaved | This village requires an upgraded internal road to provide access to some of the furthest houses. Currently only a limited number of the inhabitants are served by a district road. |
| Mangwanyane | Internal roads | 1.8 | Unpaved | The internal road is almost impassible at present. This road needs to be upgraded for ease of movement but the close by district road has been earmarked to be upgraded. |
| Mokwete | District | 3 | Unpaved | A very good district road that also serves Ga-Molepane. No immediate action required. |
| Ga-Molepane | District | 4.2 | Unpaved | A very good district road that also serves Ga-Molepane. No immediate action required. |
| Magolapong, Ga Maloa, Phushulang | District | 11 | Unpaved | A very good road connecting all this villages to the paved roads. As they are building along the road no internal access is required. |
| Kutupu | District | 1 (D 9.6) | Unpaved and paved - Good | Serviced by a paved road from Mabintwane's side. The unpaved section is also good and no further roads are required. This is a district road. |
| Ngwaritsi | District | 4 | Unpaved | From the one side the road is paved and from the other side it has been earmarked for an upgrade. This road provides sufficient access to this village. |
| Moomane North | District | 3.3 | Unpaved | The district road is still in a fairly good condition and it has been identified as one of the roads to be upgraded by the provincial government. No internal access road is required at this stage. |
| Sekwati | Internal roads | 4.5 | Unpaved and paved - Good | This village is served by a network of district roads passing through it. An additional 4.5 km of internal roads will fill in the gaps. This is however only necessary for future planning. |
| Krokodel Heuwel | Internal roads | 2.2 (D 3.4) | Unpaved | The internal road will complete the distribution network of this village. The current district roads are in good condition. |
| Greenside | Internal roads | 0.6 (D 2.3) | Unpaved | The district road is of acceptable standard. The internal road has a lot of surface water running on the road even in the dry season and special care must be taken to handle this water. |
| Glen Cowie Ext 2 | Internal roads | 1.1 | Unpaved and paved - Average | Enclosed by district roads on two sides and a very good internal road on a third. Internal roads might need to be constructed in future. |
| Molebeledi | Internal roads | 2.2 (D 2.5) | Unpaved | This is a longitudinal village which has a acceptable internal road network. This road must however be maintained to keep on providing this level of access. |
| Maserumule Park, Nebo | Internal roads | 3 | Unpaved and paved - Good | Have been identified as a growth point in the area. A limited network of paved roads exists but it has to be completed by upgrading the internal roads. |
| Dikatone | Internal roads | 0.8 (D 2.5) | Unpaved | Very good district road pass through the village but an internal road is required to provide access to the further away houses. |
| Thabanapitsi | Internal roads | 1 (D 2.9) | Unpaved | Good access provided by the district roads. A internal road will provide complete and easy access to the entire village. |
| Makgwabe | District | 1.7 | Unpaved | Serviced by two district roads which are in good condition. This village and De Paarl can be seen as one village |
| De Paarl | District | 1.9 | Unpaved | Serviced by two district roads which are in good condition. This village and De Paarl can be seen as one village |
| Vlakplaas A | Internal roads | 1.5 | Unpaved | Village is close to a paved provincial road and internal roads are acceptable but an improvement will increase the living standard of inhabitants. |
| Vlakplaas B | Internal roads | 0.5 | Unpaved | Village is close to a paved provincial road and internal roads are acceptable but an improvement will increase the living standard of inhabitants. |
| Tswaing | Internal roads | 1.9 | Unpaved | Village is close to a paved provincial road and internal roads are acceptable but an improvement will increase the living standard of inhabitants |
| Moswanyaneng | Internal roads | 0.7 (D 5.9) | Unpaved | Road in good condition with scattered bad sections |
| Glen Cowie Ext 1 | Internal roads | 2.2 | Blocks - Need cleaning | A paving block ring road exists within the village but maintenance needs to be done as unwanted material have ingresses from the side of the road. |
| Marulaneng | Internal roads | 2 (D 2.6) | Unpaved | This village is serviced by two district roads which are in acceptable condition. Internal roads are not critical but it will provide better access through the village. |
| Setebong | District | 2.5 | Unpaved | One or two bad sections are present on this district road but in general the road is in very good condition. |
| Mathapisa | District | 1.5 | Unpaved | This road is currently in good condition and it has been identified to be upgraded by the higher authorities. No action is required from the local municipality. |
| Phelindaba | Internal roads | 1.9 | Unpaved | A district road which is in very good condition passes through the village. An internal road has been identified for upgrade but it is not at all critical. |
| Dihlabeng | Only access | 1.6 | Unpaved | This village has been abandoned some time back. No population remains in this area. The road is only used by people looking to gather fire wood. |
| TOTAL KMS |  | 322,69 KMS | Unpaved |  |

Source: MLM Road Master Plan, 2014

Makhuduthamaga Local Municipality roads priority list as per District and Provincial list

| Priority no: | Road no. | Type of maintenance required |  | Road particulars | District | Local | Wards | Growth point |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Major access roads |  |  |  |  |  |  |  |  |  |
| 1 | D4260 | Upgrading from gravel to tar |  | Malope to Phokoane | SDM | MLM | 29,31,24,03 | Phokoane/Apel Cross |  |
| 2 | D4280 | Upgrading from gravel to tar |  | Glen Cowie via Thoto via Eensaam join Leeukraal | SDM | MLM | 09,06,07,05 | Phokoane |  |
| 3 | D4225 | Upgrading from gravel to tar |  | Madibong to Manganeng | SDM | MLM | 19,17,23 | Schoonoord/Jane Furse |  |
| 4 | D4251 | Upgrading from gravel to tar |  | Mashabela- Mphanama | SDM | MLM | 25 | Apel Cross |  |
| 5 | D4263 | Upgrading from gravel to tar |  | Phaahla to Masehlaneng | SDM | MLM | 24 | Apel Cross |  |
| Minor access roads |  |  |  |  |  |  |  |  |  |
| 1 | D4233 | Upgrading from gravel to tar |  | Moela-Kgopane | SDM | MLM | 14 |  | Schoonoord |
| 2 | D4232 | Upgrading from gravel to tar |  | Mabule | SDM | MLM | 14 |  | Schoonoord |
| 3 | D4264 | Upgrading from gravel to tar |  | Mathapisa road to Vlakplaas to Masehlaneng | SDM | MLM | 26,24,31 |  | Apel Cross |
| 4 | D4271 | Upgrading from gravel to tar |  | Ga-Moloi to Phokoane | SDM | MLM | 29,31,24,03 |  | Phokoane/Jane Furse |
| 5 | D4255 | Upgrading from gravel to tar |  | Thabampshe cross to Mahubitswane | SDM | MLM | 27,28 |  | Apel Cross |
| Preventative |  |  |  |  |  |  |  |  |  |
| 1 | D4253 | Preventative | Access road to Masemola Clinic |  | SDM | MLM | 27,28 |  | Apel Cross |
| 2 | D2219 | Preventative | Phokoane to Tshehlwaneng |  | SDM | MLM | 03,05,09,0 |  | Jane Furse/Phokoane |
| 3 | D4295 | Preventative | Phokoane to Moratiwa |  | SDM | MLM | 03,05,04,0 |  | Phokoane |

Source: MLM Roads Priority list, 2015

Road network

The total road network in Makhuduthamaga is estimated at nearly 452 km which include both provincial and local roads.

Makhuduthamaga local municipality roads and storm water drainage

| MLM | Households | Backlog |
| --- | --- | --- |
|  | 65 217 | 76 Bridges needed to improve mobility and accessibility for villagers |
|  |  | 255,49 Kms of MLM roads not paved or tarred |

Source: MLM Road Master Plan

Strategic Road Network and Hierarchy

| Strategic Road Network and Hierarchy | Description of Road Class |
| --- | --- |
| Provincial road R579 | Primary provincial arterial |
| Arterial routes Road: D4280,D4379,DD4250,D4200,2219 | Primary arterial routes providing vehicular mobility with limited off street access. These roads are generally the ring roads around districts providing external circulation but can also traverse the district itself - Facilitates regional mobility of traffic - Characterised by regional route continuity - Generally, the nature of these roads would not allow the construction of lay-bys or other public transport facilities. In rural areas like MLM these routes should also have a public transport role. However, a thoroughly assessed and traffic impact analysis should be undertaken where the need for a lay-by or public transport facility has been identified especially rural and peri-urban areas |
| Distributor and collector routes Roads:D4225,D4287,D4370,D4285,D4280,D4254,D4217,D4350,D4267 | Miner arterial road /collector road serving as internal vehicular circulation road within the municipal area - Primary arterial routes providing vehicular mobility with limited off street access - These roads serve a municipal /regional mobility function-connecting places of importance throughout the municipality and linking to the wider region - Generally, the nature of these roads would allow the construction of lay-bys or other public transport facilities - Facilitates long distance traffic mobility |
| Internal roads: Collector and streets | There is currently a weak internal road hierarchy. The informal nature of most of the villages makes it very difficult to development an appropriate hierarchy. The SDF will provide proposals and guidelines but detail transport and movement studies will have to be done. At local level there are no street names which further complicate the matter. Local collector roads serve as public transport routes and major pedestrians routes. As a minimum, taxi pick up and drop off points need to be provided. |

Source: MLM Reviewed SDF 2016

| Challenges |  | Action |
| --- | --- | --- |
| The high cost of tarring of roads | X | Investigate alternative to tarring of roads |
| Grading of internal access roads( streets) | X | Make financial provision for grading of internal roads |
| Construction of bridges | X |  |
| Budgetary constraints | X | Identify potential funders for roads infrastructure |
| High storm water drainage backlog | X | Include Storm water projects in MIG and ES projects and on all new roads projects |

3.3.6 Public Transport

The Department of Transport, Safety and Liaison is the Public Transport Authority. The Sekhukhune District Municipality helps in respect of transport planning. The major public transport services are bus and taxi operations. The bus industry is weakened as a result of insufficient government funding and internal management capacities. The taxi industry is well established.   The Municipality has several Taxis Associations operating within the municipal area.

In the past five years, the Department has never approved any additional trips to operators owing to financial constraints experienced by the Department. This has resulted in high overloading pressures in the District. Bus Operators in these areas continue to operate additional unsubsidized trips to ease the overload burden and going forward this has a potential to collapse the entire bus transport system should the operators decide to withdraw all the trips whose operational costs they continue to cushion without any assistance from the government.  Additional subsidy is required in this regard as a matter of urgency to address all the gaps identified and historical disparities.

The Great North Transport, Sekhukhune Express and Thembalethu are the only bus operators within Makhuduthamaga municipal area with conventional fixed routes and a fixed schedule system that provides passengers with public transport to work in the morning and back home in the evening

The Municipality through its Community Service department facilitated the granting of Operating Certificate to Operators of Meter Taxis to Jane Furse Maxi Taxi Association that operated in Jane Furse.

Unregulated and influx of  Mini taxis operating as metered taxis within Jane Furse area are posing a threat to road users as majority of them are not road-worthy. The Municipality, SAPS and the Department together with organised meter taxis in the area are doing everything in their power to address the challenge.

Provincial roads that are found within Makhuduthamaga municipal area are R579 that runs from Jane Furse to Stofberg and the R555 that run from Jane Furse to Burgersfort.

Integrated Transport Plans

It is a requirement in terms of the National Land Transport Act 2009 that municipalities develop Integrated Transport Plans (ITPs). In the absence of ITP’s it is difficult to consider applications for public transport operating licenses hence the Department decided to assist municipalities with the development of ITP’s for the growth points in the province. The Makhuduthamaga local municipality has a Draft Integrated Transport Plan which indicates that the municipality has one mode of transport found in the area, viz, road transport.

Public Transport Conflicts:

There is a high demand for new operating licenses by registered members and aspirant operators alike resulting in an increased number of new applications for the registration of new taxi associations.  Most of the conflicts are fuelled by individuals operating without operating licenses.

Road Safety

Concerted enforcement and educational campaigns in the Province managed to reduce fatalities with 31.8% during the financial year 2012/13. Speeding remains the highest contributory factor (60%) to possible causes of accidents in the Province which poses a major challenge to the Department. For further reduction of the accidents there will be a need to implement fixed speed enforcement cameras at certain strategic areas.

From 2009 the number of fatalities decreased annually. Though the number of fatalities decreases the number of road accidents increased drastically. This is linked to the increase in vehicle population yearly.

Limpopo Vehicle Population & Traffic Law Enforcement Officers

| Authority | Capricorn | Mopani | Sekhukhune | Vhembe | Waterberg | Head Office | Sub-Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Provincial | 220 | 156 | 107 | 210 | 210 | 23 | 926 |
| Municipal | 105 | 46 | 48 | 65 | 64 | 0 | 328 |
| Total | 325 | 202 | 155 | 275 | 274 | 23 | 1 254 |

Source: Department of Security, Safety and Liaison 2016

Taxi ranks in the Makhuduthamaga municipal area and their state of infrastructure

| Name of Taxi Rank | Ward | Village where rank stationed | State of infrastructure |
| --- | --- | --- | --- |
| 1.Jane Furse | 18 | Dichoeung | Has Shelter, loading bays, toilets, paved, skip and mast lights. No seating facilities and water |
| 2.Jane Furse Plaza | 18 | Vergelegen C | Has Shelter, loading bays, toilets, paved, skip, and water and mast lights. No seating facilities |
| 3.Schoonoord | 14 | Schoonoord | Has Shelter, loading bays, paved, skip and mast lights. No seating facilities, toilets and water |
| 4.Phokoane | 03 | Phokoane | Has loading bay, paved and skip. No seating facilities,water,shelter |
| 5.Vierfonten | 04 | Vierfontein | Has Shelter, loading bays, paved, skip and mast light. No seating facilities, toilets and water |
| 6.Masemola | 28 | Apel Cross | Has Shelter, loading bays, paved, skip, toilets and water and mast light. No seating facilities |
| 7.Moratiwa Plaza | 01 | Moratiwa Crossing | Informal. No shelter, loading bay, water and toilets |
| 8.Tshehlwaneng | 13 | Tshehlwaneng | Informal. Has mast light and skip. No shelter, loading bay, water and toilets. |
| 9.Malegale | 22 | Malegale | Informal. Has a Mast light and skip No shelter, loading bay, water and toilets |
| 10.New Jane Furse Hospital | 20 | Mashishing | Informal. Has skip. No shelter, loading bay, water and toilets |
| 11.Glen Cowie | 09 | Malaka Cross | Informal. Has a mast light and skip. No shelter, loading bays, water and toilets |
| 12.Marishane | 26 | Mapurunyane Cross | Informal. Has mast lights and skip. No shelter, loading bays, water and toilets |
| 13.Maserumole Park | 05 | Maserumule Park | Informal. Has skip. No mast lights, shelter, loading bays, water and toilets |
| 14.Mphanama Cross | 25 | Mphanama | Informal. Has skip. No mast lights, shelter, loading bays, water and toilets |
| 15.Mampane | 31 | Mampane | Informal. Has skip. No mast lights, shelter, loading bays, water and toilets |
| 16.Mogaladi | 30 | Mogaladi | Informal. Has skip. No mast lights, shelter, loading bays, water and toilets |
| 17.Thabampshe Cross | 28 | Thabampshe | Informal. Has skip. No mast lights, shelter, loading bays, water and toilets |

Source: MLM 2016

The Provincial and District road network is currently the responsibility of the Roads Agency Limpopo (RAL) and the Department of Public Works, Roads and Transport (Limpopo). The RAL utilise the Road Management System (RMS) as a tool for assisting with road network management.

| Challenge |  | Action |
| --- | --- | --- |
| Taxis fighting for the use of certain routes | X | Municipality public safety must organise meetings together witH Provincial Department of Transport in order to get amicable solution to the conflict |
| Regulation and control of meter taxis around Jane Furse | X | Ensure proper control of meter taxis |
| Poor roads infrastructure | X | Develop and implement road infrastructure maintenance plan |
| Traffic congestion in Jane Furse | X | By-pass roads to build to reduce congestion |
| No transport facilities in some parts of the municipality | X | To negotiate with taxi associations and bus companies to provide transport |
| Lack of public transport in some areas due to poor roads infrastructure | X | To engage DoRT to tar roads that belongs to the department |

3.3.7 Free Basic Services

The Sekhukhune District Municipality (SDM) is implementing FBW. The process began by compiling the indigent registers and development of indigent policy. The District also had yard connections of water in some areas within MLM in order that the households whose monthly income is beyond R 3400 can pay for the services while those below qualify for 6 kilolitres of water free of charge every month. This service, however, never took off due to delays by authority to develop relevant by-laws. To date, all households with yard connections regardless of their indigent status get Free Basic Water.

Sanitation service is also provided free to all households by Sekhukhune District Municipality.

The MLM provides Free Basic Electricity (FBE) .The number of households that receive FBE is 7912 to date.

1 639 households in Makhuduthamaga receive free refuse removal service through pilot project. The programme ensures that every household within the collection area i.e. Jane Furse, Phokoane, Glen Cowie and Schoonoord gets its refuse removed once per week without.

3.3.8 Housing / Integrated Human Settlements

The responsibility for Housing is that of Human Settlements in the Departments of CoGHSTA. The municipality gets allocation of houses from CoGHSTA and is only required to identify and submit the names of beneficiaries. The Department is responsible for the implementation of the projects. It has a Draft Housing Sector Plan and will be adopted during the 2017/18 financial year. All the housing stock is located within a rural setting made up of traditional authority settlements. The character of the area is viewed as rural even where some form of settlement formalization processes has been implemented. Informal dwelling / shacks need some attention although it is not a major problem.

Number of RDP housing units constructed

| # Municipality | # Financial year |  |  |
| --- | --- | --- | --- |
|  | # 2014-2015 | # 2015-2016 | # 2016-2017 |
| # Makhuduthamaga | # 0 | # 449 | # 201 |

Source: CoGHSTA, Human Settlement, 2017

Number of RDP housing units planned

| # Municipality | # Financial year |  |  |
| --- | --- | --- | --- |
|  | # 2017-2018 | # 2018-2019 | # 2019-2020 |
| # Makhuduthamaga | # 418 | # 448 | # 473 |

Source: CoGHSTA, Human Settlement, 2017

Makhuduthamaga local municipality housing backlog

| MLM | Households | Backlog |
| --- | --- | --- |
|  | 65 217 | 6 908 |

Source: MLM 2017

| Table: EA type by population group of head of the household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| LIM473: MLM |  |  |  |  |  |  |
| Formal residential | 1 388 | 2 | 1 | 0 | 5 | 0 |
| Informal residential | 0 | 0 | 0 | 0 | 0 | 0 |
| Traditional residential | 62 769 | 17 | 78 | 48 | 86 | 0 |
| Farms | 0 | 0 | 0 | 0 | 0 | 0 |
| Parks and recreation | 0 | 0 | 0 | 0 | 0 | 0 |
| Collective living quarters | 86 | 1 | 3 | 0 | 0 | 0 |
| Industrial | 0 | 0 | 0 | 0 | 0 | 0 |
| Small holdings | 0 | 0 | 0 | 0 | 0 | 0 |
| Vacant | 731 | 0 | 0 | 1 | 0 | 0 |
| Commercial | 0 | 0 | 0 | 0 | 0 | 0 |

Source: Census 2011

| Table: Number of rooms by population group of head of the household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| 1 | 3 727 | 4 | 11 | 3 | 19 | 0 |
| 2 | 4 738 | 5 | 17 | 2 | 25 | 0 |
| 3 | 6 515 | 2 | 13 | 6 | 19 | 0 |
| 4 | 10 583 | 1 | 14 | 6 | 5 | 0 |
| 5 | 10 610 | 1 | 7 | 12 | 8 | 0 |
| 6 | 10 986 | 2 | 9 | 5 | 5 | 0 |
| 7 | 8 156 | 4 | 2 | 4 | 4 | 0 |
| 8 | 4 911 | 0 | 4 | 3 | 2 | 0 |
| 9 | 2 458 | 1 | 2 | 4 | 2 | 0 |
| 10 | 1 137 | 0 | 0 | 1 | 0 | 0 |
| 11 | 562 | 0 | 1 | 3 | 0 | 0 |
| 12 | 316 | 0 | 1 | 0 | 0 | 0 |
| 13 | 125 | 0 | 0 | 0 | 0 | 0 |
| 14 | 69 | 0 | 0 | 0 | 0 | 0 |
| 15 | 34 | 0 | 0 | 0 | 0 | 0 |
| 16 | 14 | 0 | 0 | 0 | 0 | 0 |
| 17 | 10 | 0 | 0 | 0 | 0 | 0 |
| 18 | 6 | 0 | 0 | 0 | 0 | 0 |
| 19 | 4 | 0 | 0 | 0 | 0 | 0 |
| 20 | 12 | 0 | 0 | 0 | 0 | 0 |
| 21 | 0 | 0 | 0 | 0 | 0 | 0 |

Source: Census 2011

| Table: MLM type of main dwelling and Population group of head of household |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| LIM473: MLM |  |  |  |  |  |  |
| House or brick/concrete block structure on a separate stand or yard or on a farm | 57 538 | 17 | 69 | 38 | 83 | - |
| Traditional dwelling/hut/structure made of traditional materials | 2 810 | - | 3 | 6 | - | - |
| Flat or apartment in a block of flats | 205 | - | 2 | 1 | - | - |
| Cluster house in complex | 26 | - | - | - | - | - |
| Townhouse (semi-detached house in a complex) | 16 | - | - | - | - | - |
| Semi-detached house | 31 | - | 1 | - | 1 | - |
| House/flat/room in backyard | 302 | 1 | 4 | 1 | 1 | - |
| Informal dwelling (shack; in backyard) | 1 475 | - | 1 | - | 1 | - |
| Informal dwelling (shack; not in backyard; e.g. in an informal/squatter settlement or on a farm) | 1 919 | - | - | 1 | 1 | - |
| Room/flatlet on a property or larger dwelling/servants quarters/granny flat | 404 | 1 | - | - | 1 | - |
| Caravan/tent | 28 | - | - | - | 1 | - |
| Other | 222 | 1 | 2 | 1 | - |  |

Source: Census 2011

Most houses in the municipality are situated on separate stands and this indicates potential for future formalization and upgrading.  Enormous housing backlogs building up at urban areas due to influx of people to these areas resulting in large numbers of informal dwellings / shacks in backyards and an open land.  Due to envisaged development in Jane Furse proper housing plan needs to be developed.

Number of incomplete houses in Makhuduthamaga

| Municipality | Current number of incomplete houses |
| --- | --- |
| Makhuduthamaga | 2012/13- 0 |
|  | 2013/14 - 0 |
|  | 2014/15- 3 W/P (3 houses) |
|  | 2015/16- 43 FND , 67 W/P |

Source: CoGHSTA, Human Settlement, 2017

MLM Housing Priority List

| Ward no | Village |
| --- | --- |
| 08 | Brooklyn |
| 30 | Mogaladi |
| 31 | Eenkantaan |
| 15 | Ga -Magolego |
| 20 | Tisane/Lobethal |
| 11 | Vergelegen A |
| 07 | Mantlhanyane |
| 30 | Setlaboswane |
| 17 | Mashite |
| 20 | Mamoshalela |
| 08 | Caprive |
| 31 | Vlakplaas |
| 23 | Marulaneng |
| 08 | Uitkyk Mochadi |
| 30 | Serageng |
| 30 | Masanteng |
| 29 | Makgwabe |
| 30 | Legotong |
| 22 | Matolokwaneng |
| 07 | Dikatone |
| 31 | Makhutso |
| 31 | Motseleope |
| 15 | Tswele |
| 07 | Setebong |
| 30 | Kolokotela |
| 29 | Mphane |
| 19 | Madibong |
| 21 | Mashishing |
| 25 | Mohwelere |
| 21 | Mohlala |
| 29 | Pitjaneng |
| 21 | Kgoloko |
| 11 | Mokwete |
| 21 | Vergelegen C |
| 24 | Masehlaneng |
| Total |  |

Source: MLM 2013

| CHALLENGES |  | ACTION PLAN |
| --- | --- | --- |
| Incomplete houses within the municipality | X | Request the Department to complete all suspended/ incomplete housing projects |
| Slow housing delivery which is caused by shortage of funding | X | Submit annual plans and backlogs to Provincial Human Settlements Department to increase funding |
| Lack of necessary infrastructural services such as water, sanitation and roads. | X | Plan for infrastructure services in consultation with District Municipality |
| No adequate land within MLM municipal area belonging to the municipality and some of the land that belongs to other spheres of government are subject to land claim | X | Acquire more land for housing development |
| Lacking of consumer education for housing matters | X | Request provincial Department to provide consumer education |
| Community dynamics delay project implementation | X | Enhance community participation efforts |

The pace at which RDP housing is moving coupled with incomplete and substandard quality constructed RDP houses makes it difficult to confidently forecast that housing target can be achieved in Makhuduthamaga by 2024.

3.3.9 Social grants

State of infrastructure in Pay points within Makhuduthamaga Local Municipality

| No. of pay points Existing 2013/14 with/without buildings respectively | Backlogs on Pay points | Basic services Supplied for each pay point(e.g. YES/NO) |
| --- | --- | --- |
| 117 Pay points With buildings=20 Without =97 | No backlogs | Yes=20 No=97 |

Source: SASSA 2018

Statistics on grant beneficiaries

| O/A | D/G | W/V | COM | GIA | FCG BEN | FCG chil | CDG BEN | CDG CHIL | CSG BEN | CSG CHIL | BENEFI | CHILDREN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 28877 | 5691 | 0 | 40 | 287 | 2633 | 3942 | 805 | 868 | 50332 | 100233 | 88665 | 105043 |

Source: SASSA 2018

Number of individuals benefitting from Social Relief Programmes:

| Makhuduthamaga Food parcels beneficiaries | Number |
| --- | --- |
|  | 260 |

Source: Department of Social Development, 2015

Infrastructure

Makhuduthamaga has 111 service points (Pay points) whereby community members can access social grants on monthly basis. It has 6 permanent and 4 temporary offices whereby applications for grants and other services can be made

| CHALLENGES |  | ACTION |
| --- | --- | --- |
| Limited funds to address shelter, access roads and water at pay points | X | Collaborate with Department of Social Development, SASSA, NGO and CBOs to address the identified challenges |

3.3.10 Education

The strategic goals of Department of Basic Education

- Improved delivery of quality education

- Improved capacity of the department to  support delivery of quality education

Summary of Norms and Standards

- Ratio of Teacher Learner: Primary: 1:40: Secondary: 1:35

- Total walking distance to and from may not exceed 10km

- Learners who reside outside the determined radius may be provided with transport.

- Every learner has access to minimum set of text books

The Municipality has established a Bursary Fund to assist youth from disadvantage families to study at Tertiary level. The Makhuduthamaga Municipal Council during the 2009/10 financial year resolved to fund students who will pursue their studies in Infrastructure/ Engineering Development, Planning or Finance to address the skills gap within Makhuduthamaga. Currently (2018) the Municipality has forty nine (49) bursary holders.New intake (2019) is twelve (12) which brings a total to sixty one (61)

3.3.10.1 Early Childhood Development

State of Early childhood Development (ECD) / Crèches within Makhuduthamaga Municipal area

| Number of ECD | Fully/Conditionally Registered ECD Centres | Not funded ECD | Funded ECD | Overall backlog for ECD centres | Overall backlog for ECD centres |
| --- | --- | --- | --- | --- | --- |
| 170 | 167 19 fully | 55 | 115 | 35 | 2017/18=13 2018/19=14 2019/20=16 |

Source: Department of Social Development 2019

Challenges with regard to ECDs

- Mushrooming of ECD sites

- Lack and poor infrastructure

- High illiteracy rate

3.3.10.2. Schools in Makhuduthamaga

Number of schools in Makhuduthamaga

| Municipality | Secondary | Primary | Combined | Private | Special |
| --- | --- | --- | --- | --- | --- |
|  | 115 schools | 195 schools | 4 schools | 03 | 04 |

Source: Department of Education 2017

Number of current teachers and learners per municipalities in Sekhukhune

| Municipality | Total number of schools | Total number of teachers | Total number of learners | Student-teacher ratio |
| --- | --- | --- | --- | --- |
| Fetakgomo/ Tubatse | 340 | 3989 | 130861 | 1:33 |
| Ephraim Mogale | 62 | 925 | 31564 | 1:34 |
| Elias Motsoaledi | 207 | 3138 | 98796 | 1:32 |
| Makhuduthamaga | 321 | 3802 | 125427 | 1:33 |
| Total | 930 | 11854 | 386648 | 1:33 |

Matric pass rate in Sekhukhune Municipalities

| Municipality | 2014 pass rate | 2015 pass rate | 2016 pass rate |
| --- | --- | --- | --- |
| Fetakgomo | 62.4 | 55.5 | 50.6 |
| Greater Tubatse | 64.4 | 53.3 | 47.2 |
| Ephraim Mogale | 64.1 | 55.9 | 48.8 |
| Elias Motsoaledi | 66.8 | 56.9 | 55.6 |
| Makhuduthamaga | 61.8 | 59.0 | 53.8 |
| Total | 63.9 | 55.0 | 51.8 |

Matric targeted pass rate per municipalities in Sekhukhune

| Municipality | 2018 | 2019 | 2020 |
| --- | --- | --- | --- |
| Fetakgomo/ Tubatse | 70% | 75% | 80% |
| Ephraim Mogale | 70% | 75% | 80% |
| Elias Motsoaledi | 75% | 80% | 85% |
| Makhuduthamaga | 75% | 80% | 85% |
| Total | 72% | 78% | 85% |

Public School per quintile in MLM

| Quintile 1 | Quintile 2 | Quintile 3 | Quintile 4 | Quintile 5 |
| --- | --- | --- | --- | --- |
| 273 | 39 | 02 | 03 | 01 |

Source: Department of Education 2017

Number of class rooms planned for construction in Sekhukhune Municipalities

| Municipality | 2017-2018 | 2018-2019 | 2019-2020 |
| --- | --- | --- | --- |
| Fetakgomo/ Tubatse | 14 | 103 | 82 |
| Ephraim Mogale | 10 | 21 | 12 |
| Elias Motsoaledi | 09 | 45 | 40 |
| Makhuduthamaga | 21 | 66 | 59 |
| Total | 54 | 235 | 193 |

Source: Department of Education 2018

Current backlogs to school infrastructure (buildings)

| Municipality | 2017/2018 |
| --- | --- |
| Fetakgomo/ Tubatse | 14 |
| Ephraim Mogale | 10 |
| Elias Motsoaledi | 09 |
| Makhuduthamaga | 21 |
| Total | 54 |

Source: Department of Education Limpopo 2016

Schools needing infrastructure

| Municipality | 2017/2018 |
| --- | --- |
| Fetakgomo/ Tubatse | 82 |
| Ephraim Mogale | 12 |
| Elias Motsoaledi | 40 |
| Makhuduthamaga | 59 |
| Total | 193 |

Current condition of road access to schools

| Municipality | Good, fair or bad (choose) |
| --- | --- |
| Fetakgomo/ Tubatse | Fair |
| Ephraim Mogale | Fair |
| Elias Motsoaledi | Fair |
| Makhuduthamaga | Fair |

Current provision of basic services to schools (water, sanitation, electricity).

| Municipality | Good, fair or bad (choose) |
| --- | --- |
| Fetakgomo/ Tubatse | Fair |
| Ephraim Mogale | Fair |
| Elias Motsoaledi | Fair |
| Makhuduthamaga | Fair |

| Table:MLM Education Profile |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other |
| LIM473: MLM |  |  |  |  |  |
| Male |  |  |  |  |  |
| Grade 0 | 6 331 | 1 | 6 | 0 | 3 |
| Grade 1 / Sub A | 4 919 | 3 | 1 | 2 | 1 |
| Grade 2 / Sub B | 4 629 | 2 | 1 | 3 | 2 |
| Grade 3 / Std 1/ABET 1Kha Ri Gude;SANLI | 4 947 | 1 | 5 | 3 | 3 |
| Grade 4 / Std 2 | 5 282 | 0 | 2 | 0 | 4 |
| Grade 5 / Std 3/ABET 2 | 5 126 | 0 | 9 | 3 | 1 |
| Grade 6 / Std 4 | 5 489 | 1 | 3 | 5 | 8 |
| Grade 7 / Std 5/ ABET 3 | 6 075 | 1 | 9 | 1 | 10 |
| Grade 8 / Std 6 / Form 1 | 8 238 | 4 | 23 | 3 | 9 |
| Grade 9 / Std 7 / Form 2/ ABET 4 | 7 969 | 1 | 13 | 0 | 12 |
| Grade 10 / Std 8 / Form 3 | 9 343 | 2 | 25 | 7 | 13 |
| Grade 11 / Std 9 / Form 4 | 8 425 | 3 | 11 | 3 | 22 |
| Grade 12 / Std 10 / Form 5 | 10 753 | 6 | 68 | 7 | 27 |
| NTC I / N1/ NIC/ V Level 2 | 87 | 0 | 0 | 1 | 0 |
| NTC II / N2/ NIC/ V Level 3 | 96 | 0 | 0 | 1 | 0 |
| NTC III /N3/ NIC/ V Level 4 | 116 | 0 | 1 | 0 | 0 |
| N4 / NTC 4 | 101 | 0 | 0 | 2 | 0 |
| N5 /NTC 5 | 93 | 0 | 0 | 1 | 0 |
| N6 / NTC 6 | 171 | 0 | 1 | 0 | 0 |
| Certificate with less than Grade 12 / Std 10 | 68 | 0 | 0 | 0 | 0 |
| Diploma with less than Grade 12 / Std 10 | 72 | 0 | 0 | 0 | 1 |
| Certificate with Grade 12 / Std 10 | 339 | 0 | 0 | 1 | 0 |
| Diploma with Grade 12 / Std 10 | 675 | 2 | 1 | 0 | 1 |
| Higher Diploma | 601 | 1 | 3 | 1 | 0 |
| Post Higher Diploma Masters; Doctoral Diploma | 108 | 0 | 1 | 0 | 0 |
| Bachelors Degree | 386 | 0 | 8 | 0 | 0 |
| Bachelors Degree and Post graduate Diploma | 159 | 0 | 1 | 0 | 0 |
| Honours degree | 208 | 0 | 5 | 0 | 1 |
| Higher Degree Masters / PhD | 115 | 0 | 1 | 1 | 0 |
| Other | 83 | 0 | 1 | 0 | 0 |
| No schooling | 10 077 | 1 | 3 | 3 | 17 |
| Unspecified | 0 | 0 | 0 | 0 | 0 |
| Not applicable | 19 715 | 19 | 17 | 17 | 13 |
| Female |  |  |  |  |  |
| Grade 0 | 6 317 | 2 | 1 | 1 | 1 |
| Grade 1 / Sub A | 4 976 | 3 | 3 | 3 | 2 |
| Grade 2 / Sub B | 4 789 | 1 | 2 | 1 | 0 |
| Grade 3 / Std 1/ABET 1Kha Ri Gude;SANLI | 5 177 | 1 | 6 | 1 | 0 |
| Grade 4 / Std 2 | 5 178 | 0 | 6 | 1 | 1 |
| Grade 5 / Std 3/ABET 2 | 5 166 | 0 | 4 | 2 | 1 |
| Grade 6 / Std 4 | 5 283 | 2 | 2 | 1 | 2 |
| Grade 7 / Std 5/ ABET 3 | 6 249 | 2 | 3 | 3 | 4 |
| Grade 8 / Std 6 / Form 1 | 8 011 | 2 | 5 | 2 | 3 |
| Grade 9 / Std 7 / Form 2/ ABET 4 | 8 517 | 2 | 9 | 2 | 5 |
| Grade 10 / Std 8 / Form 3 | 12 031 | 1 | 9 | 9 | 6 |
| Grade 11 / Std 9 / Form 4 | 13 970 | 3 | 15 | 5 | 11 |
| Grade 12 / Std 10 / Form 5 | 18 875 | 3 | 15 | 15 | 5 |
| NTC I / N1/ NIC/ V Level 2 | 82 | 0 | 0 | 0 | 0 |
| NTC II / N2/ NIC/ V Level 3 | 88 | 0 | 0 | 0 | 0 |
| NTC III /N3/ NIC/ V Level 4 | 130 | 1 | 0 | 0 | 0 |
| N4 / NTC 4 | 125 | 1 | 0 | 0 | 0 |
| N5 /NTC 5 | 140 | 0 | 0 | 0 | 0 |
| N6 / NTC 6 | 256 | 0 | 0 | 0 | 0 |
| Certificate with less than Grade 12 / Std 10 | 100 | 0 | 0 | 1 | 0 |
| Diploma with less than Grade 12 / Std 10 | 124 | 0 | 0 | 0 | 0 |
| Certificate with Grade 12 / Std 10 | 664 | 0 | 1 | 0 | 0 |
| Diploma with Grade 12 / Std 10 | 1 168 | 0 | 0 | 0 | 0 |
| Higher Diploma | 1 071 | 1 | 0 | 0 | 0 |
| Post Higher Diploma Masters; Doctoral Diploma | 138 | 0 | 1 | 0 | 0 |
| Bachelors Degree | 485 | 0 | 0 | 3 | 0 |
| Bachelors Degree and Post graduate Diploma | 192 | 0 | 2 | 0 | 0 |
| Honours degree | 283 | 0 | 0 | 1 | 0 |
| Higher Degree Masters / PhD | 89 | 0 | 0 | 0 | 0 |
| Other | 99 | 0 | 0 | 0 | 0 |
| No schooling | 23 421 | 5 | 4 | 15 | 4 |
| Unspecified | 0 | 0 | 0 | 0 | 0 |
| Not applicable | 19 576 | 26 | 16 | 18 |  |

Source: Census 2011

| Table:MLM 2011 highest level of education grouped, gender and population group |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other |
| LIM473: Makhuduthamaga |  |  |  |  |  |
| Male |  |  |  |  |  |
| No schooling | 10 077 | 1 | 3 | 3 | 17 |
| Some primary | 36 723 | 9 | 28 | 17 | 23 |
| Completed primary | 6 075 | 1 | 9 | 1 | 10 |
| Some secondary | 34 297 | 11 | 72 | 15 | 57 |
| Grade 12/Std 10 | 10 753 | 6 | 68 | 7 | 27 |
| Higher | 3 072 | 3 | 22 | 6 | 2 |
| Other | - | - | - | - | - |
| Unspecified | 83 | - | 1 | - | - |
| Not applicable | 19 715 | 19 | 17 | 17 | 13 |
| Female |  |  |  |  |  |
| No schooling | 23 421 | 5 | 4 | 15 | 4 |
| Some primary | 36 885 | 10 | 26 | 11 | 8 |
| Completed primary | 6 249 | 2 | 3 | 3 | 4 |
| Some secondary | 42 924 | 9 | 38 | 19 | 25 |
| Grade 12/Std 10 | 18 875 | 3 | 15 | 15 | 5 |
| Higher | 4 741 | 3 | 4 | 4 | - |
| Other | - | - | - | - | - |
| Unspecified | 99 | - | - | - | - |
| Not applicable | 19 576 | 26 | 16 | 18 | 7 |

Source: Census 2011

| Census 2011 by municipalities, school attendance, gender and population group |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Black African | Coloured | Indian or Asian | White | Other | Unspecified |
| LIM473: MLM |  |  |  |  |  |  |
| Male |  |  |  |  |  |  |
| Yes | 53 829 | 15 | 36 | 16 | 13 | - |
| No | 45 351 | 15 | 168 | 33 | 123 | - |
| Do not know | 48 | - | - | - | - | - |
| Unspecified | 1 852 | - | - | 1 | - | - |
| Not applicable | 19 715 | 19 | 17 | 17 | 13 | - |
| Female |  |  |  |  |  |  |
| Yes | 51 752 | 12 | 31 | 19 | 3 | - |
| No | 78 380 | 20 | 52 | 45 | 44 | - |
| Do not know | 96 | - | - | - | - | - |
| Unspecified | 2 965 | - | 7 | 3 | - | - |
| Not applicable | 19 576 | 26 | 16 | 18 | 7 |  |

Source: Census 2011

| CHALLENGES |  | ACTION |
| --- | --- | --- |
| Development and support of Early Childhood development. | X | Develop ECD policy and establish ECD Forum |
| Delivery of basic services like sanitation, water and electricity to schools. | X | Liaise with DoE and SDM for the provision of services |
| Lack of effective literacy campaigns and ABET Centres to reduce illiteracy level. | X | Liaise with DoE |
| Lack of leaner ships and bursary schemes for students. | X | Establish a new Bursary Committee and award Bursaries to deserving students as per policy |
| Lack of tertiary institutions within Makhuduthamaga make percentage of people with post Matric qualifications very low. | X | Negotiate with tertiary institutions to establish satellite centres within MLM |
| Poor access roads to school that hampers Scholar Transport-Transportation, National School Nutrition-deliveries , and Monitoring | x | Municipality to prioritise maintenance and tarring of roads to schools |

3.3.11 Health facilities and services

Access to health services as per norms and standards

| Health facility | Radius distance in kilometers |
| --- | --- |
| Access to hospitals | 50km radius |
| Access to clinics | 5km walking distance |
| Access to Mobile | +10km from clinic |

Source: Department of Health 2017

Provision of health services within Makhuduthamaga is not satisfactory. This view derives from generally low levels of services combined with poor health infrastructure. Makhuduthamaga has only two public hospitals i.e. Jane Furse and St Rita’s hospitals, 21 clinics and 45 mobile clinic service points

Health facility Profile for the Municipality

| Number of existing Hospitals | Number of existing Clinics | Number of existing mobile clinics | Number of Private hospitals |
| --- | --- | --- | --- |
| 2 | 21 | 45 | 0 |

Source: Department of Health Limpopo 2017

Availability of mobile clinics and their frequency of visits

| Municipality | Number of mobile clinics | Total number of points | Frequency of visits/availability |
| --- | --- | --- | --- |
| Makhuduthamaga | 4 teams+ 1 sub team | 50 | 22 weekly visit 27 bi-weekly visit 1 monthly visit |

Source: Department of Health Limpopo 2017

Facilities Constructed from 2012/13-2014/15 within the Municipal area

| Municipality | Hospitals Constructed |  |  | Clinics Constructed |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2012/13 | 2013/14 | 2014/15 | 2012/13 | 2013/14 | 2014/2015 |
| MLM | 0 | 0 | 0 | Marulaneng | Jane Furse Gateway clinic,Mamone | 0 |

Source: Department of Health Limpopo 2016

Backlogs of clinics as per norms and standards

| Municipality | Backlog |
| --- | --- |
| Makhuduthamaga | 1.Mamakgosefoka |
|  | 2.Maila Mapitsane |
|  | 3.Hoeperkrans |
|  | 2.Madibaneng |
|  | 3.Molepane –Mokwete clinic |

Source: Department of Health Limpopo 2017

Number of clinics planned

| Municipality | 2017-2018 | 2018-2019 | 2019-2020 |
| --- | --- | --- | --- |
| Makhuduthamaga | 1(Mamokgasefoka) | Madibaneng-Malegale-Tjatane | Dichoeung Health Centre |

Source: Department of Health Limpopo 2017

Specific areas without health facilities and how they are being catered for

| Municipality |  |
| --- | --- |
| Makhuduthamaga | Malegale-Madibaneng-Tjatane and Maila Mapitsane both served by mobile weekly |

Source: Department of Health Limpopo 2017

Health facilities that needs upgrading

| Health facility | Ward |
| --- | --- |
| Patantshwane | 06 |
| Rietfontein | 04 |
| Klipspruit | 01 |
| Setlaboswane | 31 |
| Magalies | 21 |

Source: Department of Health 2016

| Challenges: |  | Action |
| --- | --- | --- |
| Poor access roads | X | To prioritise access roads to health facilities |
| Inadequate transportation | X | Advise the Department to make provision for patient transport in the next financial year |
| Inadequate health infrastructure | X | Request the department to complete incomplete health facilities and upgrade dilapidated ones |
| Lack of medication at clinics and mobile clinic | X | Advise Department to make adequate provision and ,manage medication effectively |

3.3.12 Libraries

The responsibility for the establishment of libraries rests within the Provincial function. However, Makhuduthamaga Local Municipality operates four libraries within its area of jurisdiction on behalf of the Department of Sports, Arts and Culture. There is a Service Level Agreement between the Municipality and the Department. The rural nature of the municipality renders accessibility ineffective. While more libraries would be needed they should be located at densely populated areas and provided with internet access.

| MUNICIPALITIES | NUMBER OF PUBLIC LIBRARIES EXISTING | STATE OF THE LIBRARIES (materials, access, personnel) |
| --- | --- | --- |
| MLM | 1. Ga-Phaahla, 2.Patantswane 3. Jane Furse. 4.Phokoane | Ga-Phaahla - Access- accessible to the community. - Materials- Academic books are a need in the community. - Personnel 04 Patantswane - Access- accessible to the community. - Materials- Academic books are a need in the community. - Personnel- 02, Jane Furse - Access- Not accessible to the community - Materials- adequate materials suitable for users’ needs. - Personnel- 01 Phokoane - Construction completed and officially opened on the 30th January 2018 by Department of Sports,Arts and Culture |

Libraries norms and standards

One (1) library per 10 000 house hold

| Challenges |  | Action |
| --- | --- | --- |
| Lack of libraries in the remote areas of the municipality | X | Establishment of mobile libraries in the said areas. |
| Limited budget for outreach programs |  | Development of library activity calendar and its presentation to guide the budget allocation. |
| Poor condition of access roads |  | Paving of access road. |
| Lack of library site boards along the main road. |  | Placement of the library site boards along the road to enable the marketing process and accessibility |
| Location of Jane Furse library |  | Relocation of Jane Furse library to the accessible area ( construction of city library in Jane Furse) |
| Lack of information about the library services to both the municipality and the community. |  | Enhance library outreach programmes in partnership with schools in areas that are not serviced |
| Shortage of staff |  | Addition of library staff as per the work load demand |

3.3.13 Thusong Service Centres

The National Government initiated the Thusong Service Centre concept which seeks to provide one stop government services and facilities to communities.

There are no Thusong centres in the municipality. The state of affair denies the community of socializing and access to services. The establishment of Thusong Centres would assist. Engagements with the Office of the Premier concluded that mobile/ temporary service centres will be established while awaiting the conclusion of the acquisition of land for such. The Thusong Service centres as envisaged by National Government are based on a 6 –Block Service Model which seeks to integrate and provide all or most of the following services in one community located facility: Government Social and administrative Office, Education and skills Development, Local Economic Development, Business Services and Community Opportunities ; and Information and communication.

The Municipality has negotiated with Masemola Traditional Council to release a land in the area to build the centre.A budget is set aside in the 2018/19 financial year to kick start the project.

3.3.14 Municipal Park and Cemeteries

Public places and local amenities are issues that are often raised during public engagement processes. The following programmes and projects have been identified to address issues related to a clean environment:

| Area | Projects |
| --- | --- |
| Construction Projects( Community Works Programme ) | Area Beautification Fencing of graveyards School surrounding cleaning |
| Enhanced Healthy Environment ( CWP) | Promotion of food gardens projects/ food security |
| Environmental Affairs | Clearing of Alien vegetation |

The Municipality has developed a Municipal Park at Jane Furse township .The area is fenced with palisate fence and will be developed further in the 2018/19 financial year.The municipality is also  engaging traditional leaders and other stakeholders on earmarked areas for municipal cemeteries per cluster.

| Challenges |  | Action |
| --- | --- | --- |
| Inadequate social amenities | X | Development of municipal park at Jane Furse continuing |

MLM Priority List for fencing of Community Cemeteries for 2016/2017-2020/21 F/Years

| Financial year | Cemetery | Ward no |
| --- | --- | --- |
| 2016-2017 |  |  |
|  | Maila Segolo | 23 |
|  | Dihlwadieme | 02 |
|  | Vierfontein | 04 |
|  | Matlakatle | 05 |
|  | Moloi Lehwelere | 10 |
|  | Thapedi | 21 |
|  | Beletlwa Dry | 22 |
|  | Serageng | 30 |
|  | Mampana | 31 |
|  | Thabanaswana | 28 |
|  | Mohwelere | 25 |
|  | Mogashoa Manamane | 13 |
|  | Dichoeung | 18 |
| 2017-2018 | Cemetery | Ward no |
|  | Mare | 06 |
|  | Tlame | 02 |
|  | Leeukraal | 05 |
|  | Tisana | 20 |
|  | Difapye | 21 |
|  | MorganzanA Glen Cowie | 09 |
|  | Senamela | 12 |
|  | Mogashoa Letamong | 13 |
|  | Marulaneng | 23 |
|  | Mathapisa Moeding wa mahea | 26 |
|  | Setan | 28 |
|  | Makgwabe | 29 |
| 2018-2019 | Cemetery | Ward no |
|  | Tshehla | 01 |
|  | Ponong | 06 |
|  | Mohlarekoma | 05 |
|  | Phushulang | 10 |
|  | Mokwete | 11 |
|  | Matsoke | 19 |
|  | Mantshong-Ratau | 12 |
|  | Sehlatsi | 13 |
|  | Hoepakrans Maceleni | 15 |
|  | Bothaspruit-Mahlotlane | 26 |
|  | Mashwanyaneng | 29 |
|  | Masanteng | 30 |
| 2019-2020 | Cemetery | Ward no |
|  | Platklip | 02 |
|  | Eenzaam trust | 06 |
|  | Ntoane | 07 |
|  | Jane Furse RDP | 18 |
|  | Matsoke | 19 |
|  | Mogorwane Mmotwaneng | 10 |
|  | Maphopha | 12 |
|  | Madibaneng | 22 |
|  | Rantoneng | 24 |
|  | Maololo | 25 |
|  | Kgaruthuthu | 26 |
| 2020/2021 | Cemetery | Ward no |
|  | Mashishing | 02 |
|  | Masioneng | 03 |
|  | Rietfontein | 04 |
|  | Vierfontein |  |
|  | Matlakatle B | 05 |
|  | Ga Maaboki | 06 |
|  | Ga Kgoloko |  |
|  | Phatantswane |  |
|  | Mabalane |  |
|  | Dikatone x2 | 07 |
|  | Setebong |  |
|  | Manthlanyane |  |
|  | Manotong |  |
|  | Matikiring | 08 |
|  | Vergelegen A Ga Mosehla | 11 |
|  | Mangoakwana Mmerika | 12 |
|  | Moretsele New Stand |  |
|  | Hoepakrans Mabalane | 15 |
|  | Modiketsi |  |
|  | Molapong |  |
|  | Mabothunya |  |
|  | Mokadi |  |
|  | Magolego |  |
|  | Semonoko |  |
|  | Madishane |  |
|  | Seopela | 16 |
|  | Mashegoana Legare |  |
|  | Manganeng | 17 |
|  | Kgolobela |  |
|  | Kgolane |  |
|  | Mathibeng |  |
|  | Mototolwaneng |  |
|  | Mashite Thobaneng |  |
|  | Moraba New stand | 18 |
|  | Madibong Ga Seboane | 19 |
|  | Madibong Madiseng |  |
|  | Mashupye | 23 |
|  | Next to centre | 20 |
|  | Manyeleti-Rantho |  |
|  | Malegale | 22 |
|  | Matolokwaneng |  |
|  | Maila Segolo | 23 |
|  | Mohlakaneng | 24 |
|  | Masehlaneng |  |
|  | Mampe | 25 |
|  | Mohlapatswane |  |
|  | Rama |  |
|  | Kgapamadi |  |
|  | Mapulaneng |  |
|  | Makgwane |  |
|  | Kgari |  |
|  | Machacha |  |
|  | Selepe |  |
|  | Lewalemolomo | 27 |
|  | Dithabeng | 28 |
|  | Sehlabi |  |
|  | Magolopong |  |
|  | Majakaneng |  |
|  | Ramushu |  |
|  | Kgoaripe |  |
|  | Monwaneng |  |
|  | Lekurung |  |
|  | Maphutha |  |
|  | Malope | 29 |
|  | Mahloloaneng |  |
|  | Pitjaneng |  |
|  | Masemola | 30 |
|  | Mokomane |  |
|  | Leswaneng |  |
|  | Setlaboswane x2 |  |
|  | Sehli-Semahlakole | 31 |
|  | Vlaka |  |
|  | Kome |  |
|  | Ntshong |  |
|  | Motselope |  |
|  | Mangwanyane |  |

List of fenced community cemeteries for the past five years

| Ward no | Village | Financial year | Status |
| --- | --- | --- | --- |
| 01 | Kutupu | 2014/15 | Completed |
| 02 | Phokoane Toishi | 2014/15 | Completed |
|  | Dihlwadieme | 2016/17 | Under construction |
| 03 | Phokoane Makoshala | 2014/15 | Completed |
|  | Phokoane Malegale | 2013/14 | Completed |
| 04 | Rietfontein | 2013/14 | Completed |
| 05 | Maserumule Park | 2014/15 | Completed |
| 06 | Phatantswane | 2013/14 | Completed |
| 07 | Ga-Malaka | 2013/14 | Completed |
|  | Thoto | 2015/16 | Completed |
| 08 | Hlahlane | 2013/14 | Completed |
|  | Mochadi | 2015/16 | completed |
| 09 | Riverside | 2015/16 | completed |
| 10 | Ngwanamatlang | 2014/15 | Completed |
| 11 | Molepane | 2013/14 | Completed |
| 12 | Moretsele | 2012/13 | Completed |
|  | Makgeru | 2015/16 | Completed |
| 13 | Ga-Mogashoa Ditlhakaneng | 2012/13 | Completed |
| 14 | Stocking | 2014/15 | Completed |
|  | Ga-Tshesane | 2013/14 | Completed |
| 15 | Maila Mapitsane | 2013/14 | Completed |
|  | Maila Mapitsane Ga Mashilo | 2015/16 | Completed |
| 16 | Kotsiri | 2014/15 | Completed |
|  | Mashegoana Tswaledi | 2015/16 | Completed |
| 17 | Mashite | 2014/15 | Completed |
|  | Dihlabaneng | 2015/16 | Completed |
| 18 | Moraba | 2014/15 | Completed |
|  | Dichoueng | 2015/16 | Dichoeung is cemetery replaced by Vergelegen A which is complete |
| 19 | Madibong | 2014/115 | Phase 2 complete |
| 20 | Magolaneng | 2014/15 | Completed |
| 21 | Mamone Phase 1&2 | 2013/14 & 2014/15 | Completed |
|  | Mamone Ga Mohlala | 2015/16 | Completed |
| 22 | Tjatane | 2014/15 | Completed |
| 23 | Dinotsi | 2014/15 | Completed |
|  | Mathibeng | 2015/16 | Completed |
|  | Maseleseleng | 2015/16 | Completed |
|  | Maila segolo | 2016/17 | Completed |
| 24 | Diphagane | 2014/15 | Completed |
|  | Ga-Phaahla | 2014/15 | Completed |
| 25 | Mashabela | 2014/15 | Completed |
| 26 | Mampana Thabeng | 2015/16 | Completed |
| 27 | Mokalapeng | 2015/16 | completed |
| 28 | Ga- Masemola Tswaing | 2013/14 | Completed |
| 29 | Ga-Masemola Majakaneng | 2013/14 | Completed |
| 30 | Kolokotela | 2014/15 | Completed |
| 31 | Makhutso | 2015/16 | Completed |

Source: MLM Environmental Division, 2017

3.3.15 Sports, arts and culture

Sports, Arts & Culture norms and standards

1 Sport and Recreation facility per ward

1 arts and culture centre per municipality

Source: Sports, Arts and Culture Department, 2017

State of Recreational facilities within Makhuduthamaga

| Ward | Village Name | Sports centre |  | Play /football field |  | Other recreational facilities |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Yes | No | Yes | None |  |
| 1 | Kutupu |  | None | Yes |  | None |
|  | Hlalanikahle |  | None | Yes |  | None |
|  | Ga Tshehla |  | None |  | None | None |
| 2 | Phokoane |  | None | 06 |  | Community hall |
|  | Mabintane |  | None | 03 |  | None |
|  | Mogudi |  | None | 02 |  | None |
| 3 | Phokoane | Yes (Stadium) |  |  |  | Phokoane Community Hall |
| 4 | Vierfontein |  | None | Yes |  | None |
|  | Rietfontein |  | None | Yes |  |  |
| 5 | Maserumule Park |  | None | Yes |  | None |
|  | Leeukraal |  | None | Yes |  | None |
|  | Mohlarekoma |  | None | Yes |  | None |
|  | Matlakatle A&B |  | None | Yes |  | None |
| 6 | Mare |  | None | Yes |  | None |
|  | Patantshwane A |  | None | Yes |  | None |
|  | Patantshwane B |  | None | Yes |  | None |
|  | Eensaam Trust |  | None | Yes |  | None |
|  | Eensaam Stam |  | None | Yes |  | None |
|  | Ga Maboki |  | None | Yes |  | None |
| 7 | Thoto |  | None | Yes |  | None |
|  | Malaka |  | None | Yes |  | Malaka Community Centre |
|  | Setebong |  | None | Yes |  | None |
|  | Mantlhanyane |  | None | Yes |  | None |
|  | Dikatone |  | None | Yes |  | None |
|  | Manotong |  | None | Yes |  | None |
|  | Ntoane |  | None | Yes |  | None |
| 8 | Brooklyn |  | None | Yes |  | None |
|  | Mochadi |  | None | Yes |  | None |
|  | Mathousands |  | None | Yes |  | None |
|  | Hlahlane |  | None |  | None | None |
|  | Pelepele Park |  | None | Yes |  | None |
|  | Cabrieve |  | None | Yes |  | None |
| 9 | Riverside |  | None |  | None | None |
|  | Morgenson |  | None |  | None | None |
| 10 | Ga Moloi |  | None | Yes |  | None |
|  | Phushulang |  | None | Yes |  | None |
|  | Moripane |  | None | Yes |  | None |
|  | Mogorwane |  | None | Yes |  | None |
|  | Ngwanamatlang |  | None | Yes |  | None |
| 11 | Mokwete |  | None | Yes |  | None |
|  | Molepane |  | None | Yes |  | None |
|  | Vergelegen A | Yes |  | Yes |  | None |
|  | Mosehla |  | None |  | None | None |
| 12 | Makgane |  | None | Yes |  | None |
|  | Moretsele |  | None | Yes |  | None |
| 13 | Phase four |  | None | Yes |  | None |
|  | Manamane |  | None | Yes |  | None |
|  | Mabonyane |  | None |  | None | Maredi hall |
|  | Mashengwaneng |  | None | Yes |  | None |
|  | Dithlakaneng |  | None | Yes |  | None |
| 14 | Maloma |  | None | Yes |  | None |
|  | Dingoane |  | None | Yes |  | None |
|  | Moela |  | None | Yes |  | None |
|  | Mabule |  | None | Yes |  | None |
|  | Sekele |  | None | Yes |  | None |
|  | Dlamini |  | None | Yes |  | None |
| 15 | Maila Mapitsane |  | None | Yes |  | None |
|  | Modiketsi |  | None | Yes |  | None |
|  | Mokadi |  | None | Yes |  | None |
|  | Tswele |  | None | Yes |  | None |
|  | Mohlakaneng |  | None | Yes |  | None |
|  | Molapong |  | None | Yes |  | None |
|  | Malaeneng |  | None | Yes |  | None |
|  | Magolego |  | None | Yes |  | None |
|  | Location |  | None | Yes |  | None |
|  | Hoeperkrans |  | None | Yes |  | None |
| 16 | Seopela |  | None | Yes |  | None |
|  | Mashegoana Tswaledi |  | None | Yes |  | None |
|  | Mashegoana Legare |  | None | Yes |  | None |
|  | Kotsiri | Yes |  | Yes |  | Peter Nchabeleng |
| 17 | Manganeng |  | None | Yes |  | None |
|  | Mashite |  |  | Yes |  | None |
|  | Mashite |  | None |  | None | None |
| 18 | Dichoeung |  | None | Yes |  | None |
|  | Moraba |  | None | Yes |  | None |
|  | Vergelegen B |  | None | Yes |  | None |
|  | Jane Furse RDP |  | None | Yes |  | None |
| 19 | Madibong |  | None | Yes |  | None |
|  | Matsoke |  | None | Yes |  | None |
|  | Maseleseleng |  | None | Yes |  | None |
|  | Mashupye |  | None | Yes |  | None |
| 20 | Rantho and Magolaneng |  | None | Yes |  | Proposal for Multipurpose centre presented to MLM |
|  | Manyeleti |  | None | Yes |  | None |
|  | Lobethal |  | None | Yes |  | None |
|  | Tisane |  | None | Yes |  | None |
|  | Mamone Centre |  | None | Yes |  | None |
|  | Mamoshalela |  | None | Yes |  | None |
| 21 | Mamone |  | None | Yes |  | None |
|  | Mashishing |  | None | Yes |  | None |
|  | Vergelegen C |  | None | Yes |  | None |
| 22 | Tjatane |  | None | Yes |  | None |
|  | Lekgwareng |  | None | Yes |  | None |
|  | Mmotong |  | None | Yes |  | None |
|  | Sebitje |  | None | Yes |  | None |
|  | Matolokwaneng |  | None | Yes |  | None |
|  | Madibaneng |  | None | Yes |  | None |
| 23 | Mathibeng |  | None | Yes |  | None |
|  | Dinotsi |  | None | Yes |  | None |
|  | Maila Segolo |  | None | Yes |  | None |
|  | Marulaneng |  | None | Yes |  | None |
| 24 | Diphagane |  | None | Yes |  | Hall, Resource centre |
|  | Masehlaneng |  | None | Yes |  | None |
|  | Phaahla |  | None | Yes |  | 2 halls, Library and NGO |
|  | Mamatjekele |  | None | Yes |  | None |
| 25 | Machacha |  | None | Yes |  |  |
|  | Selepe |  | None |  | None |  |
|  | Maololo |  | None |  | None |  |
|  | Mohwelere |  | None | Yes |  |  |
|  | Mashabela |  | None | Yes |  |  |
| 26 | Bothaspruit |  | None | Yes |  | None |
|  | Thabeng |  | None | Yes |  | None |
|  | Mathapisa |  | None | Yes |  | None |
|  | Marishane |  | None | Yes |  | None |
|  | Kgaruthuthu |  | None | Yes |  | None |
|  | Porome |  | None |  | None | None |
| 27 | Maripana |  | None |  | None | None |
|  | Thibane |  | None |  | None | None |
|  | Moshate |  | None | Yes |  | None |
|  | Manare |  | None | Yes |  | Hall |
|  | Mabopane |  | None | Yes |  | None |
|  | Moraleng |  | None | Yes |  | None |
| 28 | Tswaing |  | None | Yes |  | None |
|  | Wonderboom |  | None | Yes |  | None |
|  | Thabampshe |  | None | Yes |  | None |
|  | Vlakplaas |  | None | Yes |  | None |
|  | Mahubitswane |  | None | Yes |  | None |
|  | Maroge |  | None | Yes |  | None |
| 29 | Mphane |  | None | Yes |  | None |
|  | Makgwabe |  | None | Yes |  | Hall |
|  | Apel Cross | Yes | None | Yes |  | Masemola sports ground |
|  | Malope |  | None | Yes |  | None |
|  | Mashonyaneng |  | None | Yes |  | None |
|  | Maraganeng |  | None |  | None | None |
|  | Pitjaneng |  | None | Yes |  | None |
| 30 | Masanteng |  | None | Yes |  | None |
|  | Kolokotela |  | None | Yes |  | None |
|  | Serageng |  | None | Yes |  | None |
|  | Mogaladi |  | None | Yes |  | Community hall |
|  | Legotong |  | None |  | None | None |
|  | Setlaboswane |  | None | Yes |  | None |
| 31 | Ntshong |  | None | Yes |  | None |
|  | Mangwanyane |  | None | Yes |  | None |
|  | Sehuswane |  | None | Yes |  | None |
|  | Semahlakole |  | None | Yes |  | None |
|  | Masakeng |  | None | Yes |  | None |
|  | Motseleope |  | None | Yes |  | None |
|  | Kome |  | None | Yes |  | None |
|  | Motoaneng |  | None | Yes |  | None |
|  | Vlaka |  | None | Yes |  | None |
|  | Makhutso |  | None | Yes |  | None |
|  | Eenkantaan |  | None | Yes |  | None |

Source: MLM 2015

The rural nature of the municipality suggests that even sports facilities will be in short supply. There are very few sporting and recreational facilities most of which are sub-standard. The community is forced to share some of the facilities with schools. The main sporting codes are football, netball and cricket. Such codes are also played under non competitive circumstances due to lack of funding and the quality of the fields. There are four Sports Centres: Peter Nchabeleng, Phokoane, Mampuru Artificial Turf and Masemola. The artificial turf was constructed in Jane Furse with the help of SAFA and National Lottery as part of the 2010 Soccer World Cup legacy programme. SAFA further sponsored the second phase of Artificial Turf construction that included building of change rooms, toilets and bathrooms and drilling of water. Maintenance and repairs were done in Peter Nchabeleng and the other facilities (Marishane, Phokoane and Glen Cowie) will be taken care of in the coming financial years when funds permit. There is a need to construct few standard sports fields in the municipality. The provincial Department of Sport, Arts and Culture was contacted in this regard the following areas were identified for sports facilities upgrading in the coming three financial years which are Marulaneng,RDP Park /sports complex in Jane Furse,Mamone,Rietfontein and Masanteng. The Municipality is recently developing policy to control use of Sports Centres for their smooth management.

There has been no specific focus on Arts Crafts and Culture from a municipal perspective except a few observations of Heritage activities. With the current IDP review, the Municipality plans to introduce initiatives to respond to the citizens needs for the promotion of Arts Crafts and Culture.

| Challenges |  | Action |
| --- | --- | --- |
| Lack of sport facilities for different sporting codes | X | Coordinate and facilitate use of facilities |
| Lack of clear roles and responsibilities for Arts , Craft and Culture | X | Investigation linked to the organisational review and redesign. |

3.3.16 Religion

Religious institution within Makhuduthamaga

Overall statistical analysis indicates that there are many places of worship (535) within Makhuduthamaga. The actual number may be higher than what can be estimated due to the growing recognition and subscription to theism (belief in the existence of God).Although we did not go at lengths to evaluate the infrastructure of these institutions, it is reported that church leaders and senior priests/pastors cry out that government gives religious fraternity least attention. A predominantly theist community is often peaceful and add impetus to stability. This fraternity often plays a lead role against tendencies that signify degeneration of morality. It is therefore a blessing to have them.

3.3.17 Post Offices and telecommunications

There are seven Post offices in Makhuduthamaga municipality i.e. Jane Furse, Nebo, Masemola, Sekhukhune, Glen Cowie, Marishane, and Mamone with several villages having lobby’s offices. Post office still plays an important role in the lives of rural people on micro banking, post services, information communication and technology. When future Post Offices are provided it would be cost effective to look at a set up like the Thusong Service Centres which could be a One Stop Shop for the consumption of government services. Post Office has also embarked on a pilot project of installing house numbers in several villages within Makhuduthamaga.

Services provided by Post Office: Post services, Banking, payments of services like car registrations, TV licenses, accounts and etc.

Challenges

- Street delivery

- Households numbering

Distribution of households with a radio, television, refrigerator, computer, cell phone, landline / telephone and access to internet by municipality

| Radio |  | Television |  | Computer |  | Refrigerator |  | Landline |  | Cell phone |  | Internet |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2001 | 2011 | 2001 | 2011 | 2001 | 2011 | 2001 | 2011 | 2001 | 2011 | 2001 | 2011 | 2011 |
| 34 695 | 39 523 | 18 472 | 46 765 | 308 | 4 371 | 16 082 | 44 849 | 2 043 | 1 034 | 9 180 | 54 692 | 24 |

Source: 2011 Census

State of Communication (postal services, land lines, network towers, radio & TV reception) in Makhuduthamaga

| Ward | Description of available communication infrastructure |  |  |  |  |  |  |  |  |  | Challenges |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Postal services |  | Land lines |  | Network tower |  | Radio Reception |  | TV reception |  |  |
|  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No |  |
| 1 |  | No |  | No |  | No |  | No |  | No | Lack of services |
| 2 | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | Lack of services |
| 3 | Yes |  |  | No | Yes |  | Yes |  | Yes |  | Lack of services |
| 4 |  | No |  | No | Yes |  | Yes |  | Yes |  | Lack of services |
| 5 |  |  | Yes |  | Yes |  | Yes |  | Yes |  | Vandalising |
| 6 |  | No |  | No |  | No | Yes |  | Yes |  | Lack of services |
| 7 |  | No |  | No |  | No | Yes |  | Yes |  | Lack of services |
| 8 | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | Poor network Mochadi |
| 9 |  | No | Yes |  | Yes |  | Yes |  | Yes |  | Lack of services |
| 10 |  | No |  | No |  | No | Yes |  | Yes |  | Lack of services |
| 11 |  | No | Yes |  | Yes |  | Yes |  |  | No |  |
| 12 |  | No | Yes |  | Yes |  | Yes |  | Yes |  | Post Office 7-10 Kms |
| 13 |  | No |  | No |  | No | Yes |  |  | No | No network tower |
| 14 | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | Network problem in Leolo |
| 15 |  | No |  | No |  | No |  | No |  | No | Postal service only in Maila. No network in all villages |
| 16 |  | No | Yes |  |  | No | Yes |  | Yes |  |  |
| 17 |  | No |  | No |  | No | Yes |  | Yes |  | Postal Service only at Manganeng |
| 18 |  | No | Yes |  |  | No | Yes |  | Yes |  | No network tower |
| 19 |  | No |  | No |  | No | Yes |  | Yes |  | Network tower only in Madibong |
| 20 | Yes |  |  | No | Yes |  | Yes |  | Yes |  | Landlines needed |
| 21 |  | No |  | No | Yes |  | Yes |  | Yes |  | Landlines needed |
| 22 |  | No |  | No | Yes |  |  | No |  | No | Poor TV &Radio reception |
| 23 |  | No |  | No | Yes |  | Yes |  | Yes |  | Only postal service in Marulaneng |
| 24 |  | No |  | No |  | No | Yes |  | Yes |  | No network tower |
| 25 |  | No |  | No |  | No | Yes |  | Yes |  | No Network and reception |
| 26 |  | No |  | No | Yes |  | Yes |  | Yes |  |  |
| 27 | Yes |  |  | No |  | No | Yes |  | Yes |  | Poor network at Mohloding village |
| 28 |  | No |  | No |  | No |  | No |  | No | No network and reception |
| 29 |  | No |  | No |  | No |  | No |  | No | No network and reception |
| 30 |  | No |  | No |  | No | Yes |  | Yes |  | Poor network |
| 31 | Yes |  | Yes |  | Yes |  |  | No |  | No | Poor network |

Source: MLM 2017

3.3.18 Social Development facilities

No separate social development facilities exist. The hospitals and police stations are utilized as service points for social development related issues like counseling and victim assistance programmes

Facilities for vulnerable groups in Makhuduthamaga

Victim support centres

| Number of VEP centres existing | Number of VEP centres receiving funding | How many VEP,s centres not funded | Overall backlog for VEP centres | Fully/Conditionally Registered Centres | Planned Target for 2017/18 -2019/20 MTEF |
| --- | --- | --- | --- | --- | --- |
| 03 | 02 | 01 | 01 | 05 Fully | 01 |

Source: Department of Social Development 2019

Substance abuse service centres

| Number of Substance abuse Centres | Number of Substance abuse service Centres receiving funding | How many substance abuse service centres not funded | Overall backlog for substance abuse service centres | Fully/Conditionally Registered Centres | Planned Target for 2017/18 -2019/20 MTEF |
| --- | --- | --- | --- | --- | --- |
| 03 | 02 | 01 | 01 | 02 Fully | 01 |

Source: Department of Social Development 2019

Community Based Care and Support Service Centres for Older Persons

| Number of CBCSS Centres | Number of CBCSS centres receiving funding | How many CBCSS not funded | Overall backlog for CBCSS | Planned Target for 2017/18 -2019/20 MTEF |
| --- | --- | --- | --- | --- |
| 07 | 02 | 05 | 05 | 01 |

Source: Department of Social Development 2019

Drop in Centres

| Number of DIC centres existing | Number of DIC centres receiving funding | How many DIC centres not funded | Overall backlog for DIC centres | Fully/Conditionally Registered DIC Centres | Planned Target for 2017/18 -2019/20 MTEF |
| --- | --- | --- | --- | --- | --- |
| 09 | 05 | 04 | 04 | 2/7 | 09 |

Source: Department of Social Development 2019

Home Community Based Care

| Number of HCBC centers existing | Number of HCBC centres receiving funding | How many HCBC centres not funded | Overall backlog for HCBC centres | Fully/Conditionally Registered HCBC Centres | Planned Target for 2017/18 -2019/20 MTEF |
| --- | --- | --- | --- | --- | --- |
| 02 | 02 | 0 | 0 | NPO | 02 |

Source: Department of Social Development 2019

### 3.3.19 Community halls

The Municipality has Makgwabe, Mogaladi and Phaahla Community halls as the only places to can be used to accommodate communities during municipal meetings.But some of the halls are in poor state and as such the municipality has set aside a budget to rehabilitate the halls in the 2018/19 financial year. It also rely on traditional council’s halls and schools in various villages to accommodate communities during municipal meetings and Imbizos .In some instances even soccer fields  are used to hold big government functions because of insufficient halls within the municipal area.

3.3.20 Safety, Security and liason mandate

The Constitution Section 206 (3)

Monitor Police conduct, Oversee the effectiveness and efficiency of Police service delivery including receiving reports, promote good relations between community and the police, report to cabinet member responsible for policing matters in the province.

NDP Vision 2030

In 2030 “people living in South Africa feel safe and have no fear of crime. They are safe at home, at school, at work and they enjoy an active community life free of fear. Women can walk freely in the streets and children can play safely outside.”

MTSF /Limpopo Development Plan:

- Reduced levels of contact crime

- Domestic stability ensured; and

- Secure identity of all persons in South Africa

- An efficient and effective Criminal Justice System

- South Africa’s borders effectively defended, protected, secured and well-managed

- Secure cyber space

Makhuduthamaga Local Municipality has two Magistrate Courts located at Nebo and Schoonoord (Sekhukhune)

Police stations that services Makhuduthamaga Local Municipality Communities

| Polokwane cluster | Burgersfort cluster | Groblersdal cluster |
| --- | --- | --- |
| 1.Jane Furse Police Station | Sekhukhune Police Station | Nebo Police station |
| 2.Masemola Police station |  | Hlogotlou Police Station (wards 1,4 and 6) |

Source: Department of Safety, Security and liason, 2017

According to planning standards one police station suppose to serve 25 000 people. In Makhuduthamaga therefore there were suppose to be 11 Police Stations

Contact /Property Crime Statistics in Police Stations that service Makhuduthamaga Communities

Crime

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 07 | 08 |
| 2. Jane Furse | Polokwane | 18 | 16 |
| 3.Sekhukhune | Burgersfort | 10 | 10 |
| 4.Nebo | Groblersdal | 12 | 13 |
| 5.Hlogotlou | Groblersdal | 7 | 14 |

Sexual offences

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 13 | 20 |
| 2. Jane Furse | Polokwane | 39 | 49 |
| 3.Sekhukhune | Burgersfort | 43 | 34 |
| 4.Nebo | Groblersdal | 76 | 63 |
| 5.Hlogotlou | Groblersdal | 60 | 68 |

Assault GBH

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 68 | 60 |
| 2. Jane Furse | Polokwane | 105 | 140 |
| 3.Sekhukhune | Burgersfort | 43 | 34 |
| 4.Nebo | Groblersdal | 76 | 63 |
| 5.Hlogotlou | Groblersdal | 60 | 68 |

Common Robbery

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 08 | 23 |
| 2. Jane Furse | Polokwane | 25 | 43 |
| 3.Sekhukhune | Burgersfort | 34 | 27 |
| 4.Nebo | Groblersdal | 34 | 41 |
| 5.Hlogotlou | Groblersdal | 27 | 32 |

Burglary at Residential

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 49 | 57 |
| 2. Jane Furse | Polokwane | 118 | 106 |
| 3.Sekhukhune | Burgersfort | 70 | 84 |
| 4.Nebo | Groblersdal | 147 | 169 |
| 5.Hlogotlou | Groblersdal | 142 | 143 |

Theft of motor Vehicle

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 03 | 04 |
| 2. Jane Furse | Polokwane | 08 | 11 |
| 3.Sekhukhune | Burgersfort | 04 | 11 |
| 4.Nebo | Groblersdal | 07 | 16 |
| 5.Hlogotlou | Groblersdal | 22 | 17 |

Stock Theft

| Police station | Cluster | 2015 | 2016 |
| --- | --- | --- | --- |
| 1.Masemola | Polokwane | 30 | 39 |
| 2. Jane Furse | Polokwane | 11 | 07 |
| 3.Sekhukhune | Burgersfort | 34 | 21 |
| 4.Nebo | Groblersdal | 36 | 70 |
| 5.Hlogotlou | Groblersdal | 19 | 18 |

Source: Department of Safety, Security and liaison 2017

Hot spot police station within Makhuduthamaga municipal area

| Type of crime | Hot spot police station |
| --- | --- |
| Business robbery | Sekhukhune Police station |

Source: Department of Safety, Security and liaison 2017

Problematic schools (in terms of crime) within Makhuduthamaga municipal area

| Cluster | Police station | Name of problematic school | Crime committed |
| --- | --- | --- | --- |
| Polokwane | Jane furse | Kgoloko High School | Drugs,dangerous weapons and bullying |
| Polokwane | Jane furse | Phiri ya gae High School | Drugs,dangerous weapons and bullying |
| Polokwane | Jane furse | Tenyane High School | Drugs and bullying |
| Polokwane | Jane furse | Molepane School | Bullying and substance abuse |
| Polokwane | Masemola | Masemola High School | Substance abuse |
| Polokwane | Masemola | Phoroane Secondary school | Bullying and substance abuse |
| Groblersdal | Hlogotlou | AM Mashego Secondary School | Drugs and bullying |
| Groblersdal | Hlogotlo | Zama Zama Secondary School | Substance abuse |
| Groblersdal | Nebo | Tseke Marishane Secondary School | Drugs ,substance abuse and bullying |
| Groblersdal | Nebo | Mmatshumane High School | Drugs ,substance abuse and bullying |
| Burgersfort | Sekhukhune | Nkotwane High School | Bullying and substance abuse |
| Burgersfort | Sekhukhune | Baaphadima High School | Drugs and bullying |
| Burgersfort | Sekhukhune | Tshehlwaneng High School | Drugs and bullying |

Source: Department of Safety, Security and liaison 2017

Development challenges:

- Establishment of additional satellite police stations in some wards

- Revival and capacitating of Community Policing Forums

- Conducting crime prevention and awareness campaigns

### 3.3.21 Traffic Services

The Municipality has two Traffic Stations (Sekhukhune and Nebo) within the municipal area.The municipality has also planned to build a Grade A station in the 2018/19 financial year in the Masemola cluster. The services of the stations were fully transferred to the Municipality from the Provincial Department Transport, Security, Safety and Liaison. Upgrading and maintenance of both Nebo and Sekhukhune Traffic Stations will be effected in the 2018/19 financial year. Five Examiners were appointed through absorption for the two Stations. Programs to acquire the services of other personnel to address the shortage at both Nebo and Sekhukhune are also at an advanced stage. Sekhukhune and Nebo DLTC are fully functional.

The Municipality renders traffic services by:

- Law enforcement to decrease incidents affecting traffic safety

- Monitoring and collecting outstanding fines

- Performing an agency function for the Provincial Government by testing and licensing vehicles on an agency basis.

3.3.22 Social cohesion

The following factors affect the required social cohesion among communities and individuals in the municipality namely:

- Low per capita income levels

- High illiteracy rates

- Hunger

- Unemployment and other social ills

The inability of the municipality to deal with the above usually results in unrests and social challenges. A multi pronged approach is required to deal with the situation

BASIC SERVICES DELIVERY AND INFRASTRUCTURE DEVELOPMENT SWOT ANALYSIS

| STRENGTHS | - Good municipal infrastructures(Roads and bridges) - Effective infrastructure operation and maintenance teams(in-house and outsourced) - Adequate adherence to project implementation plan on expansion of new infrastructure, - Ability to spend MIG grant on time - Effective political support - Well established Road Traffic Management and Licensing Services - Sound relationship with sector departments (SLA) - Existing environmental, waste & disaster management divisions. - Sports, Arts & culture unit in existence. |
| --- | --- |
| WEAKNESES | - Shortage of technical personnel - Non adherence to EPWP requirements - Rely on grants - Non functional Vehicle Testing Station - Delay in filling the Posts at the VTS, DLTC’S and lack of proper Ranking Structure in Traffic Law Enforcement - No Registering Authority - Lack of Transportation Forum and Integrated Transport Plan(ITP) - No Road Demarcation either by Markings or Kerb-wall. - No Municipal Cemetery - Lack of Animals and Vehicle Pounds - No support for Child care facilities - No disposal Facility for Carcasses - inadequate office space - Lack of transfer stations & buy back centres - monitoring of service level agreements - Poor revenue enhancement. - inadequate maintenance of Sports Facilities and Parks |
| OPPORTUNITIES | - Grant Funding(MIG,EQ,EPWP and INEP) - Creating employment through EPWP. - Sustainable road infrastructure to boost economic growth - Customer’s potential for revenue purpose - job creation through EPWP environmental projects - Sustainable economic growth - Pounds will assist in revenue enhancement and Road Safety |
| THREATHS | - Insufficient funds to implement the projects - Poor maintenance of national and provincial roads - Poor operation and maintenance of water infrastructure. - Topographic location - Delay in implementation of RDP houses - Not electricity licence holder - Not Water Service Authority - Competition by other Institution in Revenue Collection - Appointment of Authorised Officers becomes a challenge because of lack of Infrastructure Number for the RA - Poor maintenance of Systems at DLTC’s by DoT - Illegal Mini Taxi-Type operation - Congestions and delays in Travelling times (Passengers and Goods) - Vandalism of municipal assets e.g. Sports facilities and fences of cemeteries - Illegal disposal of waste (e.g disposable nappies) - Environmental hazards e.g. Floods, drought, veld fires - Crime and substance abuse - Stray animals on the road - Recurring NaTIS network problem |

CHALLENGES

## Inadequate housing for the needy

## Shortage of portable water and reliable sources

## Poor operation and maintenance of water infrastructure

## Insufficient basic level sanitation services

## Electricity post connection backlog and lack of capacity from feeder lines

## Huge storm water drainage backlog

## Lack of parking space for infrastructure plants

## Turn around time for maintenance of infrastructure plants

## Insufficient storm water mechanism due to topography (existing housing pattern)

## Lack of public transport facilities

## Insufficient clinics

- Inadequate educational facilities and equipments

- Lack of support to ECDs

- Waste management (informal disposal of waste, maintenance of landfill site, cost recovering, refuse removal not covering all villages)

- Environmental problems e.g. deforestation, erosion and alien species

- Lack of environmental bylaws

- Insufficient environmental awareness

- Fencing of cemeteries

- Lack of law enforcement facilities

- Shortage of sector plans (e.g. IWMP,integrated transport plan, housing plan etc)

- Poor network (cellphones,tv and radio coverage

- Variation in employment contracts of traffic officers.

- Variation in salary scales for municipal officers and law enforcement officers.

- Failure to collect revenue through traffic fines.

- Inadequate budget to execute the departmental projects.

- Inadequate infrastructure and recreational facilities to support departmental mandate.

- Lack of experienced personnel/inappropriate organisational structure to actualise departmental plans, hence the department rely on EPWP workers and volunteers to drive its key objectives.

3.4. KPA 3: Local Economic Development (LED)

3.4.1 Economic Structure

The Makhuduthamaga municipality promotes agriculture, tourism and mining as the key growth sectors. There are a number of mining exploration exercises that are taking place within the municipality and should mining prove feasible, it will have an added impetus on the creation of much needed jobs in particular and the growth of the economy in general.

The local economy is dominated by the tertiary/services sector, which accounted for 85% of the local economic output in 2015.  The secondary and primary sectors, respectively contributed 9.9% and 5.1% to the local economic output.

The major contributor to the municipal economy is the government sector, which contributed approximately 41% to the local economy in 2015. The second largest contributor is   wholesale and retail (20%), followed by finance and business services 9% and community, transport and communication services at 8%.

Makhuduthamaga Gross Value Added stood at R4.4 billion in 2015, making municipality the third largest economy within Sekhukhune District. The dominant municipal economy in the district is Greater Tubatse with a GDP of R6.3 billion

3.4.2. Primary Sectors

The primary sector’s output has increased in nominal terms from R38 million in 1995 to R221 million in 2015.  However, the sector’s contribution to the local economy has declined from 7.3% in 1995 to 5.1% in 2015.

a) Agriculture,	Forestry and Fishing

Agriculture’s regional value output has increased from R3 million in 1995 to R18 million in 2015 – an average growth of 11% for the period.  However, the sector is a marginal contributor to the aggregate GVA, estimated at 0.4% in 2015.

Most of the land that is under cultivation in Makhuduthamaga is used for subsistence purposes with only a small portion of the land under commercial farming. The scarcity of water may be the reason why agriculture is not a larger contributor to the GVA of the area. Moreover the status of land ownership and the fact that a significant amount of the land in Makhuduthamaga is under land claims hampers the development of the agriculture sector. Assessing the agriculture potential in the area could help unlock some of the factors that inhibit the full usage of land.

b) Mining and Quarrying

Unlike Tubatse / Fetakgomo Municipality, Makhuduthamaga has a low level of mining activities.  This is also depicted in the regional value add of the sector to the local economy. The mining sector has registered a growth rate of 14% since 1995, however, its regional economic value add has declined from 0.6% in 1995 to 0.4% in 2015.

3.4.3. Secondary Sectors

The secondary sector of the MLM economy includes Manufacturing, Construction and Electricity, Gas and Water Supply.   The output of the secondary sector has grown from R51 million in 1995 to R431 million in 2015 – an average of 12%.

a) Manufacturing

Makhuduthamaga does not have a strong manufacturing base.  The contribution of the Manufacturing sector to Secondary sector GVA was estimated at R15 million in 1995 and this increased to R69 million in 2015 – an average increase of 9% over the period.

Manufacturing contribution to the local output is very marginal across many areas with the exception of Jane Furse and surrounding areas

The most common manufacturing activities include the making of sand bricks, windows, door and steel frames. These activities respond to local demand from infrastructure development relating to housing projects, road rehabilitation, and agriculture and to a lesser extent, mining activities.

There is potential for growth in manufacturing if effective links can be made to exploit opportunities resulting from the wholesale and trade sector and public sector infrastructure spending.

b) Electricity and Water

The sector contribution to the local economy increased from R20 million (3.8%) in 1995 to R206 million (4.7%) in 2015 – an average decrease of 13% over the period.

The largest GVA contribution of electricity services is concentrated in Jane Furse and the southern part of the municipal area

c) Construction

The contribution of the Construction sector to MLM GVA increased from R16 million in 1995 to R156 million in 2015 – an average increase of 13% for the period.

This sector is linked to development within all the other sectors of the economy such as demand for construction of public sector infrastructure such as housing, roads, and the provision of basic services. Most of the work is currently sourced from outside of Makhuduthamaga, which poses the challenge for locals to become competitive enough or partner with already competitive contractors to share in this growth.

3.4.4. Tertiary Sectors

The tertiary sector’s contribution to the total economy has increased from R433 million in 1995 to R3.7 billion in 2015 – an average annual increase of 11%.

a) Wholesale and Retail

The Wholesale and Retail sector is one of the dominant economic contributors (20%) in the municipality.  The sector contributed R96 million to MLM economy in 1995 and this increased to R867 million in 2015. This means the sector grew on average by a rate of 13% per annum from 1995 to 2015. The sector responds predominantly to local markets. Growth in this sector could be explained by increased local spending power as a result of growth in the public sector.

The growth point in the Municipality, Jane Furse is a key retail centre and where repair services are provided.  It is evident, as well, that residents from these neighbourhoods do a substantial part of their shopping in the area.  While formal trade is mostly restricted to Jane Furse, informal trade takes place throughout the rural parts of the municipality, including the numerous villages.

b) Transport and Communication

The transport and communication sector is becoming more and more important each day, especially as a result of the increase in activities in other sectors. The sector contribution to local GVA was R49 million in 1995.  This figure increased by an estimated 9% to R337 million in 2015.

The anticipated increase in public sector infrastructure development also requires movement of vast amounts of material and people and thereby offers tremendous opportunity for passenger transport and material. Jane Furse is the centre of logistics and communications

c) Finance and Business Services

Finance, Real Estate and Business Services contribution to GVA increased from R47 million in 1995 to R393 million in 2015 – an average increase of 12% over the period.

The financial and business services sector is an equally important economic sector, especially in terms of its enabling qualities in support of other sectors. The majority of these services are concentrated within the economic node of Jane Furse

d) Community,	Social	and Personal Services

Personal, Social and Personal Services contribution to local GVA was R45 million in 1995.  The contribution increased to R343 million in 2015 - recording an average increase of 11% over the period under review.

e) General Government Services

Government services sector is the biggest contributor to the local GVA.  As the Municipality grew over time so has been the need for additional government services. Accordingly, the sector’s contribution to local GVA increased from R196 million in 1995 to R1.8 billion in 2015.The government sector employs 24% of the total population of Makhuduthamaga and provides public services and invests in development work. Besides the employment created, income generated and spent in Sekhukhune, the public sector also has a key role to play in the economy in the way decisions are taken.

Jobs created during 2017/18 by LED Initiatives (Excluding EPWP Projects)

| Total Jobs created / Top 3 initiatives | Jobs created | Jobs lost / displaced by other initiatives | Net total jobs created in year | Method of validating jobs created/lost |
| --- | --- | --- | --- | --- |
| Total (all initiatives) | 70 |  |  | Cooperatives |
| Initiative A (12/13) |  |  |  |  |
| Initiative B (12/13) |  |  |  |  |
| Initiative C (12/13) |  |  |  |  |
| Job creation through EPWP projects |  |  |  |  |
| Year | EPWP Implemented Projects | Jobs created through EPWP projects |  |  |
|  | No. | No. |  |  |
| 2015/16 | 12 | 159 |  | Register of projects |
| 2016/17 | 8 | 242 |  | Register of projects |
| 2017/18 | 11 | 274 |  | Register of projects |

Source: Global Insight 2015

Source: Global Insight 2015

3.4.5. Agriculture

Programmes offered by LDARD

- Letsema = Production inputs  e.g. seedlings, seeds, fertilisers and chemicals

- Fetsa Tlala = Mechanization support for food production mainly maize, sorghum, beans including dry land farming/households

- CASP = Comprehensive Agricultural Support Program (CASP): CASP is a conditional grant that the province receives annually from Department of Agriculture, Forestry and Fisheries (DAFF). The irrigation schemes around Olifants River were revitalised through RESIS program funded through CASP.The names of the schemes in Makhuduthamaga are: Mogalatjane (131 ha ),Krokodilheuwel (243 ha) and Setlaboswane (119 ha)

- RESIS = Rehabilitation  of irrigation schemes

- Technical support on both crop and animal production, including agribusiness advice as well as vaccination of livestock.

Fetsa Tlala initiatives (Integrated Food Security Program)

This is a new program that LDA introduced in 2012 and it involves provision of mechanisation support coupled with production inputs to both dry-land and irrigation projects, though the main focus is communities farming on dry land - farmers producing maize, sorghum and dry beans. There is an agreement with FAO to sell maize to Lesotho and other identified countries consuming these grains. This is an incentive to encourage small scale farmers to produce more food for their families and sell some to other countries. The initiative also benefits local business because private tractors are hired to complement the departmental tractors and they are paid by LDA through Independent Development Trust (IDT).

Source: Global Insight 2015

Source: Global Insight 2015

Source: Global Insight 2015

3.4.6. Employment profile for Makhuduthamaga

| Employed | 19534 |
| --- | --- |
| Unemployed | 32780 |
| Discouraged work seeker | 13657 |
| Other not economically active | 81993 |
| Not applicable | 126 394 |
| Grand Total | 274 358 |

Source: Census 2011

MLM Population aged between 15 and 64 years by employment status – 1996, 2001 and 2011

| Employed |  |  | Unemployed |  |  | Unemployment rate |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 |
| 12 409 | 10 686 | 19 254 | 29 370 | 32 174 | 32 662 | 70,3 | 75,1 | 62,9 |

Source: Census 2011

Source: Global Insight 2015

Jobs created by MLM during 2017/18 financial year through municipal programs

| Men | Women | Youth | People with Disabilities | Total |
| --- | --- | --- | --- | --- |
| 110 (40, 2%) | 164 (59, 8%) | 133(48, 5%) | 04 (1, 5%) | 274 |

Source: MLM 2017

3.4.7 Future growth and Job Creation

Local economic development projects

The municipality promotes agriculture; tourism and services as the key growth sectors. There is a number of mining exploration exercises that are taking place within the municipality. If mining does indeed prove feasible it will have an added impetus on the creation of much needed jobs in particular and growth of the economy in general. The decision to locate the District offices in Jane Furse will provide substantial growth impetus. Furthermore, the agricultural and tourism potential of the municipality have yet to be exploited fully. At the moment limited forms of agricultural and tourism activities are taking place.

The municipality has implemented a number of temporary job creation initiatives through the implementation of the Expanded Public Works Programme (115), The Community Works Programme (1350) and the Comprehensive Rural Development Programme in the 2017/18 financial year.

Priority sectors of the municipality

| Agriculture and agro processing | Mining | Construction | Tourism | Other Sectors | Public sector |
| --- | --- | --- | --- | --- | --- |
| X | X (concrete) | X | X | X (retail) | X |

Source: MLM 2015

Constraints to economic growth of Makhuduthamaga

| Land | Roads | Skills | Other |
| --- | --- | --- | --- |
| Access to land delay in proclamation of Jane Furse as township. Fragmented release of land which leads to distorted planning | Road to Manche Masemola tourism site, various access roads to heritage and to link municipal sub growth points and nodes of neighboring municipalities | Town planning,finanance and engineers | Funding for feasibility studies |

Source: MLM 2017

### Occupation structure

The overall occupation structure of the employed population of MLM is represented in table below. Notably, there is a relatively small proportion of people employed in the professional occupations.

The spatial distribution of the occupation sector throughout the municipality which is dominated by the elementary occupations closely corresponds with the dominance of the agricultural sector.

3.4.8. MLM Occupation levels

| Occupation | Male | Male (%) | Female | Female (%) | Total | Total (%) |
| --- | --- | --- | --- | --- | --- | --- |
| Legislators and senior officials | 30 | 0.06 | - | 0.00 | 30 | 0.02 |
| Corporate managers | 97 | 0.18 | 15 | 0.02 | 112 | 0.08 |
| General managers | 165 | 0.31 | 66 | 0.08 | 231 | 0.17 |
| Physical, mathematical and engineering science professionals | 33 | 0.06 | 3 | 0.00 | 36 | 0.03 |
| Life science and health professionals | 48 | 0.09 | 83 | 0.10 | 131 | 0.10 |
| Teaching professionals | 355 | 0.66 | 339 | 0.41 | 693 | 0.51 |
| Other professionals | 99 | 0.18 | 39 | 0.05 | 138 | 0.10 |
| Natural and engineering science associate professionals | 33 | 0.06 | 12 | 0.01 | 45 | 0.03 |
| Life science and health associate professionals | 100 | 0.19 | 375 | 0.46 | 475 | 0.35 |
| Teaching associate professionals | 889 | 1.65 | 1248 | 1.52 | 2137 | 1.57 |
| Other associate professionals | 96 | 0.18 | 18 | 0.02 | 114 | 0.08 |
| Office clerks | 276 | 0.51 | 266 | 0.32 | 542 | 0.40 |
| Customer service clerks | 94 | 0.17 | 277 | 0.34 | 371 | 0.27 |
| Personal and protective services workers | 446 | 0.83 | 233 | 0.28 | 679 | 0.50 |
| Models, salespersons and demonstrators | 226 | 0.42 | 153 | 0.19 | 379 | 0.28 |
| Market-oriented skilled agricultural and fishery workers | 81 | 0.15 | 51 | 0.06 | 132 | 0.10 |
| Subsistence agricultural and fishery workers | 3 | 0.01 | - | 0.00 | 3 | 0.00 |
| Extraction and building trades workers | 532 | 0.99 | 84 | 0.10 | 616 | 0.45 |
| Metal; machinery and related trades workers | 238 | 0.44 | 21 | 0.03 | 259 | 0.19 |
| Handicraft, printing and related trades workers | 27 | 0.05 | - | 0.00 | 27 | 0.02 |
| Other craft and related trades workers | 84 | 0.16 | 60 | 0.07 | 145 | 0.11 |
| Stationary-plant and related operators | 45 | 0.08 | 9 | 0.01 | 54 | 0.04 |
| Machine operators and assemblers | 54 | 0.10 | 3 | 0.00 | 57 | 0.04 |
| Drivers and mobile-plant operators | 696 | 1.29 | 45 | 0.05 | 741 | 0.54 |
| Sales and services elementary occupations | 386 | 0.72 | 1266 | 1.54 | 1652 | 1.21 |
| Agricultural; fishery and related labourers | 36 | 0.07 | 27 | 0.03 | 63 | 0.05 |
| Mining; construction; manufacturing and transport labourers | 206 | 0.38 | 82 | 0.10 | 289 | 0.21 |
| Undetermined | 328 | 0.61 | 298 | 0.36 | 626 | 0.46 |
| Not applicable (not economically active) | 48263 | 89.43 | 77239 | 93.84 | 125502 | 92.09 |

Source: Municipal Demarcation Board

### 3.4.9 Competitive and Comparative Advantage

### For Makhuduthamaga economy to grow sustainably, revenues and investment flows must increases, preferably from external markets. Economic grows flows when businesses in local sectors become more competitive in external and/ or local markets. The market responds to better goods, at lower prices by increasing sales often lead to increased investment

It is therefore necessary to determine which external markets Makhuduthamaga based firms can compete in profitably and sustainably. These markets and sectors offer the most opportunity for self sustained economic growth and, therefore become strategic priorities for the municipality. Furthermore it is important to understand the nature of competitive advantages and disadvantages in these markets and to recognize which factors are critical to success and which still constrain the relevant sector’s performance

### 3.4.10 Trade and Industry

Trading regulation

| Challenges |  | Action Plan |
| --- | --- | --- |
| The regulation and promotion of informal trading | X | Develop an economic development strategy, and informal trading policies |
| Lack of formal economic development opportunities | X | Identify land for Economic development initiatives |
| Lack of informal trading infrastructure | X | Identify informal trading areas set up frameworks for the use of public land by communities in the creation of jobs , the job market and environment |

### 3.4.11 Rural development

Rural development requires of all agencies at national, provincial and local government, State Owned Enterprises, and the private sector to contribute to the development of rural communities in their areas of competencies.  In this regard, the Makhuduthamaga Municipality is expected to coordinate the CRDP Local committee of stakeholders, ensure effective provision of basic services, leverage municipal spending to create local jobs, and facilitate Local Economic development for all including the most rural communities in its area of jurisdiction.

Effectively, rural development is an approach for economic and social development in rural areas. It is not a service based project, but an outcome that Makhuduthamaga Municipality together with other spheres of government wishes to achieve.

The Municipality is in the process of localizing the National Comprehensive Rural Development Strategy and it has also been identified as a CRDP site.

### 3.4.12. Tourism

The Municipality has developed Draft Tourism strategy and will be adopted during the 2018/19 financial year. Annually the Municipality produces Tourism brochures to market the Municipal Tourism areas and products. Tourism Exhibition Centre is planned for Jane Furse by the municipality.

The municipality intends to enhance and maximize its tourism potential as eco-tourism presents the potential to be a major employer and economic driver in Makhuduthamaga.

The municipality will enhance tourism through:

- The resuscitation of a private sector integrated Local Tourism organisation/ Association.

- Promote green initiatives

- Promote agricultural tourism

- Develop eco-tourism and promote natural assets such as Leolo Mountain, and Manche Masemola

- Showcase and promote cultural heritage

- Confirm and embed Makhuduthamaga as a hiking/ ecotourism destination

- Establish a functional Tourism Information office

Current tourism infrastructure

Tourism has been identified as one of the major growth sectors in the Makhuduthamaga Local Municipality. Of all the local municipalities of Sekhukhune, MLM is the heartland of heritage and cultural activities.

Tourism attraction sites within Makhuduthamaga municipal boundaries

| Name of site | Significance of the site |
| --- | --- |
| 1. Tisane Nature reserve | Tisane Nature reserve is a historical heritage site which holds the history of pedi culture.It has strong walls, built in the form of of kraals and they were constructed wisely by the forefathers to defend themselves against enemies. Also home of the Matjading fortress the long passage between boulders that leads to a secret cave beneath rocks. Also other caves of facsinating history that could be of intrest to tourists. |
| 2. Grave of Manche Masemola | The grave of Manche Masemola, a religious martyr who died for Christian beliefs in the 1800.Manche Masemola who belonged to the Anglican Church, was brutally murdered by her parents for refusing to abandon her holy beliefs in favour of traditional and spiritual upbring. Her statue has been erected in West Abbey Ministry in london -Great Britain. |
| 3. Eensam tourism site | The Eensam tourism site streches 190 hectrares on the reef of the Nebo plateau. It constitutes mainly of historical sites and cultural heritages. Seefane "the wind tree", view of De hoop Dam from the peak of this mountains, the fountain of luck, mephato "initiation schools" and lediba la pula, which is place where traditional healers go and perform certain rituals in order to wish for the rain. |

Source: LEDET 2017

Annual events that lure tourists to the municipality:

- MAMPURU DAY: He was a great warrior and a chief who was brutally killed during apartheid era. It is commemorated yearly during the second or third week of January at Mamone Royal Kraal.

- MANCHE MASEMOLA DAY: She was a staunch Christian who died at the age of 14 after she was killed by her parents for refusing to stop to attend the church. Her grave turned to be one of the world’s pilgrimage centres since 1935 when small groups of Christians visited the site annually to commemorate the heroine who vowed to be baptized with her own blood. Today the grave site of Manche Masemola is visited and celebrated yearly on the first week of August by hundreds of tourists, especially Anglicans from all over the World.Her statue has been erected in West Abbey Ministry in London -Great Britain.

- THETIANE HERITAGE: This gathering is held in September at Thabampshe, Ga –Masemola village. Everyone showcase traditional attire to express their passion for cultural roots. Women and girls wear Dintepa le Mabole.Men and boys fit in Makgeswa and animals skins such as baboon skins. This is one event where you will see various musical instruments such Botsoroane, diphalafala and so forth.

Accommodation facilities within MLM

| Name of Facility | Location | Conference Facility Available | Graded |
| --- | --- | --- | --- |
| - Gravel Lodge & Central Park | Glen Cowie | No | No |
| - Laduma O.A.T Lodge | Jane Furse | Yes (100) | No |
| - Tisane Motel | Ga-Tisane | Yes (300) | No |
| - Beautiful Lodge | Jane Furse | Yes (200) | No |
| - Sekhukhune Lodge | Rantho Village | Yes | No |
| - Dorothy Lodge | Brooklyn | No | No |
| - Setso Guest House | Nebo | Yes (60) | No |
| - Royal Stay Lodge | Mogorwane | Yes | No |
| - Lapa Lodge & Conference Center | Mogorwane | Yes | No |
| - Phokowane Road Lodge & Sports Bar | Phokwane | Yes (200) | No |

Source: LEDET 2017

The following are some of the tourism hot spots that needed to be developed into tourism products

- Sekhukhune Centre of Plant Endemism: underlain by the Bush veld Igneous Complex and covers areas of approximately 5,449 square km. i.e. Protea Flower and Yellow arum Lily flower

- Wetland and Protected area: Game parks and nature conservation

- Scenery of Leolo Mountains: Adventure, Scenery, Hiking and Trail.

| Challenge |  | Action |
| --- | --- | --- |
| Accommodation facilities not graded | X | Resuscitate the Local Tourism Association |
| Lack of signage |  | Install signage where needed |
| Tourism information centre | X | Establish a fully functional Tourism Information centre |

LOCAL ECONOMIC DEVELOPMENT SWOT ANALYSIS

| STRENGTHS | SMME support policy in place LED Strategy in place SMME database in place |
| --- | --- |
| W EAKNESES | Inadequate personnel Ineffective LED forum and no tourism association Weak agricultural value chain No economic sector plans No LED strategy No funding policy |
| OPPORTUNITIES | Jane Furse declared as a town(main economic node) The town is identified as an administrative hub of the district Clear spatial linkages with the surrounding areas Several economic zones (nodes) identified Potential of large scale maize and sorghum production Potential of Economic growth |
| THREATS | Global warming and climate change Mushrooming of informal businesses by foreign nationals Instability of national and international economy and markets Unregulated local maxi taxis in the CBD High level of poverty |

Challenge

## Insufficient SMME support

## Lack of access to markets

## Weak agricultural value chain

## Weak manufacturing sector

## Ineffective tourism promotion

## Climate change

- High unemployment rate

- Unused tractors

3.5. KPA 4: Financial Viability

3.5.1 Financial Status of the Municipality

The Municipality has projected a total revenue budget of R 397.9 million and total expenditure budget of R 404.9 million for 2017/18 financial year.

The Municipality has budgeted a total Revenue of R 397.9 million for 2017/18 financial year, R408.9 million and R431.1 million for 2018/19 and 2019/20 respectively. Total revenue has grown by 6.8 per cent or R 25.3 million for the 2017/18 financial year when compared to the 2016/17 Adjustments Budget.  For the two outer years, total revenue will increase by 3 per cent and 6 per cent respectively, equating to a total revenue growth of R 62.5 million over the MTREF when compared to the 2016/17 financial year. The total revenue for 2017/18 includes the grants allocations from the national treasury to the amount of R 318.7 million and own revenue sources to the amount of R 79.1 million. For the two outer years of the MTREF 2018/19 and 2019/20 total grants allocations included in total revenue amounts to R323.6 million and 343.3 million respectively while own revenue continues to grow to R 85.2 million and R91.7 million respectively.

The Municipality is expecting the own revenue total budget for the two outer years to increase during review after the approval of the reviewed revenue enhancement strategies which will introduce new sources of revenue, such as service charges for waste collection, rental of municipal halls and sports grounds. The Municipality has also included in its budget for 2016/17 a project to develop and regularly update the indigent register, which will assist the municipality in revenue generation and to ensure sustainability of service delivery and provision of basic services to deserving indigents.

Total operating expenditure for the 2017/18 financial year has been appropriated at R 230.6 million and translates into an operating budgeted surplus of R 167.2 million. This surplus is used to fund capital expenditure for 2017/18. When compared to the 2016/17 Adjustments Budget, operational expenditure has gone down by 16 per cent in the 2017/18 budget and grows by 7.6 per cent by 2019/20. The operating surplus for the two outer years decrease to R 130.9 million for 2018/19 and  R141.2 million in 2019/20 financial year.  These surpluses will be used to fund capital projects.

The capital budget of for 2017/18 financial year amounts to R 174.2 million and has increased by 21.4 per cent when compared to the 2016/17 Adjustment Budget of R 143.5 million.  The Municipality’s revenue for 2017/18 is not sufficient to fund growth in capital expenditure budget and therefore, capital infrastructure projects will be implemented using multi-year budgets to cover all areas that have service delivery backlogs.

In the total amount for capital budget in 2017/18, an amount of R 61.7 million is funded by MIG for roads and bridges; R 13 million is funded by INEG from DOE while the remaining capital expenditure will be funded by equitable share to the amount of R 99.5 million.

The capital expenditure decrease to R 138.9 million in the 2018/19 financial year and R149.1 million in 2019/20.

Billing System

Property rates billed based on the valuation roll based on market value on monthly basis which is performed by the professional valuer. Our first valuation roll was signed by the valuator on the 31 January 2007 and implemented during the 2009/10 financial year.  MLM collect rates from Businesses and Sector departments.MLM use a system called Accpac to perform all its financial transactions.

The financial sustainability of the Municipality

The Municipality has established fully functional Budget and Treasury Department in line with chapter 9 sections 80 of MFMA and the role of Budget and Treasury department. The municipality has a challenge with regard to generation of own revenue since the municipality does not offer services like water and sanitation, electricity due to limitations on powers and functions. The municipality has always maintained positive cash flow and it does not finance its operation through loans and overdrafts.

In terms of expenditure management the municipality has always maintained watertight system of internal control and at all times municipality adheres to the principle of paying creditors on time which is 30 days payment period. Municipal credit control and debt collection policy has been fully utilized to ensure that all amounts that are being owed to municipality are indeed recovered within 60 days invoice period and the ultimate intention is to recoup all the accounts receivable within 30 days period. Furthermore municipality has introduced a system of internal control as early warning mechanisms to detect unauthorised, irregular, fruitless and wasteful expenditure as well as unfunded mandates.

For the KFAs below, we have only included the current challenges and issues.

| Issue / Challenge |  | Action plan |
| --- | --- | --- |
| Optimising and sustaining Councils revenue Increasing internally generated funds for funding operational and capital expenditure | X | Implement credit control and focus more on consumers that have the ability to pay for Municipal Services/ rates |

3.5.2 Revenue Enhancement/ Management

3.5.2.1 Revenue Enhancement

| Challenge |  | Action Plan |
| --- | --- | --- |
| Sector departments not paying property rates | X | Use of Debt collector and intervention by National Treasury. |
| Residential sites not billed | X | To consider billing residence in view of initiation of waste removal programme |

3.5.3 Cost Containment/ Management

3.5.3.1 Cost Containment

| Challenge |  | Action plan |
| --- | --- | --- |
| Correct alignment of cost drivers to appropriate expenditure through Activity Based Costing model | X | Establish and comply with activity based costing component. Prepare municipal budget in line with the cost containment practice note issued by National cabinet for all government departments. |

3.5.4 Asset Management

3.5.4.1 Asset Management

| Challenge |  | Action Plan |
| --- | --- | --- |
| Movable assets removed without proper authorisations. | X | Complete transfer forms, before removing movable assets. |

3.5.5 Capital Expenditure

3.5.5.1 Capital Expenditure

| Challenges |  | Action Plan |
| --- | --- | --- |
| Late appointment of service providers for implementation of capital projects | X | Review, update, and improve the planning cycle of the procurement of capital projects and items. Budget & Treasury to prepare an annual procurement plan that will guide the processes timeously. |

3.5.6 Supply Chain Management

3.5.6.1 Supply Chain Management

| Committees | Function |
| --- | --- |
| 1.Bid specification committee | Compiling specification for the Municipality requirements to be acquired |
| 2. Bid evaluation committee | Evaluation of Bids,compilation of reports and making recommendations |
| 3.Acquisition committee (Bid adjudication) | Consideration of the recommendations and award or recommendation to the accounting officer to make final award |

| Challenges |  | Action Plan |
| --- | --- | --- |
| Late submission of requisitions | X | Development of project plan by user departments. Budget & Treasury to process only requisitions received 7 working days before the date of service/goods required. |
| Under /Over pricing |  | To research for market related prices |

3.5.7 Financial Reporting

Challenges

None

3.5.8 Budgeting/ Funding

3.5.8.1 Budgeting

| Challenges |  | Action Plan |
| --- | --- | --- |
| Dependence on grant funding by national and provincial government | X | Concentrate on debtors that can afford to pay and enforce the credit control and debt collection policies with a view of enhancing Council revenue |
| To increase tariffs and expenditure to be in line with CPI as per National Treasury | X | Introduction of financial strategies to respond to infrastructure needs. Make more contributions to the CRR with a view of cash funding the budget from access available funds |
| Inadequate funding |  | Enhanced revenue collection |

3.5.9 Grants and Subsidies

Section 214(1) of the Constitution of the Republic of South Africa, 1996 requires an Act of Parliament to provide for the equitable division of revenue raised nationally among the National, Provincial and Local Spheres of Government and any other allocation to Provinces, Local Government or Municipalities from the National Government’s share of revenue, and conditions on which those allocations may be made.

Makhuduthamaga Local Municipality receives the following grants on yearly basis as per Division of Revenue Act (DORA)

Conditional grants

| Name of grant | Amount for 2016/17 | 2017/18 | 2018/19 | 2019/20 |
| --- | --- | --- | --- | --- |
| Municipal Infrastructure Grant (MIG) | R59 210 000.00 | R63 599 000.00 | R67 230 000.00 | R71 599 950.00 |
| Financial Management Grant (FMG) | R 1 625 000.00 | R1 700 000.00 | R1 955 000.00 | R2 033 200.00 |
| Municipal Systems Improvement Grant (MSIG) | R 0.00 | R 0.00 | R 0.00 | R 0.00 |
| Integrated National Electrification | R 7 000 000.00 | R 13 000 000.00 | R12 000 000 | R 0.00 |
| Department of Public Works | R 1,505,000.00 | R 0.00 | R 0.00 | R 0.00 |

Source: MLM Budget and Treasury, 2017

Unconditional grants

| Name of grant | Amount for 2016/17 | 2017/18 | 2018/19 | 2019/20 |
| --- | --- | --- | --- | --- |
| Equitable Shares (ES) | R 225 123 000.00 | R 240 496 000.00 | R254 456 000.00 | R 269 723 360.00 |

3.5.10 existing revenue sources

| Revenue | Observation |
| --- | --- |
| Investment and tender documents | The interests earned on investment and tender documents are also revenue sources |
| Traffic functions(licenses and permit) | The devolution of the traffic function will positively impact on revenue generation like vehicle licensing, driver’s licenses and traffic fines |
| Property rates | The Municipal Property Rates Act, 2004 was promulgated with effect from 2 July 2005.Property rates would be one of the primary sources of revenue for the municipality. Factors that will determine the amount that a property owner must pay to the municipality include: the assessed value of the property, the effective assessment rate etc. |

Source: Internal Studies (MLM 2016)

The MLM’s revenue sources are both internal and external. The internal sources contribute about 18% of the total revenue of the municipality while external sources make up to 82%.The internal sources include vehicle licensing and registration, property rates (businesses) and interest earned on investment and tender documents. The external sources of revenue at the disposal of MLM are grants and social donations from private sector. Some grants are often conditional such that the municipality is not at liberty to spend otherwise despite deserving needs.

3.5.11 Makhuduthamaga Audit Findings for 2017/18 Financial year

The following are the findings of the Auditor General: AGSA Opinion: Qualified Audit Opinion with matters

| 3.5.12 Audit remedial plans for 2017/18 financial year audit findings |  |  |
| --- | --- | --- |
| Description of Finding | Root Cause | Action Plan Description |  |
| Bank Account with Mutual Bank (VBS) In terms of MFMA Sec7 (3) (c)). The Bank account(s) of the municipality should be with an institution registered as a bank in terms of the Banks Act, 1990, (MFMA Sec 7(3)(b)) Although, the municipality withdrawn funds from VBS mutual during the current accounting period, it is important to note that investment with the institutions that are not registered in terms of the Banks Act, 1990, (MFMA Sec 7(3)(b)) is prohibited. There are comprehensive risks of financial loses as this kind of institutions are not sufficiently regulated | 1. Inadequate review of investment procedures and validation of due diligence process. | 1. Management to review the Banking and investment Policy to amend necessary clauses in the policy. |  |
|  |  | 2. Municipal Manager to request approval from Council for all investments. |  |
| Consequence Management In terms of MFMA 32 (2) (a) (b), The municipality must recover unauthorised, irregular or fruitless and wasteful expenditure from the person liable for that expenditure unless the expenditure: a) In the case of unauthorised expenditure, is authorised in an adjustments budget or certified by the municipal council, after investigation by a council committee, as irrecoverable and written off by the council; and b) In the case of irregular or fruitless and wasteful expenditure, is, after investigation by a council committee, certified by the council as irrecoverable and written off by the council. The reported prior year unauthorised, irregular, fruitless and wasteful expenditure were not investigated to determine if any person was liable for the expenditure or was certified as irrecoverable by council after investigation was conducted. | Instability or vacancies in key positions, Slow response by management, Slow response by oversight | 1. Report all alleged Unauthorised, Irregular, fruitless and wasteful expenditure within 30 days of discovery. |  |
|  |  | 2. MPAC to conclude and report on investigations of any UIFW case referred to the committee by council within 3 Months of the council resolution. |  |
|  |  | 3. Municipal Manager to implement the council resolution regarding the MPAC investigation report on UIFW immediately after the resolution was approved. |  |
| The appointment of Segeru General Suppliers-Not Market related Price, In terms of MFMA section 112(1)(f) the supply chain management policy of a municipality or municipal entity must be fair, equitable, transparent, competitive and cost-effective and comply with a prescribed regulatory framework for municipal supply chain management which must cover competitive bidding processes in which only pre-qualified persons may participate; In terms of Section 6, paragraph 9 of the preferential procurement regulation: a) If the price offered by a tenderer scoring the highest points isn’t market related the organ of state may not award the contract to that tender Contrary to the above, The Municipality appointed Segeru General Suppliers as the winning tenderer for the provision of cooking products/ cooking essentials. Through comparing of the quotation submitted by the appointed tenderer and market related prices as obtained on Pricecheck.co.za, Evergreen.co.za and Macro on line we identified the following non market-related prices | Lack of maximum acceptable prices framework, policies and procedures | 1. Determine maximum acceptable price list for all operational goods and services for approval by management. |  |
|  |  | 2. Negotiate prices above the maximum acceptable list |  |
| Appointment of services provider for the supply, registration and licensing and delivery of waste compactor truck with Maintenance plan of five years or 10 000 Kms | Lack of accounting framework, policies and procedures for maximum prices for bidders. | 1. Management did not agree with this finding and the auditor's conclusion and therefore unable to come up with corrective action for a finding that was not properly concluded. A letter was send to the DBE of AGSA Limpopo business unit, to assist in concluding this finding properly and to date no response was received. |  |
| Irregular appointment of Sihle Civil and Projects. - The appointment of a service provider to provide Contract management relating to the Construction of Makgwabe to Mphane access road: Tender number MIG/LP/1980/R/15/19 | Inadequate review of the evaluation reports before approval of the bid. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular |  |
|  |  | Expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
| Irregular appointment of Thalami, Ntshiana& Maunyatlala JV - The appointment of a service provider for the construction off Rietfontein to Eensaam Access Road Phase 2: Tender number MIG/LP/1981/R/15/19 | Adequate evaluation of the supplier tender documents. Inadequate review of evaluation committee report by Adjudication committee and the Accounting Officer before approving the recommendations. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
| Irregular appointment of Kgwadi ya Madiba - The appointment of a service provider for the maintenance of Madibong Landfill site for a period of three (3) years: Tender number LIM473/MAINT-MADIBONG/17/18/04 | Inadequate review of the evaluation reports before approval of the bid. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted |  |
|  |  | with the adjudication report to MM for approval of the recommendations. |  |
| Irregular appointment of CORPMD Consulting - The appointment of a service provider to provide internal audit services for a period of three (3) years: Tender number LIM473/AUDIT/16/17/054 | Inadequate review of the evaluation reports before approval of the bid. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
|  |  | 6. Perform tax compliance validations with SARS before appointment of service providers. |  |
| Irregular appointment of Mogwape Business Enterprise - Lim473/Cleaning-Service/17/18/07: Provision of cleaning services on all municipal buildings for a period of three (3) years | Instability or vacancies in key positions | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
|  |  | 6. Perform tax compliance validations with SARS before appointment of service providers. |  |
| Irregular appointment of Popopo and Sons JV - The appointment of a service provider for the Construction of access bridge at Manganeng village: Tender number MLM/ES/16/17/03 | Inadequate review of the evaluation reports before approval of the bid. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
|  |  | 5. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
| Awards to persons in the service of the State - Regulation 44 of SCM states “The supply chain management policy of a municipality or municipal entity must, irrespective of the procurement process followed, state that the municipality or municipal entity may not make any award to a person 1. (a) Who is in the service of the state; 2. (b) If that person is not a natural person, of which any director, manager, principal shareholder or stakeholder is a person in the service of the state; or (c) Who is an advisor or consultant contracted with the municipality or municipal entity? | Management also did not review and monitor compliance with applicable legislation. | 1. Management did not agree with this finding and therefore unable to come up with corrective action for a finding that was not properly concluded. A letter was send to the DBE of AGSA Limpopo business unit, to assist in concluding this finding properly and to date no response was received. |  |
| Award Made to Suppliers in Which Partners of employees or Associates have an Interest - In terms of Municipality Systems Act 32 of 200 schedule 2: Code of conduct for municipal staff members’ sec 5(1) “A staff member of a municipality who, or whose spouse, partner, business associate or close family member, acquired or stands to acquire any direct benefit from a contract concluded with the municipality, must disclose in writing full particulars of the benefit to the council” | Management also did not review and monitor compliance with applicable legislation. | 1. Management did not agree with this finding and therefore unable to come up with corrective action for a finding that was not properly concluded. A letter was send to the DBE of AGSA Limpopo business unit, to assist in concluding this finding properly and to date no response was received. |  |
| Local Content-Declaration - In terms of preferential procurement regulation 8.5, a tender that fails to meet the minimum stipulated threshold for local production and content is an acceptable. The following suppliers did not submit their declaration on local content and should have been disqualified and not evaluated further. | Implement proper record keeping in a timely manner to ensure that complete, relevant and accurate information is accessible and available to support financial and performance reporting | 1. Adjudication committee to develop and implement compliance checklist for review of evaluation reports before recommendations are made to MM. The checklist must be submitted with the adjudication report to MM for approval of the recommendations. |  |
|  |  | 2. Scan and file SCM reports electronically. |  |
| Declaration of interest not submitted - In terms of Municipal Supply Chain Management Regulations paragraph 13(c), the municipality may not consider a written quotation or bid unless the provider who submitted the quotation or bid has indicated: 1. Whether he or she is in the service of the state, or has been in the service of the state in the previous twelve months 2. If the provider is not a natural person, whether any of its directors, managers, principal shareholders or stakeholders is in the service of the state, or has been in the service of the state in the previous twelve months, or 3. Whether a spouse, child or parent of the provider or of a director, manager, shareholder or stakeholder referred to in subparagraph (ii) is in the service of the state, or has been in the service of the state in the previous twelve months. | Management also did not review and monitor compliance with applicable legislation. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
| Irregular expenditure not disclosed. - The municipality did not disclose the irregular expenditure incurred from a contract that was awarded in the 2015/16 year to Mulalo Business Enterprise for Construction of Kolokotela internal road (MLM/ES/16/17/03). The contract was noted to be irregular during the 2016/17 audit conducted by the AGSA. The total irregular expenditure that was not disclosed with regards to this contract amounts to R 4 541 542.00. | Management also did not review and monitor compliance with applicable legislation. | 1. Report the alleged irregular expenditure to council for investigation. |  |
|  |  | 2. Council to refer the reported irregular expenditure to MPAC for investigation and recommendations. |  |
|  |  | 3. Council to consider and approve or disapprove the MPAC report recommendations. |  |
|  |  | 4. Municipal Manager to implement the council resolution on the reported irregular expenditure. |  |
| No comparison of actual performance to that of prior year - In terms of Section 46 of the Municipal Systems Act, a municipality must prepare for each financial year a performance report reflecting - a) The performance of the municipality and of each external service provider during that financial year; When testing the presentation of the Annual Performance Report for the 2017/18 financial year, it was noted that the municipality did not disclose prior year performance information in the Annual Performance Report. | Instability or vacancies in key positions | 1. Review and adjust the Annual Performance report to include prior year comparison. |  |
| Performance indicators not useful and verifiable - The Framework for Managing Programme Performance Information (FMPPI) paragraph 3.2, states that a good performance indicator should be: • Reliable: the indicator should be accurate enough for its intended use and respond to changes in the level of performance • Well-defined: the indicator needs to have a clear, unambiguous definition so that data will be collected consistently, and be easy to understand and use. • Verifiable: it must be possible to validate the processes and systems that produce the indicator. We reviewed the revised SDIBP and noted that the municipality’s performance indicators are not well defined and verifiable. The following indicators for construction of the roads, bridges, buildings, electrifications and road designs are measured in terms of the percentages. On further enquiry with management we noted that the percentage is based on the stage at which the project was at the reporting period. For example, when the contractor is appointed, the project is assumed to be between 10%-15% complete and when the site establishment is completed the project is assumed to be between 15%-20% complete. This type of measurement is misleading as at 20%, the physical construction of the road/bridge is not yet started and it is therefore inappropriate to report 20% completion of the road constructed while only site establishment was completed. | Management did not thoroughly review the SDBIP to ensure that all indicators are well defined and verifiable | 1. Review the 2018/19 SDBIP. |  |
|  |  | 2. Submit reviewed SDBIP for pre audit to AGSA |  |
| Number of Ward based LED profiles Completed - The performance measure of Number of Ward based LED profiles Completed is not will defined such that data can be collected consistently. Its related target is not specific as the nature and required level of performance cannot be clearly identifiable. The indicator relates to LED profiles completed, however management reported on the number wards visited within the demarcation of the municipality and not on the LED profile completed. | The municipality did not have adequate staff with required knowledge of performance management during the 2017/18 financial year. The position of Manager PMS was only filled later in the last quarter of the financial year. | 1. Review the 2018/19 SDBIP. |  |
|  |  | 2. Submit reviewed SDBIP for pre audit to AGSA |  |
| Number of Sports Tournament Played -The performance measure of sports tournament played is not will defined such that data can be collected consistently. Its related target is not specific as the nature and required level of performance cannot be clearly identifiable. The reported performance of this indicator included the below event which are not related to sports tournament played. | Adequate review on the SDBIP was not performed by all levels as per delegation of authority to detect and correct errors on the SDBIP | 1. Review and adjust the Annual Performance report to include correct information |  |
| Road Safety Awareness Campaigns - The performance measure of Road Safety Awareness Campaigns is not will defined such that data can be collected consistently. Its related target is not specific as the nature and required level of performance of the cannot be clearly identifiable. The reported performance of this indicator included road block operations which are not campaigns. It is not clear whether the municipality want to report on road blocks operation or campaigns. | Adequate review on the SDBIP was not performed by all levels as per delegation of authority to detect and correct errors on the SDBIP | 1. Management to review the 2018/19 APR against the SDBIP to ensure that all performance indicators are meaningful to enhance performance reporting 2. Internal audit to audit the achieved targets against the predetermined objectives to ensure consistency before submission to the AG |  |
| Disaster awareness campaign held - In terms of sec 62 (1) of MFMA, the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps (a) that the resources of the municipality are used effectively, efficiently and economically; (b) that full and proper records of the financial affairs of the municipality are kept in accordance with any prescribed norms and standards; (c) that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control | Adequate review on the SDBIP was not performed by all levels as per delegation of authority to detect and correct errors on the SDBIP | 1. Management to review the 2018/19 APR against the SDBIP to ensure that accurate information is being reported 2. Internal audit to audit the achieved targets against the predetermined objectives to ensure consistency before submission to the AG |  |
| Number of cemeteries fenced - In terms of sec 62 (1) of MFMA, the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps (d) that the resources of the municipality are used effectively, efficiently and economically; (e) that full and proper records of the financial affairs of the municipality are kept in accordance with any prescribed norms and standards; (f) that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control | Adequate review on the SDBIP was not performed by all levels as per delegation of authority to detect and correct errors on the SDBIP | 1. Management to review the 2018/19 APR against the SDBIP to ensure that accurate information is being reported 2. Internal audit to audit the achieved targets against the predetermined objectives to ensure consistency before submission to the AG |  |
| Relevance of Performance Information Indicators - The Framework for Managing Programme Performance Information (FMPPI) paragraph 3.2 (f) states that a good performance indicator should be: Relevant: the indicator must relate logically and directly to an aspect of the institution's mandate, and the realisation of strategic goals and objectives. The strategic objective of KPA 2: Basic service delivery and infrastructure is to provide infrastructure for improved quality of life. The following performance indicators do not relate logically and directly to the realisation of the strategic objective for KPA 2: Basic service delivery and infrastructure. | Inadequate review of the SDBIP and the APR for 30 June 2018. | 1. Management to review the 2018/19 APR against the SDBIP to ensure consistency between the planned and the reported performance information 2. Internal audit to audit the achieved targets against the predetermined objectives to ensure consistency before submission to the AG |  |
| General Control Deficiencies - The performance agreement referred to in subsection (1) (b) must include— a) In terms of a written employment contract with the municipality complying with the provisions of this section; and subject to a separate performance agreement concluded annually as provided for in subsection (2). i) be concluded within 60 days after a person has been appointed as the municipal manager or as a manager directly accountable to the municipal manager, failing which the appointment lapses: Provided that, upon good cause shown by such person to the satisfaction of the municipality, the appointment shall not lapse; and be concluded annually, thereafter, within one month after the beginning of each financial year of the municipality; When evaluating the operating effectiveness of the municipality's internal control, we noted the following deficiencies: 1. High rate of vacancies in key positions The municipality has the following vacant key positions • Inadequate implementation of the action plan to address internal and external audit findings • Performance Evaluation for section 57 employees was not conducted • There was no external quality assurance review conducted on internal audit function • High level review of AFS The asset register supporting Land was not included in the assets resister submitted for audit When comparing the comparative figure for employee cost with the prior year audited financial | Instability or vacancies in key positions, 1. Lack of external reviewer for identification of errors not identified by the CFO. 2. The municipality did not have funds for external review of internal audit work | 1. Appoint a committee for evaluation of all Senior Managers and Municipal Manager. 2. Evaluate all Senior Managers and Municipal Manager by end of January 2019. |  |
| Variances on Depreciation Calculation - In terms of section 63 (2)(b) of MFMA, the accounting officer must for the purposes of subsection (1) take all reasonable steps to ensure that the municipality’s assets and liabilities are valued in accordance with standards of generally recognized accounting practice. We recalculated depreciation on assets and noted the following variances: | Inadequate review | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Recording of Assets without Rights of Ownership. - terms of sec122(1)(a) of MFMA, every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” When auditing the additions of assets, we noted that the municipality have recorded the following assets in to their financial statements of which they don’t have right of ownership attached to them | Inadequate review | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Credit Control Policy and Procedure Manual - In terms of GRAP 104, paragraph 58, A financial asset or a group of financial assets is impaired and impairment losses are incurred if, and only if, there is objective evidence of impairment as a result of one or more events that occurred after the initial recognition of the asset (a ‘loss event’) and that loss event (or events) has an impact on the estimated future cash flows of the financial asset or group of financial assets that can be reliably estimated. Objective evidence that a financial asset or group of assets is impaired includes observable data that comes to the attention of the holder of the asset about the following loss events: We reviewed the municipality’s credit control policy and procedure manual and noted that they are not consistent with the requirement of GRAP 104 for provision of impairment of debtors. For example, in the below guidance used by management, row 5: debt ageing less than 90 days whom are currently paying their invoice are provided 100% allowance for provision of impairment of debtors. | Inadequate review | Management to review the Credit Control Policies to strengthen the loop holes in the policy also addressing processes and procedures with regard to GRAP 104 |  |
| Cash and cash equivalent: Disclosure of Bank accounts - In terms of section 125 (2)(a) of MFMA, the notes to the annual financial statements of a municipality or municipal entity must disclose the following information in respect of each bank account held by the municipality or entity during the relevant financial year (i) The name of the bank where the account is or was held, and the type of account; and (ii)Year opening and year end balances in each of these bank accounts The following bank accounts opened during the year were not disclosed on the annual financial statement. | Inadequate review | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Information Not Submitted for Audit. - In terms of section 74 (1) of MFMA, the accounting officer of the municipality must submit to the National Treasury, the Provincial Treasury, the Department for Local Government in the province or the Auditor-General such information, returns, documents, explanations and motivations as may be prescribed or as may be required. In terms of the audit engagement letter for the 2017/18 audit cycle, paragraph 46, bullet point number 5 - “All documentation and information in support of the financial statements, the annual performance report and compliance with legislation must be available on request and be retrievable within a reasonable time, which should not exceed three working days.” | Implement proper record keeping in a timely manner to ensure that complete, relevant and accurate information is accessible and available to support financial and performance reporting | To ensure that Management complete and accurate audit file is prepared before the commencement of the audit. |  |
| Limitation of Scope - In terms of section 74 (1) of MFMA, the accounting officer of the municipality must submit to the National Treasury, the Provincial Treasury, the Department for Local Government in the province or the Auditor-General such information, returns, documents, explanations and motivations as may be prescribed or as may be required. -We requested payments vouchers and bidding file for local content on request number 35 and 40, however they were not submitted for audit purpose | Implement proper record keeping in a timely manner to ensure that complete, relevant and accurate information is accessible and available to support financial and performance reporting | To ensure that Management complete and accurate audit file is prepared before the commencement of the audit. |  |
| Expenditure: Payment of the suppliers within 30 days - In terms of sec 65(2)(e) of the MFMA, the accounting officer must for the purpose of subsection (1) take all reasonable steps to ensure that all money owing by the municipality be paid within 30 days of receiving the relevant invoice or statement, unless prescribed otherwise for certain categories of expenditure. | § Inadequate review | 1. Management to ensure that it comply with Section65(2)(e) of the MFMA |  |
| Disclosure of Accounting Policies. - In terms of sec122(1)(a) of MFMA, every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” The accounting policies for cash and cash equivalent was not disclosed on the annual financial statements. | A weakness in the internal control system used to verify completeness of the accounting policies in the financial statements. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Prior period error note - In terms of section 74 (1) of MFMA, the accounting officer of the municipality must submit to the National Treasury, the Provincial Treasury, the Department for Local Government in the province or the Auditor-General such information, returns, documents, explanations and motivations as may be prescribed or as may be required. | A weakness in the internal control system used to verify completeness of the accounting policies in the financial statements. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Journals - In terms of sec122 (1)(a) of MFMA, every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” We reviewed the municipality’s general ledger and noted non routine entries that appeared to be journals, however upon our enquiries with management, we were informed that journals were not processed for this entries. When corrections of errors, reversals of transactions, transfer of an amount to another account occurs it has to be done through journals which are supported by documents and approved by the relevant senior officer. Contrary to that, the auditors are not provided with any journals for such transactions even though numerous requests were made. | Review and monitor compliance with applicable legislation | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Irregularities identified on fleet management - Section 62 (1) (b) of the Municipal Finance Management Act states that “The Accounting Officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps to ensure that full and proper records of the financial affairs of the municipality are kept in accordance with any prescribed norms and standards.” The following example of fuel consumption and odometer readings from the ABSA transaction reports which leads to the irregular transactions which costed municipality significant amount of money. The findings from the ABSA reports leads to the following: • Petrol filled exceeded the fuel tank capacity of the vehicles- possibility of filling personal cars using the fleet card • Petrol filled to a bakkie/car and kilo meter travelled does not correlate- possibility of filling private cars | Prepare regular, accurate and complete financial and performance reports that are supported byreliable information. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Commitment Schedule - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year The following operating lease commitment was incorrectly included in the schedule for commitments | Management did not thoroughly review the AFS to ensure that commitment schedules are complete | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Completeness of Commitments: Contract rates - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” The following active contracts expressed in terms of applicable rates were not included in the commitment schedule. | Management did not thoroughly review the AFS to ensure that commitment schedules are complete | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Commitments Schedule VS D-Road written off - In terms of sec122 (1)(a) of MFMA, every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year; We compared the current year expenditure amount as per the commitment schedule with the capital expenditure for D-Roads and noted the following variances | Inadequate review of the AFS. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Commitments completeness of commitments register. - Financial statements shall present fairly the financial position, financial performance and cash flows of an entity. Fair presentation requires the faithful representation of the effects of transactions, other events and conditions in accordance with the definitions and recognition criteria for assets, liabilities, revenue and expenses. The application of Standards of GRAP with additional disclosures, when necessary, is presumed to result in financial statements that achieve a fair presentation. | Management did not thoroughly review the AFS to ensure that commitment schedules are complete | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Orders open for More than 60 days - In Terms of Supply chain management policy and procedures, 53. Procurement procedures Official Purchasing order: 4) The official purchase order issued by the municipality must be valid for a period not exceeding sixty (60) days from the date of issue for all supply and delivery transactions. (5) The purchase order must clearly indicate that the purchase order is valid for (60) days only and the fact that it shall be cancelled if delivery is not made within the terms of the purchase order. (6) The accounting officer must cancel the official purchase order issued by the municipality if the appointed supplier fails to deliver goods or services within the sixty (60) days from the date of issue. Contrary to the above SCM policy, the following purchases orders were open for more than 60 days. | Inadequate review of the supply chain management policy | Councell all orders exceeding 60 days. |  |
| Interest on outstanding debtors calculated incorrectly - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;”The following variances were noted, in the sample selected, when recalculating interest on outstanding debtors | Inadequate review of the AFS supporting schedules. | Perform Monthly reconciliations. |  |
| Restatement of Operating Lease Commitment. - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” The following misstatement was noted when auditing the comparative figures of operating lease commitments. | Inadequate review of the AFS. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Banking Service Bid advertised for less than 60 days - The closure date for the submission of bids may not be less than 60 days from the date on which the advertisement is placed in a newspaper in terms of regulation 22(1). Bids must be restricted to banks registered in terms of the Banks Act, 1990 (Act No. 94 of 1 990). | Inadequate review of the required regulation before the advertisement | 1. Conduct refresher training for all SCM officials. |  |
|  |  | 2. Review all adverts against the applicable regulations before publishing. |  |
| Unwanted Over Spending - Section 62 (1) (h) of the Municipal Finance Management Act states that “The Accounting Officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps to ensure that the municipality’s available working capital is managed effectively and economically in terms of the prescribed cash management and investment framework.In contravention to the act, the municipality procured security services from a service provider without assessing, actual operations, security threat and the need to address such threat by spending more than R10.5m per annum. The security cost is not justifiable due to the following reasons: 1. The cash collections/transactions at the municipality is absolutely low 2. Assets prone to any security threat is very minimal to justify a fraction of such expenditure. 3. Operations are confined to a specific point and area of premises is small The current number of security personnel deployed and their search do not add value to the municipality instead, it is just a fruitless and wasteful expenditure. The reasonable amount of security expenditure considering the security threat, operations and industry bench mark amounts to R1 368 000 per annum. Any expenditure incurred over and above is fruitless and wasteful expenditure. |  |  |  |
| Unauthorized Expenditure - In terms of MFMA definition, Unauthorised expenditure means any expenditure incurred by the municipality otherwise than in accordance with section 15 or 11(3) of MFMA and it includes: - overspending of the total amount appropriated in the municipality s approved budget. - overspending of the total amount appropriated for a vote in approved budget. - Expenditure from a vote unrelated to the department or functional area covered by the vote We compared the actual spending against the adjusted budget per department and noted that unauthorised expenditure is understated by R10 312 833 | Inadequate review of the AFS Disclosure. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Presentation of Contingent liability. - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” When reviewing the disclosure note of contingent liabilities, we noted that the presentation does not include the comparative figures. | Inadequate review of the AFS Disclosure. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Completeness of Related Parties. - According to MFMA 122(1)(a) “Every municipality and every municipal entity must for each financial year prepare annual financial statements which fairly presents the state of affairs of the municipality or entity, its performance against its budget, its management of revenue, expenditure, assets and liabilities, its business activities, its financial results, and its financial position as at the end of the financial year;” The municipality did not disclose Sekhukhune District Municipality as related party for maintenance of landfill side. | Inadequate review of the AFS Disclosure. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Listings for KPA 2 and 3 not submitted - In terms of section 74 (1) of MFMA, the accounting officer of the municipality must submit to the National Treasury, the Provincial Treasury, the Department for Local Government in the province or the Auditor-General such information, returns, documents, explanations and motivations as may be prescribed or as may be required.“All documentation and information in support of the financial statements, the annual performance report and compliance with legislation must be available on request and be retrievable within a reasonable time, which should not exceed three working days.” The listings that support performance reported in the APR as per KPA 2 and 3 were not submitted for audit as per request for information number 17 dated 06 September 2018. | Implement proper record keeping in a timely manner to ensure that complete, relevant and accurate information is accessible and available to support financial and performance reporting Management did not provide us with the information requested | 1. Management to ensure that a complete and accurate audit file is prepared before the commencement of the audit. 2. Record management systems to be improved in the 2018/19 financial year to prevent unecessary delays due to slow submission of information to the auditors |  |
| Number of EPWP jobs created. - In terms of sec 62 (1) of MFMA, the accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps (a) that the resources of the municipality are used effectively, efficiently and economically; (b) that full and proper records of the financial affairs of the municipality are kept in accordance with any prescribed norms and standards; (c) that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control The following variances were noted when auditing number of EPWP jobs created. | Inadequate review of the APR. |  |  |
| No effective traffic law enforcement - The municipality's community safety department does not monitor the traffic law enforcement. Municipality has employed traffic law enforcement officers in Jane Furse. But the traffic/law enforcement officers are not enforcing the traffic laws as required. Inadequate law enforcement monitoring by the Community Safety Department at this municipality 1. Accidents are common and it leads to loss of property 2. Traffic blocks, traffic chaos and road congestions 3. Delays in travelling as the traffic flow is hampered. | Traffic officers’ needs trainings. | Management to ensure the effectiveness of the traffic law enforcement |  |
| Life Span of Traffic Fines - Section 62 (1) (b) of the Municipal Finance Management Act states that “The Accounting Officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take all reasonable steps to ensure that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control The municipality does not have procedures in place that determine the life span of traffic fines and serves as a guidance on after how long should the traffic fines should be regarded as irrecoverable and be written off. In the absence such control measure/procedures the receivables from traffic fine and provision for impairment are misstated. | Review and monitor compliance with applicable legislation | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Receivables – Provision for Impairment of Debtors on Property Rates - In terms of GRAP 104, paragraph 58, A financial asset or a group of financial assets is impaired and impairment losses are incurred if, and only if, there is objective evidence of impairment as a result of one or more events that occurred after the initial recognition of the asset (a ‘loss event’) and that loss event (or events) has an impact on the estimated future cash flows of the financial asset or group of financial assets that can be reliably estimated. Objective evidence that a financial asset or group of assets is impaired includes observable data that comes to the attention of the holder of the asset about the following loss events | Review and monitor compliance with applicable legislation | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |
| Misstatements of traffic fines debtors that supposed to be written offs as a bad debt -In terms section 12(1) of the prescription Act, the prescription of a debt begins to run as soon as the debt is due. Prescription Act paragraph 11. State that the periods of the prescription debts shall be the following: (a) Three years in respect of • Traffic fines issued. | Management did not thoroughly review the AFS to ensure that receivables classification is in line with GRAP requirements. | Annual Financial statements and the Annual Performance Report to be thoroughly reviewed by the CFO, Internal Audit and Audit Committee before submission to the AGSA |  |

FINANCIAL VIABILITY SWOT ANALYSIS

| STRENGTHS | - Well established BTO unit - Competent skilled staff - AFS prepared in house - All key position are filled. - Effective mSCOA compliance system - Team work - Adequate cash flow Management - Credible Valuation roll - Stable Political and Administration Environment - Support from both National and Provincial Treasury - Approved Budget Related Policies |
| --- | --- |
| W EAKNESES | - Inadequate office space - Inadequate Revenue Control. - Inadequate contract management Measurements - Inadequate Fleet Management Controls - Inadequate Document Management - Time Management - Limited Sources of Revenue and poor collection - Poor Implementation of Procurement Plan |
| OPPORTUNITIES | - New sources of revenue (Waste management, testing stations, street advertising, stalls). - Training - Job creation through FMG - Economic development in Jane Furse(Primary node) - Revenue from government properties (Property rates) |
| T HREATS | - Grant Dependency - Unsustainable budget. - Work stations not compatible to mSCOA - Changes in mSCOA Version - Non compliance office Plan to OHS - Loss of key financial Management staff - Regression in Audit opinion - Residence by Customers to pay Municipal Rate and Taxes - Non compliance with MFMA and its Regulation. |

Challenges

- Limited revenue base

- High grant dependency

- Poor collection of property rates billed revenue

- Inadequate implementation of MSCOA project

- Material audit findings on municipal Annual Financial Statements

- Poor adherence to municipal procurement plan

- Underspending of approved annual budget.

3.6. KPA 5: Good Governance and public participation

3.6.1 Governance Structure

The Governance Structure of Makhuduthamaga Municipality is informed by the Municipal Structures Act (Act 117 of 1998). This Act stipulates different roles and responsibilities that each structure within the municipality should perform.

3.6.1.1 Political Structure

Section 53 of the Municipal Systems Act, Act 32 of 2000, stipulates inter alia that the respective roles and areas of responsibilities of the political structure and each Political Office Bearer of the Municipality and of the Municipal Manager must be defined.

Table 3: Makhuduthamaga Municipal Council consists of 62 Councilors and the political party representation is as follows:

| Political party | No of Councilors | % (Percentages) | No of Voters |
| --- | --- | --- | --- |
| African National Congress (ANC) | 43 | 67.95% | 85 338 |
| Economic Freedom Fighters (EFF) | 14 | 21.73% | 27 293 |
| Democratic Alliance (DA) | 02 | 3.39% | 4 259 |
| South African Maintenance and Estate Beneficiaries Association (SAMEBA) | 1 | 1.13% | 1 417 |
| Azanian People’s Organisation (AZAPO) | 1 | 1.19% | 1 498 |
| African People’s Socialist Party (APSP) | 1 | 1.75% | 2 198 |

3.6.1.2 Mayor and EXCO

The Mayor of the Municipality Minah Maitula assisted by the Executive Committee heads the executive arm of Council. The Mayor is at the centre of the system of governance. The Mayor operates in concert with the Executive committee (see table below):

| Name of Member | Portfolio |
| --- | --- |
| M.M. Maitula ( Mayor) | Exco Head |
| Clr .M.J Mohlala | Head Infrastructure Services |
| Clr N.H Mankge | Head Corporate Services |
| Clr | Head Budget and Treasury /Leader of Council Business |
| Clr KR Maisela | Head Community Services |
| Clr MP Lerobane | Economic Development and Planning |
| Clr MT Mapheto | Deputy Head Budget and Treasury |
| Clr PT Maloma | Deputy Head Community Services |
| Clr AL Monakedi | Deputy Head Economic Development and Planning |
| Clr M Phala | Deputy Head Infrastructure Services |

3.6.1.3 Speaker and Council

The Makhuduthamaga Municipality consists of 62 Councilors. 31 are ward Councilors and 31 are proportional Councilors, and 10 Magoshi, making a total of 72.  The Speaker presides at meetings of Council.

The Table below indicates with their capacity / positions.

| Name of Councilor | Capacity / Ward no | Political Party | Ward Representing / Proportional |
| --- | --- | --- | --- |
| Mamushi Frank | Ward Councilor -1 | ANC | Ward |
| Shikoane Mohlahle Louis | Ward Councilor - 2 | ANC | Ward |
| Leshalabe Makopi Mavis | Ward Councilor -3 | ANC | Ward |
| Nkgadima Moshukutjoane Renes | Ward Councilor -4 | ANC | Ward |
| Ranala Semeneke Tiny | Ward Councilor -5 | ANC | Ward |
| Thokwane Kgalake Zacharia | Ward Councilor -6 | ANC | Ward |
| Mapitsing Tswaledi Jerry | Ward Councilor -7 | ANC | Ward |
| Morodi Papana Ezekiel | Ward Councilor -8 | ANC | Ward |
| Maitjie Christina Dudu | Ward Councilor -9 | ANC | Ward |
| Madihlaba Mpjane Gilbert | Ward Councilor -10 | ANC | Ward |
| Maredi Helen Matsemela | Ward Councilor -11 | ANC | Ward |
| Rankoe Tabane Peter | Ward Councilor -12 | ANC | Ward |
| Mogashoa Nkopodi Ambrose | Ward Councilor -13 | ANC | Ward |
| Maloma Disedi Rachel | Ward Councilor -14 | ANC | Ward |
| Maduane Kwelagobe Albert | Ward Councilor -15 | ANC | Ward |
| Makua Seekane Samuel | Ward Councilor -16 | ANC | Ward |
| Marabele Kgabane Olly | Ward Councilor -17 | ANC | Ward |
| Motseni Ntibaneng Lilly | Ward Councilor -18 | ANC | Ward |
| Seboane Tricker Mmadire | Ward Councilor -19 | ANC | Ward |
| Mothogwane Ditsepu | Ward Councilor -20 | ANC | Ward |
| Mabatane Mathale Class | Ward Councilor -21 | ANC | Ward |
| Komane Magomarele Lydia | Ward Councilor -22 | ANC | Ward |
| Maila Mathabeng Johannes | Ward Councilor -23 | ANC | Ward |
| Matsageng Ditlale Betty | Ward Councilor -24 | ANC | Ward |
| Diketane Selege Paul | Ward Councilor -25 | ANC | Ward |
| Mahlase Masekwele Merah | Ward Councilor -26 | ANC | Ward |
| Masemola Maapo Simon | Ward Councilor -27 | ANC | Ward |
| Mosoane Erick Makatise | Ward Councilor -28 | ANC | Ward |
| Maleka Koaedi Jimson | Ward Councilor -29 | ANC | Ward |
| Dolamo Mathabathe Faith | Ward Councilor -30 | ANC | Ward |
| Matseding Maleesane Louisa | Ward Councilor -31 | ANC | Ward |
| Bahula Maledimo Mina | PR Councilor | ANC | Proportional |
| Tala Mathope Andrew | PR Councilor | ANC | Proportional |
| Chego David Kgwediebotse | PR Councilor | ANC | Proportional |
| Maisela Kanyane Rinah | PR Councilor | ANC | Proportional |
| Mankge Herman Ntuwe | PR Councilor | ANC | Proportional |
| Lerobane Matjudubane Paulinah | PR Councilor | ANC | Proportional |
| Phala Mmalebo | PR Councilor | ANC | Proportional |
| Mamahlako Mike | PR Councilor | ANC | Proportional |
| Mokomane Magedi Linkie | PR Councilor | ANC | Proportional |
| Matjomane Namudi Moses | PR Councilor | ANC | Proportional |
| Diale Kotupo Elizabeth | PR Councilor | ANC | Proportional |
| Mohlala Magetlane Johannes | PR Councilor | ANC | Proportional |
| Mathume Mateng Rose | PR Councilor | APSP | Proportional |
| Thokoane Matshehle Joseph | PR Councilor | AZAPO | Proportional |
| Mapheto Moses Thangwane | PR Councilor | DA | Proportional |
| Diale Mochalaka Helen | PR Councilor | DA | Proportional |
| Monakedi Alfred Lekgitlane | PR Councilor | EFF | Proportional |
| Nkadimeng Lekoba Reinah | PR Councilor | EFF | Proportional |
| Thamaga Modise Robert | PR Councilor | EFF | Proportional |
| Leshaba Tshuba Reneilwe | PR Councilor | EFF | Proportional |
| Madutlela Kopedi Klaas | PR Councilor | EFF | Proportional |
| Magashula Matjatja Elizabeth | PR Councilor | EFF | Proportional |
| Maloma Putting Timothy | PR Councilor | EFF | Proportional |
| Sebesho Mamathung Selinah | PR Councilor | EFF | Proportional |
| Phala Margared Maletsiri | PR Councilor | EFF | Proportional |
| Shongwe Bhekimbi Edward | PR Councilor | EFF | Proportional |
| Mashifane Gladys Mathabathe | PR Councilor | EFF | Proportional |
| Phasha Lepou Patricia | PR Councilor | EFF | Proportional |
| Sekwati Khudu Dipuo | PR Councilor | EFF | Proportional |
| Moganedi Balebetse Ennie | PR Councilor | EFF | Proportional |
| Makobe Phello Alpheus | PR Councilor | SAMEBA | Proportional |
| Source:MLM Office of the Speaker,2016 3.6. 1.4 Additional Committees In addition to the above, the municipality has various committees , these include: Section 79 / 80 Committees: - Corporate Services - Community Services - Infrastructure Development - Economic Development and Planning - Budget and Treasury - Local Labour Forum - Audit committee - Appeals committee - Municipal Public Accounts Committee ( MPAC) - Ward committees - Rules and programming committee - Ethics committee - Geographic Names Change Committee |  |  |  |
| 3.6.2 Stake holder participation 3.6.2.1 Stakeholder Participation analysis Stakeholder; Description; Challenge. Makhuduthamaga Local Municipality Council; - Prepare process plan for IDP review - Undertake the overall management, coordination and monitoring of the process as well as the drafting of the local IDP - Approve IDP within the agreed framework; Non adherence to stakeholder engagements. SDM; - Compile IDP Framework for the District - Ensure alignment of IDP s in the District - Prepare joint strategy workshops with local municipalities, provincial and national role players; Adhered to. Office of the Premiere; - Ensure Medium Term Framework and Strategic Plans of Sector departments considers IDPs - Support and monitor CoGHSTA alignment responsibilities; Inadequate monitoring of sector departmental participation in the IDP/Budget processes. CoGHSTA; - Ensure horizontal alignment of IDPs of various municipalities - Ensure vertical alignment between provincial sector departments/strategic plans and IDP processes; Delays in issuing the results of IDP/Budget Assessment. Sector departments; - Contribute technical knowledge, ideas and sector expertise to the formulation of municipal strategies, projects and sector plans - Provide departmental operational and capital budgetary information; Inadequate participation in the IDP processes Implementation of projects not listed in the IDP No progress reports on implementation of projects. IGR Structures (IDP Rep forum,IDP Managers/ Officers Forum,PDPF,DDPF); - Provide dialogue between sectors for holistic infrastructure development - Promote inter-governmental dialogue to agree on shared priorities and interventions; Ineffective DDPF. LEDET; - Provide advice on environmental, economic development and trading issues; Adhered to more particularly on environmental issues. Treasury; - Provide support to ensure that the municipality complies with MFMA and relevant regulation; Adhered to. Civil society (CBOs,NGOs,Organisations for Youth, women and people with disabilities, tertiary and research institutions; - Inform and consult various interests of the community; Not enough resources are available to meet needs of all interests groups. Communities; - Identify and prioritize needs - Discuss and comment on the draft IDP review - Monitor performance in the implementation of IDP. Ward committees; - Articulate community needs - Participate in the community consultation meetings - Help in the collection of needed data/research; Delays in submitting needs Conflict with CDWs. Community Development Workers; - Help in the generation of required data, thereby providing requisite support to ward committees; Delays in submitting needs Conflict with ward committees. Political parties; - Provides inputs; Conflicts among political parties. Media; - Inform the public on the municipal activities. Newsletter; - Contribute to the success of reaching the community; Delayed production /distribution of newsletter. 2019 -2020 IDP/Budget Stakeholders Consultations Programme Date; Target /Stakeholder; Time; Venue. 18/04/2019; Masemola Cluster; 10H00; Kome (Kome Morning Stars Sports Ground). 18/04/2019; Schoonoord Cluster; 10H00; Malegale (Vultures Sports Ground). 18/04/2019; Jane Furse Cluster; 10H00; Molepane (Silver Stars Sports Ground). 18/04/2019; Phokoane Cluster; 10H00; Mogudi (Mogudi United). 22/04/2019; Social Sector (Traditional councils,HIV/Aids council,NAFCOC,LED forum,NGOs and CBOs; 13H00; MLM Council Chamber. 23/04/2019; Magoshi; 09H00; MLM Council Chamber. 24/04/2019; Ward Committees (Schoonoord and Jane Furse Cluster); 10H00; Peter Nchabeleng Sports Centre. 24/04/2019; Ward Committees (Masemola and Phokoane Cluster); 10H00; MLM Council Chamber. 25/04/2019; Municipal Staff; 10H00; MLM Council Chamber. 15/05/2019; IDP Representative Forum; 10H00; MLM Council Chamber. 29/05/2019; Municipal Council (Approval of final Draft 2019-20 IDP/Budget); 10H00; MLM Council Chamber. IDP Rep Forum and Mayoral Imbizos The forum is not functional as per approved process plan. The Public Participation Division in the Office of the Speaker sometimes fails to coordinate meetings. The Mayor together with councilors held Imbizos whereby ordinary community members are given chance to raise their views in terms of service delivery challenges and report to them on progress made by the municipality. Ward committees and CDWs The municipality has established 31 ward committees which assist council in terms of liaising with the community. They play a role as link between the municipality and community and facilitate development of long term vision. Ward committees ensure that the views of the committees are captured in the IDP by attending to public participation meetings and submitting inputs to the municipality. The municipality has developed a ward committee policy to ensure the effectiveness and efficiency of system. They assist in terms of monitoring municipal institutional performance. The ward committees’ reports get evaluated every month for the purpose of monitoring their functionality and effectiveness.The newly elected committee members were inducted on their roles, functions and code of conduct from the 13-15 February 2017. The municipality has 24 Community Development Workers (CDWs) deployed to 31 wards and remain with 7 wards without CDWs. This is constituted by 15 females and 9 males.The CDWs are linked directly with Public Participation Office which is in the Office of the Speaker.CDWs attends all ward committee meetings duly convened by the Chairperson (Ward councilor) of the ward committee.They serve as resource persons during the official sittings of the ward committee Traditional leaders Makhuduthamaga Local Municipality has 27 Traditional leaders and indunas appointed in terms of Traditional Leadership and Governance Framework Amendment Act, 2003.There are 10 traditional leaders serving in the Municipal council as Ex- officios in terms of Municipal Structures Act.The relationship between Traditional leaders and the municipality is healthy. The main issue with the traditional authorities in the municipality is that residential development is currently taking place in uncoordinated and chaotic manner in the area. This is largely because there is inadequate coordination between the municipality, the traditional authorities and CoGHSTA. The functions for site demarcation and allocation remain vested with traditional authorities and Provincial Department of CoGHSTA respectively. The land issue within Makhuduthamaga is of critical importance because of the extent of tribal ownership. Municipal Public Accounts Committee (MPAC) The Municipality has established a Municipal Public Accounts Committee in terms of Sections 33 and 79 of the Municipal Structures Act 1998. This committee plays an oversight role of the council.It examine the financial statements and audit reports of the municipality and in doing so the committee must consider improvements from previous statements and reports and must evaluate to which extent the audit committees and auditor general recommendations have been completed.To recommend or undertake any investigation in its area of responsibility, after reviewing any report from any acouncil committee or from the Audit committee. The committee consists of twelve non-executive councilors and the Chairperson is fulltime. Challenges; Action Plan. Minimal stakeholder participation; X; Capacity enhancement of different stake holders. Alignment of activities and programmes with other spheres of government; X; enhancement of IGR Function. 3.6.3 Risk Management 3.6.3.1 Extremely Critical Risks The Municipality is critically aware of the impact of risk on service delivery. As such; it has developed extensive risk mitigation measures for both strategic and operational risks that have been identified. The municipality has adopted an integrated approach to risk management with the primary aim of embedding of a culture of making a correct and timely decisions that take in to consideration associated risk exposures and opportunity. Risk governance in the Municipality The Municipality has Independent Governance Oversight and Advisory committees, namely, Risk management Committee and the Audit Committee, which operate in accordance with Council approved terms of reference, Corporate governance guidelines and practices (King III).This will ensure both the reliability and quality of advisories and integrated reporting to the council. Some of the key strategies in the short-to-medium term to ensure successful implementation of risk governance and enterprise risk management in Makhuduthamaga Local Municipality are listed below: - Risk governance structure, Framework and Policy - Risk management Oversight - Risk ownership and accountability - Risk management approach and principles - Risk assessment methodology - Continuous risk assessment, design and implementation of risk response and continuous monitoring. - Risk profile and integrated risk reporting Challenges facing Risk Management - Non existence of Risk Management IT system / Infrastructure - Insufficient Staff The Table below illustrates an overview of risk assessment: Objectives; Risk Description; Root cause; Inherent risk. To optimize revenue base through enhanced collection; Inadequate revenue generated; Inadequate basic services rendered to communities Misunderstanding of property rates bt business owners Land ownership (Tribal authority)land is owned bt 3rd parties and not municipality; Medium. To ensure effective and efficient utilization of space; Inability to manage utilization of space; Tribal authorities not engaging the municipality when allocatin land Land is owned by Tribal authorities; Medium. To successfully implement mSCOA by 01 July 2017; Inability to execute mSCOA transaction; Poor planning Resistance to change Lack of skills Lack of resources; Medium. To ensure solid waste collection; Inability to collect waste in all municipal areas; Inadequate waste management systems. To ensure greater road infrastructure; Inability to maximize eradication of road infrastructure baclog; Budget constraints; Medium. To ensure effective oversight by new council; Lack pof understanding of municipal operations by new council; Newly elected councilors Inadequate understanding of municipal processes. To manage effectively all political parties in council; Diversity of political parties with conflicting interests and agendas; Newly elected councilors Multi-party democracy. Audit Committee The Internal audit component of the municipality was established in terms of the approved organizational structure to ensure that the municipality has systems and processes in place that will ensure or improve compliance to various legislative requirements,thus trying to achieve a better audit opinion.The Audit committee was appointed through a Council resolution.This committee reports directly to council to assist it to achieve its oversight role efficiently and appropriately based on the expertise of the various members of the committee. Section 166(2) of the MFMA state that an Audit Committee is an independent advisory body which must amongst others advise the Municipal council,the Political Office Bearers,the Accounting Officer and the management staff of the municipality,on matters relating to: - Internal financial control - Risk management - Performance management,and - Effective governance In the financials under review the Audit committee also performed the Perfomance Audit Function. Municipal Audit Outcomes (External Audit) The Makhuduthamaga municipality is required to prepare Annual Financial Statements (AFS) which must be audited by the Auditor General of South Africa (AGSA) in terms of Section 188 of the Constitution of the Republic of South Africa, 1996 (Act No.108 of 1996) Section 4 of the Public Audit Act of South Africa, 2004 (Act No.25 of 2004) (PAA) and Section 126(3) of the Municipal Finance Management Act of South Africa, 2003 (Act 56 of 2003). For the past five years the Municipality has performed well according to Auditor General’s reports in terms of Financial Management and finance related matters. Analysis of Audit Opinion by the Auditor General over the last five years 2013/14; 2014/15; 2015/16; 2016/17; 2017/18. Unqualified opinion; Unqualified opinion; Unqualified opinion; Unqualified opinion; Qualified audit. Source: Auditor General Report Anti-Corruption Corruption is defined as “ any conduct or behavior in relation to persons entrusted with responsibilities in public office which violates their duties as public officials and which is aimed at obtaining undue gratification of any kind for themselves or for others The municipality has developed the anti-corruption strategy, which aims : - To prevent and combat fraud and corruption and related corrupt activities - To punish perpetrators of corruption and fraud - To safeguard MLM properties, funds, business and interest 3.6.4 Policies, Strategies and Plans 3.6.4.1 Policies, Strategies and plans These documents are instruments that guide Council, the Administration and Communities and provide the environment for responsible Local Government in the municipal area. The following table contains a list of policies, systems, plans, frameworks and strategies with current assessments thereof indicated. Policies, Strategies and Plans; Status; Date approved. Staffing Policy; Adopted; 15 December 2016. Tariff Policy; Adopted; 31 May 2016. Credit control and Debt collection policy; Adopted; 31 May 2016. Asset management Policy; Adopted; 31 May 2016. Property Rates Policy; Adopted; 31 May 2016. Indigent Policy; Reviewed; 2017/18. Overtime Policy; Adopted; 31May 2016. Communication Policy; Adopted; 31 May 2016. Supply Chain Management Policy; Adopted; 31 May 2016. Budget policy; Adopted; 31 May 2016. Public Participation Policy; Adopted; 10 June 2016. Complaints Management Policy; Adopted; 10 June 2016. Employment Equity Plan; Adopted; 2014/ 2015. HR policies; Adopted; 15 December 2016. Revenue enhancement policy; Adopted; 31 May 2016. Rates policy; Adopted; 31 May 2016. SDF; Adopted; 2014/15. Land Use Management Scheme; Adopted; 2008. Institutional Plan; Adopted; 2015/16. Workplace Skills Plan; Reviewed; 2017/18. PMS Strategy; Reviewed; 2017/18. Water Services Master Plan; Adopted by SDM; 2014. WSDP; Adopted by SDM; 2016. Road Master Plan; Adopted; 2012/13. Integrated Transport Plan; Draft; Since 2014/15. Housing Chapter; Draft; Since 2014/15. Integrated Waste Management Plan; Adopted; 2017/18. Disaster Management Plan; Adopted; 2014/15. LED Strategy; Reviewed; 2017/18. Risk Management Policy; Adopted; 2017/18. Risk Management Strategy; Adopted; 2017/18. Anti corruption strategy; Adopted; 2017/18. Internal Audit Charter; Adopted; 2017/18. GIS policy; Adopted; 2017/18. 3.6.5 BY -LAWS 3.6.5.1 BY –Laws The following By- laws are promulgated No; By-Law. 1; Street advertising by-law. 2; Street trading by-law. 3; Municipal Waste Management by-law. 4; Makhuduthamaga Local Municipality Property Rates by-laws. 5; Makhuduthamaga Local Municipality Tariff by-laws. 6; Rules of order regulating the conduct of meetings of the Council at Makhuduthamaga. 7; Rules of order regulating the conduct of meetings of the Portfolio Committees at Makhuduthamaga. 8; Makhuduthamaga Local Municipality Credit Control by-laws. 3.6.6 Inter Governmental Relations 3.6.6.1 Inter Governmental Relations Intergovernmental relations take place in an unstructured manner in Makhuduthamaga. The municipality aims to ensure that IGR takes place in terms of our Constitutional mandate and other relevant Legislation, most importantly the Inter Governmental Framework Act. The main purpose of IGR in a Municipality is to coordinate, facilitate and intervene between the various functions and responsibilities of the different spheres of government as well as interactions with parastatals, private sector and other stakeholders within our functional sphere in order to influence the effective delivery of our mandate. The municipality endeavors to ensure the full implementation of the IGR framework through the establishment of the IGR Forum that is represented by Municipal officials as well as sector departments within the district. The strategic aim of the Makhuduthamaga IGR Framework would include: - To promote and facilitate cooperative decision making - To coordinate and align priorities, budgets, policies and activities across interrelated functions and sectors - Ensure a smooth flow of information within government and between government and communities with a view of enhancing implementation of policies and programmes. Challenges; Action plan. Unstructured engagements with other spheres of government by line departments; X; Mainstreaming IGR within all line departments. Lack of interaction between different spheres of government; X; Mainstreaming IGR within Makhuduthamaga area. Non existence of IGR forum; X; Establishment of Forum. Customer care Makhuduthamaga Municipality has established a sound Customer Care Management system that aims to create positive and reciprocal relationship with customers.The council appoved customer care policy,customer care procedure manual and Draft turn around stratety.The Presidential and Premiers hotlines established mechanisms of complaints management for dealing with complaints from communities,to act / reply promptly to complaints and queries and provide corrective action.The municipality also installed suggestion boxes to all 27 tribal offices and other municipal satellite offices,this enables the municipality to deal with the needs and provide feedback to complainants.A customer care survey was conducted during 2013/14 financial year.All employees are provided with name tags as and when required,although the challenge is that employees do not comply all the time.The municipality managed to hold Bathopele build up activities successfully. Progress made in the past five years in terms of customer care Bathopele indicators; 2011/2012; 2012/2013; 2013/2014; 2014/2015; 2015/2016. Presidential hotline; 42; 68; 74; 84; 109. Premier Hotline; 0; 09; 12; 14; 18. Suggestion boxes; Boxes installed; No collection made; No collection made; No collection made; No collection made. Bathopele survey; Survey not conducted; Survey not conducted; Survey not conducted; Survey not conducted; Survey not conducted. Bathopele committees; Not yet established; Not yet established; Not yet established; Not yet established; Not yet established. 3.6.7 Traffic and Vehicle Licenses 3.6.7.1 Traffic Services and agency function The Municipality is rendering traffic services through: - Law enforcement to decrease incidents affecting traffic safety - Monitoring and collecting outstanding fines - Conducting community engagements and awareness programmes - Conducting an agency function for the Provincial Government by testing and licensing vehicles and drivers on an agency basis. Challenges; Action plan. Limited staff to perform licensing and law enforcement; X; Ensure ongoing Training of Traffic Officers to be undertaken. Collecting outstanding fines; X; Investigate the possibility of appointing external service providers/ procurement of system to assist with collection of outstanding fines. 3.6.8 Environmental Management 3.6.8.1 Environmental Management The Municipality is responsible for the development of Environmental policies, comment on Environmental issues, and compilation of Environmental reports, Environmental Law Enforcement and awareness. The Municipality needs to develop an Environmental Management System (EMS) based on International Standards ISO 144001 for Makhuduthamaga Municipality. This system will be used to ensure the protection of the integrity of the environment and ensure sustainability of the municipality. It will also ensure participative greener governance. The EMS forms part of the municipal sector plans that need to be submitted with the IDP. Challenges; Action plan. Increasing number of illegal activities by inhabitants leading to degradation of the environment; X; Increase law enforcement initiatives conduct environmental awareness campaigns. Lack of coordination in ensuring the protection of the environment within the municipal space; X; Strengthen the role of the Environmental Management Committee. Lack of capacity in environmental management; X; Capacitate the environmental officials in environmental management, compliance and enforcement training. 3.6.9 Disaster Management The MLM has developed and adopted Disaster Management Plan during the 2007/8 financial year and it will be reviewed in the 2018/19 financial year. The plan is aimed at disaster prevention, mitigation, preparedness, response, recovery and rehabilitation. It also aimed at providing an enabling environment for disaster management in the municipal area- Promote pro active disaster management through risk reduction programmes, promote cooperative relationships between all spheres of government in case of emergency incidence 3.6.10 Municipal Law Enforcement 3.6.10.1 Law Enforcement The general priority of the law enforcement unit is to ensure that the community is adhering to the By-laws and policies of Makhuduthamaga Municipality. This unit works hand in hand with all municipal departments, the SAPS and other sector departments. GOOD GOVERNANCE AND PUBLIC PARTICIPATION SWOT ANALYSIS STRENGTHS; - Council inaugurated legally - Political stability - Institutional policies adopted (HR, Finance etc) - Section 79 and 80 committees established - Ward committees established - Branding manual and communication strategy adopted - Audit committee charter adopted by council - Organizational structure approved - Customer care facilities in place. WEAKNESES; - Inadequate staff in Risk management and Internal audit units - Lack of policy for security for municipal staff and councilors - Inadequate resources, skills and experience for maximum performance within legislative and executive units - Reviewed standing rules and orders should include security management in council - Appointed security officers not utilized effectively - Inadequate implementation of Risk Management and internal audit recommendation. - Inadequate office space - None compliance with approved WSP - No salary progression system - No PMS for lower staff component - Poor organizational design - Non compliance with EEP - Low staff morale - Non implementation of gazzeted requlatory framework by-laws and policies. OPPORTUNITIES; - Audit and Risk committees functional - New governance model implemented - Improved public participation - Improved institutional performance - SALGA collective agreement available. THREATHS; - Inadequate safety and security of Municipal staff, councilors and stakeholders - Disruption of council proceedings by public members - Unauthorised public protests /marches - Negative media coverage - Litigation o municipal cases. CHALLENGES - Ineffective functioning of IGR structures - Inadequate implementation of Internal Audit and Risk Management recommendations and action plans - Inconsistent coordination of good communication principles and practices within the municipality - Non coordination and adherence to Council Master Plan (Public Participation - Inadequate stakeholders engagement 3.7. KPA 6: Municipal Transformation and Organisational Development 3.7.1 Institutional analysis Council, Committees and functionality / Governance Makhuduthamaga Local Municipality has 62 Councilors i.e. 31 Ward Councilors and 31 Councilors elected from proportional party list (PR). The Mayor is the head of Exco which comprises of 10 Councilors who are Heads of departments in terms of Section 80 of Municipal Structure Act. The Mayor, Speaker, Chief whip and two Exco members are full time whereas the remaining number of Councilors is on part time basis. The Municipality has considered the establishment of Council Structures, the statutory committees established in terms of the Municipal Structures Act and the Municipal Finance Management Act. The composition of a particular committee is mainly determined by the role it is envisaged to play. For instance, if the committee has to perform the political oversight, the members will as such be politicians and take the form of portfolio committee while administrative committees focus on technical issues and are constituted by the technocrats. The Council Structures of Makhuduthamaga Local Municipality include the following: Council, Executive committee, Economic Development and Planning portfolio committee, Infrastructure Development portfolio committee, Corporate Services portfolio committee, Community Services portfolio committee, Budget and Treasury portfolio committee, Local Labour forum, Human Resource committee(Training, Employment Equity committee, OHS committee, Employees wellness),Bids committees, Oversight, Audit committee and Municipal Public Accounts Committee The functionality of these committees is often determined by the frequency of meetings and turnaround time on issues that are delegated to respective committees. The governance committees usually have schedules of meetings and they meet at least four times annually i.e. hold a meeting at least once per quarter. On the other hand, administrative committee can meet as frequent as possible, depending on the need and urgency of matters to be dealt with. However, a minimum of six meetings per annum is expected for each administrative committee. 3.7.2 Staff components and Employment Equity The staff component of the municipality is made up of 40 women and 55 men and it represents Employment Equity. We have five Disabled employees. Employment equity challenges The Municipality is grappling with employment equity challenge of ensuring that its structures reflect equitable representation of all groups, particularly the people with disability. The male- female ratio stands at 55:40.This translates into the municipality having 38% of its workforce being women while men contribute 62% of the workforce. The ability to retain and attract skilled staff is limited – a situation is reflected in the number of vacancies in the Organogram. The table below depicts the current equity status in respect of designated categories of employees at various levels. 3.7.3 Organisational Performance Management System (OPMS) and Performance Management System Performance management serves to measure the performance of the Municipality on meeting its IDP.The Makhuduthamaga Local Municipality has adopted its Performance Management Strategy during 2015/16 financial year. A performance management unit was established in 2011. It is currently concentrating on the organizational and individual performance at the level of section 57 managers. Immediately after the adoption of the IDP and budget, the municipality develops Service Delivery and Budget Implementation Plans (SDBIP) which serves as business plans for individual departments within the municipality. The municipality has undergone a strategic planning session from 01-03 March 2017. From the adopted SDBIP the municipality abstracts Performance Contracts of the Section 57 employees which become the Departmental annual business plans. Departments report progress on the implementation of the SDBIP to Management reviews; Exco – Makgotla, Executive committee and Council for adoption. The purpose of these sittings is to monitor progress and performance in terms of the implementation of the IDP and budget and to propose reviews where necessary. The municipality is currently developing organisational review and staff re-engineering to address work processes, job descriptions and to do comparative job evaluation on the basis of TASK system. A Midyear a report (Section 72 report) is developed from the Quarterly reports generated during the EXCO Lekgotla sessions. Municipal annual service delivery reports are generated from this process on annual basis which amongst others will inform the formulation of the annual report. After the adoption of the Annual report by the Municipal Council, the Oversight Committee scrutinizes the report and makes final recommendations to the council for the adoption of the final Oversight report which will then be open for public consumption .All Section 57 Managers have signed Performance Agreements for 2017/18 financial year. |

HR and PMS Challenges

| CHALLENGES |  | ACTION |
| --- | --- | --- |
| Inadequate performance results | X | Annual review of PMS |
| Mainstreaming of the PMS Framework to all employees at management level | X | Roll out of PMS to all Management in 2018/19 |
| Inadequate remuneration packages |  | Development of remuneration policy and strategy |
| Inadequate policies and procedures for HRM / HRD |  | Develop and review of HRM / HRD policies and procedures |
| Inadequate office space and furniture |  | Extension of office building /acquiring of temporary offices |

Administrative Structure

Makhuduthamaga Local Municipality is divided into six departments which are interrelated:

- Economic Development and Planning

- Corporate  Services

- Community Services

- Budget and Treasury

- Infrastructure Services

- Office of the Municipal Manager

3.7.4 Skills needs within the Municipal Council

Municipalities are required in terms of the Skills Development Act no 97 of 1998 to facilitate training for capacity building in order to address skills gaps. A skills audit is conducted on an annual basis to inform the Workplace skills plan which guides all the training to be conducted throughout the year. The plan is developed in consultation with the staff members and councilors. Individuals from the mentioned stakeholders complete questionnaires that serve as tools to identify training needs. The training needs are further consolidated into WSP / ATR and submitted to LG SETA after approval by the Council on time as legislated. This should be able to address the issues of scarce skills.  MLM has a training committee which comprises of labour, Management and council; its role is to ensure that all training activities are done in consultation with all relevant stakeholders.

It is critical to note that among others, the critical skills needs within the Municipal Council are Engineering, Town Planning, and Finance and Leadership skills for Councilors.

### 3.7.5 Occupational Health and Safety (OHS)

The Makhuduthamaga Local Municipality has established Occupational Health Safety Committee.Committee is functional which has also been established as per legislative requirement and also there are six Health and Safety reps in place. The committee meets on quarterly basis .Committee members have thus far received training on First Aid Level one. And OHS Official to run the Unit has been employed by the municipality during the 2015/16 financial year.  The functions of the unit are guarded to advance the objects of Occupational Health and Safety Act, 85 of 1993.

The sub-unit will perform the following functions in an effort to ensure Health and Safety within the workplace.

• Enforcement or implementation of Occupational Health and Safety Act.

• Responsible for all administrative duties related to OHS including policy formulation and reviewing.

• Conducting health and safety workshop, meetings and seminars.

- Providing full range of Employee assistance program that is assisting employees with solving problems which might affect them from executing their duties. The sub-unit is currently manned by the Labour Relations Officer who is also responsible for Employee Wellness

### 3.7.6 Records and Registry Services

Shortage of space for records keeping and non compliance with the policy by departments’ i.e. some information not taken to the registry for filing is the main challenge. Registry office is available and an adopted file plan is also in place

3.7.7 Organisational Structure

The performance of powers and functions, and delivery of the IDP projects is dependent upon appropriate institutional structure. The Municipality reviewed its Organogram. The Organogram is the product of engagement with the CoGHSTA.  A model Organogram for Grade 3 municipalities was used as a base to develop the organisational structure. The powers and functions that are amenable to the municipality were also considered in the process.

NB: Draft Organogram for 2018/19 financial Year: See annexure B

Flowing from Public Participation Engagement with Communities and Stakeholders within Makhuduthamaga Local Municipality, the following issues repeatedly surfaced as overarching needs of the community:

### 3.7.8 Community needs analysis

1. Water and sanitation: water supply to communities is highly needed.The need to fix recurring broken water pumping machines and leakages of pipes.

2. Roads surfacing and provision of sufficient bridges and storm water drainages. Many roads were destroyed by heavy rains and floods in some areas.Speed humps.

3. Electricity (post connection is needed)

4. RDP houses (Sufficient and fast tracking delivery of RDP houses, proper construction and the need to complete the incomplete houses).

5.Better/tarred roads

6. High unemployment and illiteracy level.

- Spatial issues. Municipality does not own land, Ineffective implementation of LUMS and public awareness

8. Cell phone, TV and radio reception in some areas.

9.Inadequated Childcare facilities and libraries services

10.Cemetries(fencing and provision of sanitary facilities)

11.Inadequate public transport

12.Increasing capacity of the municipality to perform more functions

14.Mast lights to combat crime

15.Building of schools and additional classrooms

16.Noise control bylaw

Source: MLM 2016

### 3.7.9 KFA 65: Cross Cutting Issues

### Women Empowerment

Women empowerment is a phenomenon that is high on the agenda. The municipality has woman Mayor as part of empowering them. Women should be encouraged to partake in developmental projects that would assist them to get out of the poverty line that they found themselves in. This means that the resources should be channeled in the direction of women empowerment projects in order to empower them economically and politically. The municipality has developed a policy on how women matters can be approached and addressed.

### Youth Empowerment

The Municipality has appointed an official to deal with youth matters. It is in this office where issues that affect the youth are attended to. Issues that affect the youth are unemployment, lack of housing, poverty, shortage of skills, high level of crime and violence, social and family disintegration and other social ills like HIV/AIDS.A youth Council has been established as a platform whereby youth discuss and agree on issues that affect youth. It is within this background that youth development policy was developed to assist youth and young people to deal with issues that affect them such as unemployment, skills shortage, and vulnerability and under resourced. Resources should be biasely channeled towards the development of youth’s projects for the upliftment of young people of the municipality to stop the escalating crime and violence.Makhuduthamaga Youth Council was re-launched in February 2017 by the Office of the Mayor.

Gender Equity

Gender inequalities exist in the social, economic, physical and institutional environment of the municipality. The municipality has put in place an employment equity plan with monitoring indicators that are gender disaggregated. Within the municipality, several initiatives have been undertaken to advance the national gender agenda. Amongst others, a gender procurement scoring system is in place to encourage the economic empowerment of women entrepreneurs and companies.

### Children

The Office of the Mayor through their Special Programme Division support Rights of Children through

- Annual celebration of children’s day, and participating in annual activities aimed at promoting the rights of Children.

Aged / elderly

The Office of the Mayor through their Special Programme Division supports Aged development programmes through:

- Celebration of Social development month

- Programmes initiated by the Makhuduthamaga Aged group

### HIV/AIDS

The Municipality has developed and adopted policy on HIV/AIDS during 2008/9 financial year. The policy was reviewed during the 2015/16 financial year.HIV/Aids Council was re-launched during 2015/16 financial year. Mother-Children dialogue on HIV/Aids was held in collaboration with Sekhukhune Educare Project and Image.

HIV prevalence

| Municipality | 2012/13 | 2013/14 | 2014/15 |
| --- | --- | --- | --- |
| Makhuduthamaga | 5.9 | 6.2 | - |

Source:  Department of Health 2015

Voluntary testing for HIV

| Municipality | 2014-2015 |  |  | 2015-2016 |  |  | 2016-2017 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Males | Females | Total | Males | Females | Total | Males | Females | Total |
| Makhuduthamaga |  |  | 66506 |  |  | 7097 |  |  | 148178 |

Source: Department of Health Limpopo 2017

Latest TB, maternal deaths and infant mortality

| Municipality | Number of TB cases reported | Number of maternal deaths reported | Number of infant deaths reported (mortality) |
| --- | --- | --- | --- |
| Makhuduthamaga | 628 | 7 | 134 |

Source: Department of Health Limpopo 2017

Developmental challenges

- Inaccessibility of health due to poor roads and inadequate transportation

- Stigma attached to the HIV/AIDS disease by communities

- Awareness campaign to educate the community about the normality of living with the Virus

- Lack of medication at clinics and hospitals

- Insufficient drop in centres

- Most orphaned children are not in foster care due to long  procedures

- Inaccessible ARV sites and HIV and AIDS support groups

### Disabled Persons

Youth, women and people with disabilities have generally a broad range of interrelated needs which therefore must be addressed in a holistic and integrated manner. The municipality has identified major challenges that face people with disabilities such as lack of skills and career guidance. The Municipality together with OTP (Office of the Premier) has embarked on a programme of skilling the unemployed disabled persons whereby four people were on a one year Learnership on Development Practice. During the 2013/14 financial year the municipality has also employed three disabled persons as interns. A policy to address and approach matters affecting people with Disabilities was developed.

Business Sector

The Municipality is in good working relations with Makhuduthamaga Chamber of Commerce and Hawkers Associations within its area of jurisdiction. They participate actively in the affairs of the municipality especially during IDP stakeholders consultations meetings where the municipality engages stakeholders on development issues.

Non Government Organizations (NGOs) and Community Based Organizations (CBOs)

NGOs and CBOs like Love life, Kgwana, Sekhukhune Educare Project (SEP) and Makhuduthamaga Umbrella (umbrella body for Home Based Cares) are some of the important stakeholders that the municipality takes on board on matters of development. These organizations also have programmes on youth and HIV/AIDS that they run together with the municipality.

Academic and Research institutions

Makhuduthamaga Local Municipality has good working relations with institutions of higher learning. Officials and Councilors attended capacity development programs with University of Witwatersrand (CPMD), University of Pretoria (ELMDP and MFMP), University of Johannesburg (Municipal Governance) and DBSA Vulindlela Academy (MIDP) and many other courses run by accredited institutions in terms of LG SETA. The Municipality is also establishing links with the Limpopo Agro Food Technology Station based at the University of Limpopo.

IGR and intergovernmental relations

The Constitution of the Republic of South Africa, 1996 reflects on the Government of the Republic as “constituted as national, provincial and local spheres of government, which are distinctive, inter-dependent and interrelated”. It thus establishes some principles of co-operative and intergovernmental relations which all spheres of government all organs of state within each sphere must adhere to.

Among such principles with an impact on the IDP of which all spheres must observe are:

- Respect the constitutional status, institutions, powers and functions of government in the other spheres;

- Not assume any power or function except those conferred in terms of the Constitution;

- Exercise their powers and perform their functions in a manner that does not encroach on the geographical, functional or institutional integrity of government in another sphere;

- Co-operate with one another in mutual trust and good faith by-

- Fostering friendly relations

- Assisting and supporting one another;

- Informing one another of, and consulting one another on, matters of common interest;

- Coordinating their actions and legislation with one another;

- Adhering to agreed procedures; and

- Avoiding legal proceedings against one another.

In view of these principles of co-operative governance, a consideration was thus made on the powers and functions conferred to the Makhuduthamaga Local Municipality as well as policy frameworks binding on the municipality, requiring consideration, or requiring alignment.

MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT SWOT ANALYSIS

| STRENGTHS | - Qualified and experienced personnel - Credible highly rated IDP - Development of Annual report - Submission of legislated reports - Full Compliment of Senior Management Credible highly rated IDP |
| --- | --- |
| WEAKNESES | - Misalignment of IDP, Budget and SDBIP - Ineffective implementation of organizational structure - Poor performance of some personnel - IDP structures dysfunctional - Poor communication with stakeholders - Non implementation of PMS framework |
| OPPORTUNITIES | - Willingness on stakeholders and communities to participate in municipal programmes including consultations - Sectoral support (SALGA,COGHSTA,EPWP &CWP) |
| THREATHS | - Dissatisfied wards due to uneven service delivery - Network and electricity Outage affect production and performance |

Challenges

- Inadequate institutional governance systems

- Limited powers and functions

- Non adherence to service delivery standards and charter

- Inconsistent and inadequate capacity building (councilors,employees and ward committees)

- Inadequate Municipal Business Management Systems(PMS,IT,Record Management System,policies and procedures)

# CHAPTER 4: STRATEGIES PHASE

4.1. KPA 1: Spatial Rationale

Strategic Objective: To ensure effective and sustainable use of land to promote growth and development

| KPA | Development challenge | Objectives | Development Strategies |
| --- | --- | --- | --- |
| Spatial Rationale | Municipality does not own land | - To promote growth and investment - To ensure formalise settlements - to ensure sustainable revenue generation through billing of rates and services | - Develop and implement land acquisition strategy - Identify strategic land for development in accordance with SDF for mixed development - Conduct land audit - Acquire strategic land |
|  | Dispersed settlements, uncoordinated land use | - To promote integrated settlements and compatible land uses - To consolidate dispersed and unsustainable settlement patterns - To ensure connectivity and appropriate movement system | - Develop precinct plans in nodal/growth areas as per the SDF - Develop corridor development plans |
|  | Unresolved land claims | - To promote formal settlement planning | Engagement with Dept. of Rural Development and Land Reform, House of Traditional Leaders, SDM and other relevant stakeholders to expedite land claim resolution and release of strategic land |
|  | Ineffective land use management system | - To support economic development through appropriate land use mechanism and spatial development concept - To ensure formalized and well managed land regularization process | - Implement wall-to-wall Land Use Scheme across the municipal space for efficient and effective land use management - Land Use awareness training / workshop / consultation - Pass and enforce SPLUMA Bylaw - Implementation of building control policies and regulations - Formal settlement planning and site demarcation - Develop appropriate land information management system |
|  | Mushrooming of informal settlements |  |  |
|  | Mushrooming of unregulated business establishment |  |  |
|  | No Bylaws for building control and land development regulation |  |  |
|  | Informal allocation of land by traditional leaders |  |  |

KPA 2: Basic service delivery and infrastructure Development

Strategic Objective: To reduce infrastructure and service backlogs in order to improve quality of life of the community by providing them with roads & storm water, bridges electricity and housing

| KPA | Development challenge | Objective | Development strategies |
| --- | --- | --- | --- |
| Basic service delivery and infrastructure Development | ## Inadequate housing for the needy | - To facilitate the provision of low cost free (RDP) to 6908 beneficiaries by CoGHSTA during 2019/20 to 2021 | - Development of Housing Chapter - Negotiate and monitor implementation of adequate low cost housing unis with CoGHSTA |
|  | ## Shortage of portable water and reliable sources | - To facilitate provision of potable water to 33312 households through SDM engagement during 2019/20 to 2020/21 | - Draw up priority list to SDM and follow up roll out programme and extension of bulk water to new areas - Ensure indigent households are provided with FBW at all times through our engagements with SDM (Implementation of indigent register) |
|  | ## Poor operation and maintenance of water infrastructure | - To facilitate Operation and maintenance | - Highlight to SDM for improved and acceptable turnaround time of maintenance and operation of water infrastructure |
|  | ## Insufficient basic level sanitation services | - To facilitate provision of VIP toilets to 2800 households by SDM during 2019/20,ensure cleaner and hygienic lifestyle | - Engaged SDM for provision of sufficient sanitation units to meet the national targets - Facilitate for construction and upgrading of existing sewerage plants - Facilitate monitoring of sanitation projects |
|  |  |  | - Ensure indigent households are provided with free sanitation at all times through our engagements with SDM(Implementation of indigent register) |
|  | ## Electricity post connection backlog and lack of capacity from feeder lines | - To facilitate provision of electricity post connection to 4565 households by Eskom during 2019/20 to 2020/21,to ensure access to more efficient energy for everyday use | - Engage Eskom in prioritisation of villages in line with IDP’s priority list - Update data on households that need post connections with the possibility of new projects - Provision of electricity to households - Ensure indigent households are provided with FBE through implementation of indigent register - Advocate for provision of solar energy |
|  | ## Gravel impassable roads | - To build,(at all roads,bridges,storm water)infrastructure,150km (at up all roads, bridges and storm water kilometers)new roads and storm water infrastructure and maintain (at up all gravel roads kilometers)of gravel roads, during the 2019 to 2021 period, to improve accessibility - Paving of roads. | - Construction of 150km new roads (of the 255,49km and 76 bridges backlog) and storm water infrastructure (Review and implementation of the road and storm water master plan) - Maintain 200km of gravel roads - Construction and maintenance of municipal roads and bridges - Mobilise resources through engagements with Department of Public Works, Roads and Infrastructure ,SANRAL and RAL for surfacing of District,Provincial and National roads - Advocate maintenance and extension of roads through Department of Public Works, Roads and Infrastructure SANRAL and RAL engagements |
|  | ## Construction of bridges |  |  |
|  | ## Huge storm water drainage backlog |  |  |
|  | ## Lack of parking space for infrastructure plants | To ensure safe parking space for infrastructure plants and equipments. | Engage EDP in possible stands available in municipal jurisdiction. Purchase private land for parking space. |
|  | Turnaround time for maintenance of infrastructure plants | To ensure effective and efficient maintenance of infrastructure plant. | To engage direct service providers (Bell or cat) for maintenance service level agreements. Establish mechanical team in-house. |
|  | Out-dated library material | - To provide the current and relevant library material that shall meet the information needs of our community members. | - Purchasing of new library material |
|  | Lack of access roads | - To ensure accessibility of the library to the community. | - To pave or tar the access roads to the libraries |
|  | Underdeveloped culture of reading in our municipality | - To ensure the transformed, informed and knowledgeable society | - Introduction of library and information services in the remote areas of the Municipality. |
|  | Inaccessibility of Wi-Fi in Jane Furse library Hall | - To ensure to internet access to all library users | - Engagement of the DSAC in the next financial year |
|  | Lack of public transport facilities | - To ensure that there is infrastructure for transport facilities | - Negotiate for adequate transport (buses and taxis) and extension of routes |
|  | Insufficient clinics | - To facilitate provision of clinics | - Lobby for partnership in favour of establishment of clinics |
|  | Inadequate educational facilities and equipments | - To facilitate for provision of educational facilities and equipments | - Engage Dept. of Education for building of schools and general infrastructural provision and equipments at schools within Makhuduthamaga |
|  | Lack of support to ECDs |  | - Lobby for partnership in favour of supporting ECDs |
|  | Inadequate safety and security operations | - To enhance safety and security of the public | - Lobby for partnership in favour of SAPS for construction of additional police stations i.e. engage with Department of Police |
|  | Waste management (informal disposal of waste, maintenance of landfill site, cost recovering, refuse removal not covering all villages) | - To provide sustainable waste management infrastructure | - Provision of sufficient waste management services to meet national target |
|  |  |  | - Maintenance of waste management assets |
|  |  |  | - Expand waste collection |
|  | Lack of environmental bylaws | - To develop environmental bylaws | - Development of environmental by-laws |
|  | Insufficient environmental awareness | - To enforce community about environmental issues | - Development of environmental awareness programs |
|  | Fencing of cemeteries | - To fence and provide sanitary facilities at the cemeteries | - Identify,prioritise and construction of fence and ablution facilities |
|  | Lack of law enforcement facilities | - To establish law enforcement facilities | - Upgrading / expansion of Drivers’License Test Centres /services |
|  | Disaster Management | - To provide relieve to disaster affected households | - Mobilisation of and provision of relief to disaster victims |
|  |  |  | - Educate communities about Disaster management |
|  | Shortage of sector plans (e.g. IWMP, Integrated Transport Plan, Housing Plan, Disaster Management Plan etc.) | - Develop all infrastructure related management plans during 2018/19,to ensure all infrastructure development interventions follow effective,standardised protocols | - Develop / review Environmental Management Plan, Integrated Transport Plan, Disaster Management, Housing Plan etc. |
|  | Poor network (cell phones, TV and radio coverage) | - To facilitate for strengthening of cell phone, TV and radio network coverage | - Lobby SENTECH,ICASA,Cell phone, operations and relevant authorities for strengthening network coverage within Makhuduthamaga - Lobby for Telkom in favour of provision of telephone facilities |

## KPA 3: LED

Strategic Objective: To create and manage an environment that will develop, stimulate and strengthen local economic growth

| KPA | Development Challenge | Objective | Development Strategies |
| --- | --- | --- | --- |
| Local Economic Development | Insufficient support across economic sectors | - To increase support for SMMEs across key economic sectors | - Increase infrastructure support aimed at SMMEs - Promote SMME and Cooperative support through skills development |
|  | Lack of access to markets across economic sectors | - To promote local products and create linkage with markets | - Cooperatives, SMME and enterprise development workshops/training and support - Establishment of fresh produce markets |
|  | Weak agricultural value chain | - To promote agriculture value chain | - Agricultural value chain mapping and promotion - Establishment of abattoir - Promotion of Agro-processing |
|  | Weak manufacturing sector | - To promote local manufacturing | - Promotion of manufacturing in different sectors e.g. furniture, building material, jewellery e.t.c. |
|  | Informal tourism sector | - To promote local tourism | - Promotion of local tourist attractions and destinations - Development of tourism strategy |
|  | Inadequate water availability | - To support local farmers by improving access to water | - Engage SDM and DWA as water authorities to assist SMMEs in agriculture |
|  | Overgrazing and poor grazing practices | - To promote sustainable grazing practices | - Identify specified areas grazing - Create feedlots - Create livestock support programme for emerging farmers |

## KPA 4: Financial Viability and Management

Strategic objective: To provide sound and sustainable management of the financial affairs of Makhuduthamaga Local Municipality.

| KPA | Development Challenges | Objectives | Development Strategies |
| --- | --- | --- | --- |
| Financial viability | Limited revenue base | - To maximally utilize opportunities for revenue generation. | - Allocate resources to increase revenue from the following current sources: traffic functions, licensing function, property rates, renting of council facilities, and sourcing other available grants - Allocate resources to increase revenue generation base on the following potential sources: Waste collection and Landfill operation, Billboards advertisement, Business licensing, Building plans approval, rental of municipal halls, sports fields, hawker’s stalls (investment property), and Vehicle road worthy testing, Vehicle impoundment and discontinuation. - Review and implement Revenue Enhancement Strategies and. |
|  | High grant dependency | - To reduce high grant dependency | - Allocate/deploy resources to strengthen the waste management division and acquire all necessary assets for waste collection and disposal. - Allocate resources and expand the municipal testing grounds and testing station facilities. - Allocate resources and build facilities for the traffic function of the municipality and acquire/maintain all necessary assets. - Set service standards for all services affecting revenue generation and collection and ensure adequate monitoring and reporting. - Implement all approved and gazetted revenue management by-laws. - Review current valuation roll and debt book of the municipality for accuracy and completeness. - Control and approve the erection/construction of all buildings within the targeted municipal nodal points. (Engage local authorities and CoGHSTA). - Engage provincial and National departments to intervene on Government debts. |
|  | Poor collection of property rates billed revenue. | - To collect 95% of the total billed revenue for property rates from customers. | - Review and verify credibility, completeness and reliability of information in the municipal valuation roll. - Conduct consultative engagements with all property owners on the municipal valuation roll. - Allocate resource and monitor the accurate billing and timeous delivery for property rates invoices to property owners. - Council to approve amnesty for long overdue accounts up to the percentage to be agreed with the customers to assist them to afford settling the accounts and keep their accounts up to date. - The property rates customers (local businesses property owners) to sign settlement agreements with the municipality. - Take legal actions (use debt collector) against defaulters who does not cooperate with the municipal arrangements for accounts settlements. – All 60 days overdue accounts. - Review and update the Credit control and debt management policy annually. - Adequately implement the Credit control and debt management policy. - Engage provincial and National departments to intervene on Government debts. |
|  | Inadequate implementation of mSCOA project. | - To ensure all municipal departments understand and operate the mSCOA live systems adequately. - Improved data quality and credibility of reported financial and non-financial information. | - mSCOA steering committee and project implementation team to have meetings quarterly to monitor progress and provide remedial actions for none achievement of targets. - Report mSCOA implementation progress in every management meeting, Executive committee meeting, portfolio committees, audit committee meeting and council meetings. - Report mSCOA implementation progress to Provincial and National Treasury on a monthly basis. |
|  | Material audit findings on municipal Annual Financial Statements. | - To ensure accurate recording of all financial transactions in compliance with applicable GRAP standards. - To ensure adequate management and recording of all municipal assets. - To ensure compliance with SCM regulations and municipal SCM policy. | - Review the Budget and Treasury Office organogram and ensure adequate Human resource to implement the BTO mandate as per the approved IDP. - Fill all vacant BTO positions and regularly capacitate (train) the current staff to grow their knowledge and to be up to date with developments within their financial management career. - Adequately review all financial transaction and segregate duties. - Review, approve and implement the Budget related policies. (Asset management policy, Budget management and virement policy, Revenue management policies, SCM policies and Expenditure management policies.) - All procurement processes to comply with the approved SCM policies and National Treasury SCM regulations, CIDB regulations and MFMA circulars. - Adequately review annual financial statements and internally audit the financial records at least quarterly. |
|  | Poor adherence to municipal procurement plan. | - To ensure effective and efficient procurement system. | - Senior managers must realistically project timelines for annual targets and clearly outline how they will be achieved on a monthly basis and quarterly basis. - Procurement process must be started well in advance as per timelines in the approved municipal SCM policy. (implement forward planning) - Develop and approve a demand management plan. - Capacitate (train) the SCM Bid-Committee members on a regular basis. |
|  | Underspending of approved annual budget | - To adequately implement the approved IDP and annual budget within targeted timeframes. | - Implement procurement plan and report progress on its implementation in every management meeting, executive committee meeting, audit committee meeting and council meeting. |

## 4.5. KPA 5: Good governance and public participation

Strategic objective: To promote good governance, public participation, accountability, transparency, effectiveness and efficiency.

| KPA | Development Challenge | Objective | Development Strategies |
| --- | --- | --- | --- |
| Good governance and public participation | Ineffective functioning of IGR structures | - To Improve functionality of Intergovernmental relations | - Strengthen stakeholders relations at local level ( IGR) |
|  | Inadequate implementation of Internal Audit and Risk Management recommendations and action plans | - To ensure implementation of internal audit and Risk Management action plan | - Strengthening of Internal Audit and Risk Management Structures through capacitation and filling of vacant positions within governance structures (Internal Audit and Risk management) |
|  | Inconsistent coordination of good communication principles and practices within the municipality | - To ensure implementation and monitoring of communication strategy and policy. | - Development of publications. - Media bulk buying to take advantage of the influence of digital communication (Fourth industrial Revolution) |
|  | Non Coordination and adherence to Council Master Plan(Public Participation) | - To ensure proper coordination and implementation | - Review and incorporate National calendar events and public participation activities such as imbizo |
|  | Inadequate stakeholder engagement | - To ensure adequate stakeholder engagement | - Identify and develops stakeholder database |

## KPA 6: Municipal Transformation and Organizational Development

Strategic objective: Improve internal and external operation of the municipality and its stakeholders

| KPA | Development Challenges | Objectives | Development Strategies |
| --- | --- | --- | --- |
| Municipal transformation and organizational development | Inadequate institutional governance systems | - To improve institutional governance and administrative systems - To ensure compliance with all governance and administrative systems - To develop Organisational capacity | - Review and implementation of municipal planning framework, e.g. IDP/Budget - Recruit more qualified competent and skilled personnel - Ensure implementation of PMS - Implement Employment Equity Plan - Implement Human Resource Strategy - Develop and implement Organisational structure - Implement PMS for all Managers - Monitor implementation of retention policy - Implement development projects (1pa) ( discretionary grant) - Implement Municipal Human Resource Policies - Mobilise for empowerment of IGR forums i.e. IDP Representative forum, LED forum etc. |
|  | Limited powers and functions | - To advocate inter-sectoral collaboration of powers and functions commensurate with the capacity of the municipality (MOU & SLA) | - Engage SDM, CoGHSTA and LEDET in sharing some of the feasible powers and functions such as water provisions, maintenance and operations, business licensing |
|  | None compliance with legislative guidelines, directives, policies, SLA/Contracts, by-laws | - To ensure that there is no none compliance with all related municipal legislations including monitoring of all SLA/contracts | - Develop a legal and credible SLA/Contracts - Compile a database of all legislative compliance - Management of litigations - Conduct workshops to enhance compliance - Ensure legal compliance of by-laws and its implementation |
|  | None adherence to Service standards and service delivery charter | - To improve customer care service for better service delivery | - Hold Batho Pele Build up event - Implement Customer Care Service Standards - Implement Customer Care Policy - Implement service delivery charter - Develop Municipal excellent service awards |
|  | None adherence and implementation of Labour relation policy and the code of conduct by managers and employees. | - To ensure compliance with the Labour Relations policy and code conduct. | - Workshop Staff on code of conduct. - Workshop Managers on the implementation of the Labour Relations Policy. - Implement Minimum Service Level Agreement - Implement the SALGA collective Agreement (Limpopo Division) (LLF) |
|  | Inconsistent and inadequate Capacity building (councilors, employees and ward committees) | - Train and develop employees, councilors and ward committee members to ensure adequate capacity exist in the municipality’s human service delivery machinery at all times | - Conduct workshops for all staff members. - Annual Employee training through WSP (Workplace Skills Plan) - Completing of Skills audit questionnaire - Development of PDP’s - Implement Internal Bursary Policy - Councilors training - Ward committees’ training |
|  | Business management systems (PMS,IT,Records management systems, policies and procedures) | - Develop / install municipal business management systems to ensure effective management of all municipal activities at all times | - Performance Management System Cascade PMS to all staff members i.t.o HR Strategy - Adequate implementation of Electronic Records Management System - Implement municipal File Plan - Implement Records Management Policy and Procedure Manual - Implement PAIA |
|  |  |  | - Implement and monitor ICT Strategy - ICT governance (ICT Steering Committee) - ICT Organisational structure - ICT processes (Control Objectives of Information Technology (COBIT) processes) - ICT information (flow, access and security) - ICT application (VIP,ESS,SAGE, service desk) - ICT technology (latest technology) - ICT external influences (ICT risks) - Review policies and develop processes and procedures (all functional areas) i.t.o the approved Policy Development Framework - Staff workshops on business management system elements |

# CHAPTER 5: PROJECTS PHASE

5.1. PROJECTS TO BE IMPLEMENTED BY MAKHUDUTHAMAGA

KPA 1: SPATIAL RATIONALE

Strategic Objective: To ensure effective and sustainable use of land to promote growth and development

| No. | Project | Project location | Measurable Objective | Key Performance Indicator | Source of funding | 2019/20 Annual Target | Budget |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget (R’000’) | 2019/20 (R)‘000’ |  | 2020/21 (R)‘000’ | 2021/22 (R)‘000’ |
| SR01 | Land acquisition | MLM | To secure land for coordinated spatial development | No. of ha acquired . | ES | 200 ha | R1000 | R1000 |  | R0.00 | R0.00 |
|  | Land survey | Ward 28 | To allenate municipal land | No. of ha to be surveyed | ES | 50 ha | R0.00 | R0.00 | R0.00 |  | R0.00 |
| SR02 | Spatial planning (demarcation of sites) | MLM | To promote proper and efficient planning practice. | No. of settlements demarcated | ES | 1 | R3 700 | R 1 000 |  | R1 200 | R1 500 |
| SR03 | GIS implementation and support | Main Office | To ensure functional and effective GIS | No. of GIS software updated | ES | 03 | R300 | R300 |  | R0.00 | R0.00 |
|  |  |  |  | No. of GIS database updated | ES | 01 | R200 | R200 |  | R0.00 | R0.00 |
|  |  |  |  | No. of GIS applications updated | ES | 05 | R100 | R100 |  | R0.00 | R0.00 |
| SR04 | Development of precinct plan at Glen Cowie | Ward 8, 9 and 29. | To promote growth and development in nodal areas. | No. of Precinct plans developed | ES | 01 | R1000 | R1000 |  | R0.00 | R 0.00 |
| SR05 | Implementation of Land Use Management System (LUMS) | MLM | To ensure effective land use management | No. of workshops held. | ES | 4 | R 0.00 | R0.00 |  | R 0.00 | R 0.00 |
|  |  |  |  | No. of LUS approved. | ES | 01 | R1900 | R1900 |  | R0.00 | R0.00 |
|  |  |  |  | No. of SPLUM -bylaws submitted for promulgation | ES | 01 | R0.00 | R0.00 |  | R0.00 | R0.00 |
| SR06 | Development of Building Control By-Law | MLM | To promote proper and efficient enforcement of NBRBS Act on building practices. | No. of building control by-law developed and approved. | ES | 01 | R0.00 | R0.00 |  | R0.00 | R0.00 |

KPA 2: BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT

Strategic Objective: To reduce infrastructure and service backlogs in order to improve quality of life of the community by providing them with roads & storm water, bridges electricity and housing

| N0. | Project | Project location | Measurable Objective | Key Performance Indicator. | Source of Funding | Annual Target 2019/20 | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget (R)‘000’ | 2019/20 (R)‘000’ | 2020/21 (R)‘000’ | 2021/22 (R)‘000’ |
| BS01 | Construction of Makgwabe to Mphane Access Road (10km) – Phase 2 | Ward 29 | To improve accessibility of villages within Makhuduthamaga. | Percentage (%) progress for Construction of Makgwabe to Mphane Access Road (10km) – Phase 2 | MIG | 100% | R11 709 | R11 709 | R0.00 | R0.00 |
| BS02 | Construction of Ga Mampane access road Phase 4 (5 km) | Ward 31 | To improve accessibility of villages within Makhuduthamaga | Percentage (%) progress for Construction of of Ga Mampane access road Phase 4 | MIG | 100% | R23 270 | R 23 270 | R0.00 | R0.00 |
| BS03 | Construction of Marishane and Phaahla Internal Streets (4.2km) | Ward 24,26 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for the Construction of Marishane Phaahla Internal Street | MIG | 100% | R10 000 | R10 000 | R0.00 | R0.00 |
| BS04 | Construction of Matulaneng Access Bridge | Ward 14 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for the Construction of Matulaneng Access Bridge | MIG | 100% | R 2000 | R2000 | R0.00 | R0.00 |
| BS05 | Construction of Stocking internal street (5.3km) | Ward 14 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for the Construction of Stocking internal street (5.3km) | MIG | 100% | R5 069 | R5 069 | R0.00 | R0.00 |
| BS06 | Construction of road from Mashabela Tribal office to Machacha (10km) | Ward 25 | To improve accessibility of villages within Makhuduthamaga | Percentage (%) progress for Construction of road from Mashabela Tribal office to Machacha (5km) | ES | 50% | R37 173 | R6 391 | R17 739 | R13 043 |
| BS07 | Construction of road from Mokwete to Molepane /Ntoane(10km) | Ward 11/07 | To improve accessibility of villages within Makhuduthamaga | Percentage (%) progress for Construction of road from Mokwete to Molepane /Ntoane(5km) | ES | 50% | R 49 782 | R5 000 | R27 391 | R17 391 |
| BS08 | Construction of Rietfontein storm water control | Ward 04 | To sustain the life span of the access road | Percentage (%) progress for Construction of Rietfontein storm water control | ES | 100% | R6000 | R6000 | R0.00 | R0.00 |
| BS09 | Designs of access road from Maila Mapitsane to Magolego Tribal Office(3.6km) | Ward 15 | To improve accessibility within Makhuduthamaga | No of Designs developed for access road from Maila Mapitsane to Magolego Tribal Office(3.6km) | ES | 1 | R19 130 | R870 | R5 217 | R13 043 |
| BS10 | Designs of access road from Glen Cowie Old Post Office to Phokwane (7km) | Ward 8,02,03 | To improve accessibility of villages within Makhuduthamaga | No of Designs developed for access road from Glen Cowie Old Post Office to Phokwane (7km)). | ES | 1 | R5 223 | R 435 | R1 043 | R3 745 |
| BS11 | Designs of access road from Lobethal to Tisane(3.3km) | Ward 24 | To improve accessibility of villages within Makhuduthamaga | No of Designs developed for access road from Lobethal to Tisane(3.3km) | ES | 1 | R11 305 | R435 | R10 870 | R0.00 |
| BS12 | Construction of Seruleng /Marishane Access Bridge | Ward 26 | To improve accessibility of villages within Makhuduthamaga | Percentage (%) progress for Construction of Seruleng/Marishane Access Bridge | ES | 100% | R500 | R500 | R0.00 | R0.00 |
| BS13 | Rehabilitation of access road to Phaahla Tribal office (1.5km) | Ward 24 | To improve condition of access road to Phaahla Tribal Office | Percentage (%) progress for Rehabilitation of access road to Phaahla Tribal office | ES | 100% | R6 087 | R6 087 | R0.00 | R0.00 |
| BS14 | Repair and Maintenance of roads, bridges and storm water | MLM | To improve lifespan of service delivery infrastructure | Percentage (%) progress of expenditure implementation budget for Repair and maintenance of roads, bridges and storm water in terms of (actual expenditure/Total budget x100). | ES | 80% | R52 086 | R21 739 | R17 304 | R13 043 |
| BS15 | Repairs and Maintenance of electricity Infrastructure. | MLM | To improve lifespan of service delivery infrastructure | Percentage (% ) of expenditure budget implementation of Repairs and Maintenance of electricity infrastructure in terms of (actual expenditure/Total budget x100) | ES | 80% | R 6 957 | R2 174 | R 2 609 | R 2 174 |
| BS16 | Repairs and Maintenance for other assets | MLM | To improve lifespan of service delivery assets. | Percentage % of implementation expenditure budget for Repairs and Maintenance for other assets in terms of (actual expenditure/Total budget x100). | ES | 80% | R7 261 | R2 478 | R2 174 | R2 609 |
| BS17 | Job creation projects through Ward based Expanded Public Works Programme /Projects | MLM | To alleviate unemployment and poverty | No of jobs created through EPWP | ES/DPW | 138 | R 5 070 | R2 070 | R1500 | R1500 |
| BS18 | Construction of Mohlala/ Ngwanatshwane access bridge | Ward 21 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for the construction of Mohlala/ Ngwanatshwane access bridge | ES | 100% | R500 | R500 | R0.00 | R0.00 |
| BS19 | Free Basic Electricity | MLM | To improve the lives of indigent households | No of indigent households provided with FBE | ES | 8102 | R14 300 | R4 500 | R4 800 | R5000 |
| BS20 | Fecing of Masemola sports facility and Thusong centre | Ward 28 | To secure municipal land for illegal occupants | No of fencing completed | ES | 2 | R3000 | R3000 | R0.00 | R0.00 |
| BS21 | Partitioning of New Municipal Offices | Ward 18 | To create office space for municipal employees | Percentage (% )progress of partitioning of new municipal offices | ES | 100% | R3000 | R3000 | R0.00 | R0.00 |
| BS22 | Construction of weight bridge at Madibong Land fill site. | Ward 19 | To enhance landfill operations | Percentage (% )progress of construction of weigh bridge at Madibong Land fill site | ES | 100% | R 2 300 | R2 300 | R0.00 | R0.00 |
| BS23 | Construction of Access bridge at Nchabeleng (Thabampshe) | Ward 28 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of bridge at Nchabeleng(Thabampshe) | ES | N/A | R4 347 | R0.00 | R695 | R3 652 |
| BS24 | Construction of Kome Internal Streets(2.5km) | Ward 26 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Kome internal streets | MIG | N/A | R 13 000 | R0.00 | R0.00 | R13 000 |
| BS25 | Construction of Thusong Centre | Ward 28 | To provide One Stop Services Centre to the community | Percentage (%) progress for Construction of Thusong center | MIG | N/A | R 30 000 | R0 | R0 | R30 000 |
| BS26 | Designs and Construction of a Grade A DLTC and VTS at Ga-Masemola | Ward 28 | To improve DLTC and VTS facilities | Percentage (%) progress for Construction of a Grade A DLTC and VTS at Ga-Masemola | ES | N/A | R 14 781 | R0 | R8 695 | R6 086 |
| BS27 | Construction of Setlaboswane Internal Road (1.6km) | Ward 30 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Setlaboswane internal road | ES | N/A | R 7 200 | R0.00 | R0.00 | R7 200 |
| BS28 | Construction of Cabrieve Internal Road (2.6km) | Ward 08 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Cabrieve internal road | ES | N/A | R13 042 | R0.00 | R6 086 | R6 956 |
| BS29 | Construction of access road from Rietfontein to Mare village (3km) | Ward 04,06 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Rietfontein to Mare village | ES | N/A | R 14 000 | R0.00 | R3 500 | R10 500 |
| BS30 | Access road from R579 to Mogorwane via RDP(3.6km) | Ward 10 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from R579 to Mogorwane via RDP | ES | N/A | R 9 000 | R0.00 | R0 | R9 000 |
| BS31 | Construction of access road from Brooklyn to Makoshala(2.5km) | Ward 03,08 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Brooklyn to Makoshala | ES | N/A | R 12 500 | R0.00 | R0 | R12 500 |
| BS32 | Construction of access road and Bridge from Mathousands to Maraganeng | Ward 08 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access bridge from Mathousands to Maraganeng | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS33 | Construction of access bridge from Jane Furse RDP to Comprehensive School | Ward 18 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access bridge from Jane Furse RDP to Comprehensive school | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS34 | Construction of access road from Ga-Kgagara to Moretsele Primary(1.6km) | Ward 12 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Ga-Kgagara to Moretsele Primary | ES | N/A | R 7 826 | R0.00 | R0.00 | R7 826 |
| BS35 | Construction of Access bridge from Makgeru Moshate to Mantime Primary School | Ward 12 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access bridge from Makgeru Moshate to Mantime Primary school | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS36 | Development of Road Master Plan | MLM | Roads management master plan | No. of Road Master plans developed. | ES | N/A | R 0.00 | R0.00 | R0.00 | R0.00 |
| BS37 | Mamone Sekwati-Motlokwe access road | Ward 20 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Mamone Sekwati-Motlokwe access road | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS38 | Access road from Mohlala Mamone-R579 from Jane Furse | Ward 20 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Mohlala Mamone-R575 from Jane Furse | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS39 | Access road from Phaahla Tribal Office-T-Junction at Main Road | Ward 24 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Phaahla Tribal Offfice T Junction at Main road | ES | N/A | R 0.00 | R0.00 | R0.00 | R0.00 |
| BS40 | Access road from Mokgapaneng reservoir-Malegale Cemetery | Ward 03 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road from Mokgapaneng reservoir-Malegale cemetery | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS41 | Talane access road to Ga-Kgari | Ward 25 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Talane access road to Ga-Kgari | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS42 | Mamone clinic-Ngwanatshwane access road | Ward 21 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Mamone clinic-Ngwanatshwane access road | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS43 | Manotong/Setebong bridge | Ward 07 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Manotong/Setebong bridge | ES | N/A | R 2 500 | R0.00 | R0.00 | R2 500 |
| BS44 | Serageng bridge | Ward 30 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Serageng bridge | ES | N/A | R 2 500 | R0.00 | R0.00 | R2 500 |
| BS45 | Mathapisa-Kgarethuthu access road | Ward 26 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of Mathapisa-Kgarethuthu access road | ES | N/A | R 5 000 | R0.00 | R0.00 | R5 000 |
| BS46 | Design and construction of Access road to Manche Masemola Heritage site | Ward 26 | To improve accessibility within Makhuduthamaga | Percentage (%) progress for Construction of access road to Manche Masemola Heritage site | ES | N/A | R0.00 | R0.00 | R0.00 | R 4000 |
| BS47 | Electrification of Vergelegen C (Letlapeng,Jane Furse) | Ward 19 | To improve Access to electric energy for households | No of households electrified | INEP | 30 H/H | R0.00 | R0.00 | R0.00 | R0.00 |
| BS48 | Electrification of Sebitsane | Ward 22 | To improve Access to electric energy for households | No of households electrified | INEP | 30H/H | R0.00 | R0.00 | R0.00 | R0.00 |
| BS49 | Electrification of Matolokwaneng | Ward 22 | To improve Access to electric energy for households | No of households electrified | INEP | 200H/H | R0.00 | R0.00 | R0.00 | R0.00 |
| BS50 | Electrification of Mamone extension phase 1 | Ward 20 | To improve Access to electric energy for households | No of households electrified | INEP | 40H/H | R0.00 | R0.00 | R0.00 | R0.00 |
| BS51 | Electrification of Setlaboswane | Ward 30 | To improve Access to electric energy for households | No of households electrified | INEP | 88H/H | R0.00 | R0.00 | R0.00 | R0.00 |
| BS52 | Solid waste collection | MLM | To promote a healthy and clean environment | No. of H/H solid waste collected | ES | 750H/H | R 15 200 | R2 300 | R5 700 | R7 200 |
| BS53 | Landfill site operations | Ward 19 | To comply with minimum license standards | Percentage (%)of waste received and disposed (total No. of waste received /total No. of disposed) | ES | 100% | R77 400 | R25 800 | R25 800 | R25 800 |
| BS54 | Procurement of skip bins | MLM | To promote a healthy and clean environment | No of skips | ES | N/A | R2 500 | R0.00 | R2500 | R0.00 |
| BS55 | Fencing of cemeteries | MLM | To protect gravestones from wandering animals | No. of cemeteries fenced | ES | 5 | R 2 600 | R 1 000 | R 800 | R800 |
| BS56 | Environmental care | MLM | To promote environmental awareness to communities | No. of environmental awareness and clean-up campaigns held | ES | 4 | R900 | R250 | R300 | R350 |
| BS57 | Library promotions. | MLM | To promote the culture of reading and learning | No.of library awareness campaigns held | ES | 8 | R 480 | R150 | R160 | R170 |
| BS58 | Disaster relief | MLM | To provide relieve to disaster affected H/H | Percentage Disaster relief provided ( disaster cases attended /total number of reported disaster cases) | ES | 100% | R6 250 | R2000 | R2000 | R2 250 |
| BS59 | Disaster awareness | MLM | To educate communities to respond adequately to disaster events | No of disaster awareness campaigns and advisory forums held | ES | 8 | R0.00 | R0.00 | R0.00 | R0.00 |
| BS60 | Sports promotion | MLM | To promote healthy lifestyle and social cohesion | No of sports promotions activities held | ES | 7 | R2 800 | R800 | R900 | R1100 |
| BS61 | Arts and culture promotion | MLM | To promote and sustain cultural heritage | No of arts and culture promotions activities held | ES | 8 | R2 400 | R700 | R800 | R900 |
| BS62 | Traffic Management System | MLM | To enhance law enforcement | No of traffic management system acquired | ES | 1 | R800 | R800 | R0.00 | R0.00 |
| BS63 | Road Traffic safety. | MLM | To promote road safety | No of road safety campaigns held | ES | 4 | R350 | R100 | R120 | R130 |
| BS64 | Purchase of traffic equipments | MLM | To enhance traffic law enforcement and revenue collection | No of traffic equipments purchased | ES | 8 | R1500 | R500 | R1000 | R0.00 |
| BS65 | Development of Integrated Transport Plan | MLM | To develop Integrated Transport Plan for the municipality | No of ITP developed | ES | N/A | R200 | R0.00 | R200 | R0.00 |

KPA 3: LOCAL ECONOMIC DEVELOPMENT (LED)

Strategic Objective: To create and manage an environment that will develop, stimulate and strengthen local economic growth

| No. | Project | Project location | Measurable Objective | Key Performance Indicator | Source of Funding | Annual Target 2019/20 | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget | 2019/20 R‘000’ | 2020/21 R‘000’ | 2021/22 R‘000’ |
| LED01 | LED forums | MLM | To improve access to economic opportunities | No. of LED Forums held. | ES | 4 | R210 | R60 | R70 | R80 |
| LED02 | SMME support | MLM | To promote SMME growth, sustainability and job creation | No. of SMMEs supported No of feasibility studies conducted | ES | 07 01 | R 7500 | R1500 | R3 000 | R3 000 |
| LED03 | Review of tourism guide pack (shago la moeng) | MLM | To promote local tourism | No of tourism guide pack reviewed | ES | 01 | R0.00 | R0.00 | R0.00 | R0.00 |
| LED 04 | Manufacturing industry analysis study | Ward14, 21 | To improve economic productivity in Manufacturing | No. of manufacturing analysis study conducted | ES | 1 | R0.00 | R0.00 | R0.00 | R0.00 |

KPA 4: FINANCIAL VIABILITY

Strategic objective:  To provide sound and sustainable management of the financial affairs of Makhuduthamaga Local Municipality.

| No. | Project | Project location | Measurable Objective | Key Performance Indicators | Source of Funding | Annual Target 2019/20 | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget (R)‘000’ | 2019/20 (R‘000’) | 2020/21 (R‘000’) | 2021/22 (R‘000’) |
| BTO01 | Implementation mSCOA | MLM | To enhance reporting. | No. of mSCOA financial system modules running live. | FMG and ES | 9 | R2 500 | R 1000 | R1000 | R 500 |
| BT0 02 | Revenue management | MLM | To increase own revenue and reduce dependency on grants. | No. of Revenue Enhancement Strategies implemented. | Property rates | 36 | R1 250 | R 500 | R 790 | R 1 500 |
|  |  |  |  | No. of supplementary valuation rolls. | Property rates | 1 | R750 | R 200 | R 250 | R 300 |
|  |  |  |  | No. of customer awareness campaigns conducted. | Property rates | 4 | R950 | R 300 | R 350 | R 400 |
| BTO03 | Own Revenue collection. | MLM | To increase own revenue and reduce dependency on grants | Percentage of billed revenue collected. | Own revenue | 95% | R14 700 | R 1 600 | R 6 000 | R 7 100 |
| BTO04 | Procurement management activities. | MLM | To facilitate effective and efficient implementation of SDBIP. | No. of procurement plans approved. | ES | 1 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
| BTO05 | Financial Management capacity building. | MLM | To enhance human resource competency. | No. of Interns on MFMA programme | FMG | 8 | R3 456 | R 1 152 | R 1 152 | R 1 152 |
|  |  |  |  | No. of trainings attended. | FMG | 5 | R650 | R 200 | R 200 | R 250 |
|  |  |  |  | No. of Financial systems maintained. | FMG | 1 | R1 044 | R 348 | R 348 | R 360 |
| BTO06 | Budget and reporting. | MLM | To ensure Credible and compliant municipal budgeting and reporting. | No. of draft annual budgets tabled. | Not applicable | 1 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
|  |  |  |  | No. Annual budget approved, | Not applicable | 1 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
|  |  |  |  | No. of adjustment budgets approved | Not applicable | 1 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
|  |  |  |  | No. of (IYM) Reports submitted | Not applicable | 12 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
|  |  |  |  | No. of AFS submitted | Not applicable | 1 | R0.00 | R 0.00 | R 0.00 | R 0.00 |
| BTO07 | Expenditure Monitoring activities. | MLM | To ensure authorized expenditure and timeous payment of obligations. | No. of creditors payment period No. of creditors reconciliations report | Own Revenue | 30 days | R0.00 | R 0.0 | R 0.0 | R 0.0 |
|  |  |  |  |  | Own Revenue | 12 | R0.00 | R0.0 | R0.0 | R0.0 |
| BTO08 | Asset management | MLM | To adequately manage all municipal assets. | No of assets verification activities conducted | Own revenue | 8 | R0.00 | R0.0 | R0.0 | R0.0 |
|  |  |  |  | No. of municipal assets repaired or maintained. | ES | 50 | R3 550 | R 900 | R 1 150 | R 1 500 |
|  |  |  |  | No. of furniture purchased | ES | 400 | R4 200 | R 2 500 | R 1 000 | R 700 |
|  |  |  |  | No. of assets insured | ES | 1 704 | R3150 | R 900 | R 1 100 | R 1 150 |
| BTO09 | Unqualified AGSA audit opinion. | MLM | To improve AGSA audit opinion. | AGSA audit report | Own Revenue | Unqualified audit opinion. | R10 930 | R 3 390 | R 3 690 | R 3 850 |

KPA 05: Good governance and public participation

Strategic objective:  To promote good governance, public participation, accountability, transparency, effectiveness and efficiency.

| No. | Project | Project location | Measurable Objective | Key Performance indicators | Source of Funding | Annual Target 2019/20 | Budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget (R‘000’) |  | 2019/20 (R’000) | 2020/21 (R‘000’) | 2021/22 (R‘000’) |  |
| GG01 | Risk managementprogrammes | MLM | To promote an effective Risk Management | No of Risk assessments conducted No. of anti-fraud and corruption awareness activities conducted. No of risk management trainings No of Quarterly Reports submitted to audit committee meetings | ES | 6 1 1 4 | R2 050 |  | R500 | R750 | R800 |  |
| GG02 | Internal Audit | MLM | To ensure the effectiveness of internal controls and governance processes. | No of Risk-based Internal audit reports. No of performance information audit No of professional development training,workshop and forum for internal audit personnel attended Percentage of adhoc audits conducted(No of completed adhoc audits/total No of adhoc audits approved) | ES | 14 04 04 100% | R7 200 |  | R 2 700 | R2 000 | R2 500 |  |
| GG03 | Audit Committee oversight reports. | MLM | To ensure effectiveness of sound financial management | No. of Oversight reports | ES | 04 | R 2 500 |  | R800 | R850 | R 850 |  |
| GG04 | Conduct Bathopele build-up campaign | MLM | To bring services to the communities in collaboration with sector departments | No. of Bathopele build-up campaigns conducted | ES | 1 | R 1 200 |  | R350 | R410 | R 440 |  |
| GG05 | Implement Customer care service standards | MLM | To promote compliance with Bathopele principles. | No. of customer care service standards workshops held | ES | 2 | R 00 |  | R 00 | R 00 | R 00 |  |
|  |  |  |  | No. of Bathopele Committee meetings held | ES | 12 | R 00 |  | R 00 | R 00 | R 00 |  |
|  |  |  |  | No. of Bathopele community awareness campaigns conducted | ES | 4 | R 0.00 |  | R 0.00 | R 0.00 | R0.00 |  |
|  |  |  |  | No of complaints Management reports developed | ES | 12 | R 00 |  | R 00 | R 00 | R 00 |  |
|  |  |  |  | No. of service delivery charter displayed in all municipal buildings | ES | 12 | R200 |  | R50 | R70 | R80 |  |
| GG06 | Display Bathopele service delivery charter |  |  |  |  |  |  |  |  |  |  |  |
| GG07 | Develop Municipal services excellent awards | MLM | To improve staff morale and performance | No. of municipal service excellent award model developed | ES | 1 | R0.00 |  | R0.00 | R60 | R60 |  |
| GG08 | Celebrate Africa service day | MLM | To bring services to the communities in collaboration with sector departments (Khayethu Deployment) | No.of sector departments supported during Africa Service Day Celebration | ES | 1 | R0.00 |  | R0.00 | R0.00 | R 00 |  |
| GG09 | Celebrate Public Service month |  |  | No. of teams deployed to sector departments for support during Public Service Month celebration | ES | 1 | R0.00 |  | R0.00 | R0.00 | R 00 |  |
| GG09 | Multi -media channels | MLM | To enhance public participation in the affairs of the municipality. | No. of sms send No. of radio slots acquired | ES | 60 000 4 | R 2 750 |  | R 800 | R 950 | R1000 |  |
| GG10 | Publications. | MLM | To ensure effective involvement and participation of all stakeholders. | No. of Lentsu Newsletter Booklets published. No. of 2020 Branded Diaries published. No. of 2020 Branded Calenders published. No. of SOMA speech booklets published. No. of Budget speech Booklets published. | ES | 5000 1600 6000 2000 2000 | R 27 350 |  | R 5 650 | R 10 800 | R 10 900 |  |
| GG11 | Branding of municipal assets. | MLM | To profile and promote Makhuduthamaga brand. | No of municipal assets branded. No. of sign boards installed. | ES | 14 16 | R 2 950 |  | R 500 | R 1 150 | R 1 300 |  |
| GG12 | Capacity building of councilors | MLM | To ensure effective and efficient good governance. | No of trainings conducted | Own funding | 5 | R4 210 |  | R 1 300 | R 1 400 | R1 510 |  |
| GG13 | Speaker ‘s Outreach events | MLM | To fulfill public participation and deepening participatory democracy. | No of Speaker’s Outreach events conducted. | Own funding | 5 | R 2 850 |  | R 1 010 | R 1 065 | R 1 123 |  |
| GG14 | Council meetings | MLM | To Fulfill legislative mandate | No of ordinary Council meetings held No. of special council meetings held. | Own funding | 4 8 | R 1 536 |  | R 485 | R 511 | R 540 |  |
| GG15 | Whippery support | MLM | To enhance public participation | No of meetings held | ES | 4 | R333 |  | R105 | R111 | R117 |  |
| GG16 | Mayor Outreach programmes | MLM | To fulfill public participation and deepening democracy | No of outreach events held | ES | 10 | R10 002 |  | R3 159 | R3 331 | R3 512 |  |
| GG17 | Special Programmes | MLM | To enhance public participation for special programmes | No of special programmes conducted | ES | 20 | R |  | R 4 522 | R7 860 | R8 283 |  |
| GG18 | HIV/AIDS awareness campaigns | MLM | To create HIV/Aids awareness to Makhuduthamaga residents | No of HIV/Aids awareness campaigns conducted | ES | 5 | R1 650 |  | R300 | R650 | R700 |  |

KPA 6: MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT

Strategic objective: Improve Internal and External operation of the municipality and its stakeholders

| No. | Project | Project location | Measurable Objective | Key Performance Indicators | Source of Funding | Annual Target 2019/20 | Budget |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MTREF Overall Budget | 2019/20 (R)‘000’ | 2020/21 (R)‘000’ | 2021/22 (R)‘000’ |
| MTOD01 | 2020/21 IDP review activities | MLM | To improve governance and deepen community involvement in the affairs of the municipality | No of IDP process plans approved No of IDP process plan implementation reports No of draft 2020/21 IDP tabled No of 2020/21 IDP approved No of IDP documents printed | ES | 2 12 1 1 2500 | R1800 | R500 | R600 | R700 |
| MTOD02 | Performance Management activities. | MLM | To Improve municipal performance and service delivery. | No. of SDBIPs approved. No. of PMS quarterly reports. No. of Appointed Senior Managers performance agreements signed. No. of Mid -year Performance and Budget implementation reports No. of B2B reports ( Monthly and quarterly No. of Performance Management Frameworks approved. No. of Senior Managers performance assessments conducted. No of annual reports compiled No of oversight reports submitted No. of Annual report documents printed | ES | 2 4 6 1 16 1 2 1 1 2 500 | R2400 | R700 | R800 | R900 |
| MTOD03 | Conduct medical survelliance for employees | MLM | To Ensure health and safety of employees. | No. of Medical surveillance conducted | ES | 2 | R3 641 | R1000 | R 1210 | R1331 |
| MTOD04 | Procure protective equipment (PPE) for employees | MLM | To ensure personal protection in hazardous working environment. | No. of Personnel provided with PPE |  | 20 |  |  |  |  |
| MTOD05 | Conduct health risk assessment | MLM | To ensure safety of employees and clients. | No. of Health risk assessments conducted. |  | 12 |  |  |  |  |
| MTOD06 | Monitor compliance of municipal construction projects in line with OHS Act | MLM | To ensure compliance of municipal construction with Construction regulations | No. of reports generated |  | 12 |  |  |  |  |
| MDOD07 | Coordinate employees wellness events | MLM | To promote a healthy lifestyle for employees. | No. of Employee Wellness events coordinated |  | 04 |  |  |  |  |
| MDOD08 | Promote municipal employees sports | MLM | To promote social interaction and team building of staff members. | No. of sports events conducted |  | 06 |  |  |  |  |
| MTOD09 | Comply with COID Act. | MLM | To ensure compliance with COID Act | No. COIDA reports submitted. | ES | 1 | R 00 | R 700 | R 00 | R 00 |
| MTOD10 | Review and Implement WSP and ATR | MLM | To provide skilled and capable workforce to support service delivery | No. of WSP/ ATR reviewed and implemented and submitted to LGseta | ES | 1 | R3 650 | R 1 300 | R 1 350 | R 1 000 |
|  |  |  |  | No. of training development projects ( discretionary grant) implemented | LGseta | 20 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of Skills audit questionnaire completed. No of orientation and induction programmes conducted | ES/LGSETA | 149 04 | R 00 | R 00 | R 00 | R 00 |
| MTOD011 | Award and manage external bursary fund. | MLM | To provide academic support to needy students for higher education. | No. of students funded. (new intake) | ES | 10 | R 12 700 | R 4 150 | R 4 300 | R 4 500 |
|  |  |  |  | No. of bursary committees appointed | ES | 1 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of bursary committee meetings held | ES | 3 | R 0.00 | R0.00 | R 0.00 | R0.00 |
| MTOD012 | Provide internal bursary to internal staff | MLM | To provide academic support to internal staff | No. of staff members supported with bursaries | ES | 6 | R100 | R100 | R0.00 | R0.00 |
| MTOD013 | Review municipal Organisational structure | MLM | To ensure Organisational structure aligns with IDP service delivery projects | No. of municipal Organisational structure reviewed | ES | 1 | R00 | R 00 | R 00 | R 00 |
| MTOD 14 | Implement Human Resorce policies | MLM | To ensure compliance with the approved HR policies | No of leave reports submitted | ES | 4 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No of recruitments reports submitted | ES | 4 |  |  |  |  |
|  |  |  |  | No of time management reports submitted | ES | 4 | R 00 | R 00 | R 00 | R 00 |
| MTOD15 | Appoint service provider for sign language | MLM | To effectively consult and interact with people living hearing impairment | No of service provider appointed for sign language | ES | 1 | R 00 | R 00 | R 00 | R 00 |
| MTOD16 | Achieve Employment Equity Plan targets | MLM | To promote workplace equity and compliance with EE Act. | No. of quarterly EEP reports submitted | ES | 4 1 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of EEP reports submitted to DoL |  |  |  |  |  |  |
| MTOD17 | Implement Human Resource strategy | MLM | To maintain the right skills and competencies | No. of PMS assessments for all Managers done | ES | 2 | R 00 | R 00 | R 00 | R 00 |
| MTOD18 | Coordinate SAQA verification of all staff members | MLM | To ensure proper placement within municipal Organisational structure | No. of SAQA verification reports done | ES | 160 | R 728 | R 220 | R 242 | R 266 |
| MTOD19 | Hold Local Labour forum meetings | MLM | To ensure sound labour relations and promote workplace harmony | No. of LLF meetings held | ES | 12 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of workshops held (code of conduct) | ES | 2 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of workshops held (LR policy) |  | 2 | R 00 | R 00 | R 00 | R00 |
| MTOD20 | Conduct legal compliance workshop for employees. | MLM | To promote legislative awareness for employees dealing with contracts. | No. of Legal compliance workshops for employees conducted. | ES | 2 | R 00 | R 00 | R 00 | R 00 |
| MTOD21 | Draft municipal contracts | MLM | To regulate the relationship and performance between municipality and service providers. | Percentage (%) of developed SLA / contracts signed | ES | 100% | R 00 | R 00 | R 00 | R 00 |
| MTOD22 | Compile and monitor Legislative compliance database/register | MLM | To ensure proper legal compliance by all departments. | No. of Legal compliance database/ register developed | ES | 1 | R 00 | R 00 | R 00 | R 00 |
| MTOD23 | Conduct Contracts management workshops |  |  | No. of contract management workshops held | ES | 2 | R 00 | R 00 | R 00 | R 00 |
| MTOD24 | Hold Contract management meetings |  |  | No. of contract management /by laws meetings held | ES | 4 | R 00 | R 00 | R 00 | R 00 |
| MTOD25 | Manage municipal litigations cases | MLM | To ensure that the Municipality receives proper legal outcome | % of litigations managed | ES | 100% | R 3 900 | R 1 200 | R 1 300 | R 1 400 |
| MTOD26 | Implement ICT governance programs | MLM | To strengthen ICT governance | No. of ICT steering committee meetings held | ES | 4 | R 00 | R 00 | R 00 | R 00 |
| MTOD27 | Implement ICT Information (intranet) programs | MLM | To improve internal information flow | No. of sites intranet installed | ES | 1 | R 1 810 | R 550 | R 600 | R 660 |
| MTOD28 | Implement ICT processes (COBIT) programs | MLM | To comply with ICT legislations | No. of policies reviewed | ES | 6 | R 00 | R 00 | R 00 | R 00 |
| MTOD29 | Implement ICT applications (ICT assets) programs: Software licensing | MLM | To ensure effective management and usage of municipal ICT systems and infrastructure | No. of software licenses renewed | ES | 8 | R 6 900 | R 2000 | R 2400 | R2 500 |
| MTOD30 | ICT hardware |  |  | No. of hardware assets procured | ES | 25 | R 1000 | R 1 100 | R 1 210 | R 1 331 |
| MTOD31 | ICT technology | MLM | To provide proper information management system | Number of municipal information management systems (APPs) installed | ES | 1 | R0.00 | R0.00 | R0.00 | R0.00 |
| MTOD32 | Install electronic time management system for municipal offices | MLM | To effectively manage hours of work | No. of installations of municipal sites done. | ES | 9 | R1200 | R1200 | R 0.00 | R 0.00 |
| MTOD33 | Implement File Plan | MLM MLM | To improve municipal records management and preserve institutional memory. | No. of workshop conducted | ES | 2 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of records management audits done (all departments) | ES | 2 | R 00 | R 00 | R 00 | R 00 |
|  |  |  |  | No. of records management audits done (Registry) | ES | 4 | R 00 | R 00 | R 00 | R 00 |
| MTOD34 | Implement Records management policy & procedure manual |  |  | No. of records disposals done | ES | 1 | R 00 | R 00 | R 00 | R 00 |
| MTOD35 | Develop municipal master plan | MLM | To improve municipal compliance with national, provincial and local events | No. of Municipal master plan developed | ES | 1 | R 00 | R 00 | R 00 | R 00 |

5.2. PROJECTS TO BE IMPLEMENTED BY SEKHUKHUNE DISTRICT MUNICIPALITY

Infrastructure and Water Services

| Strategy (Approach to achieve objective) | Project | Backlog | Baseline 2018/2019 | Indicators | Annual Target 2019/2020 | Budget 2019-2020 | Budget 2020-2021 | Budget 2021-2022 | Funder /Fund Name |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic objective 1: To reduce water services backlog with 90% by June 2022 |  |  |  |  |  |  |  |  |  |
| RBIG |  |  |  |  |  |  |  |  |  |
| By facilitating the approval of final design by DWS. By appointing the contractor | Makgeru to Schoonoord bulk water supply pipeline | 22877HH | 18.2km of Schoonoord bulk water supply pipeline in Makgeru completed | Number of kilometers of bulk water pipeline constructed | 5 kilometers of bulk water supply pipeline constructed | R15 000 000.00 | R10 000 000.00 | R 0 | RBIG |
|  | Jane Furse to Lobethal BWS pipeline |  | 18 km of bulk water supply pipeline Phase 2 from Jane furse to Lobethal completed | Number of kilometers of bulk water supply pipeline assessed | 18 kilometers of bulk water supply pipeline assessed | R 5 000 000.00 | R50 000 000.00 | R35 000 000.00 | RBIG |
| Strategic objective 2: To achieve 70% blue drop and 50% green drop by June 2022 |  |  |  |  |  |  |  |  |  |
| WATER QUALITY |  |  |  |  |  |  |  |  |  |
| By collecting the samples to accredited laboratory and loading the results into the BDS system | Generation of Water Quality Reports | NA | 12 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | R7 150 000.00 | R 7 614 750.00 | R8 147 782.00 | SDM |
| By collecting the samples to accredited laboratory | Full SANS 241 Water Quality Analysis | NA | 4 Full SANS 241 Analysis reports conducted through accredited laboratory | Number of Full SANS 241 Analysis conducted through accredited laboratory | 4 Full SANS 241 Analysis conducted through accredited laboratory |  |  |  |  |
| By ensuring proper monitoring of usage | Purchase of LAB Chemicals | NA | 90% of LAB chemicals purchased | Percentage of LAB chemical purchased | 100% of LAB chemical purchased |  |  |  |  |
| By collecting the samples to accredited laboratory and loading the results into the BDS system | Plants participation in Blue and Green Drops Certification Programme | NA | 15 Water Treatment Works participating in Blue Drop Certification programme and 15 waste water treatmemt works participated in Green Drop certificate | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 15 WWTW Participating in Green Drop Certification Programme |  |  |  |  |
| Strategic objective 3: To provide 90% of sustainable and reliable basic water and sanitation services to communities by June 2022 |  |  |  |  |  |  |  |  |  |
| O & M EXPENDITURE |  |  |  |  |  |  |  |  |  |
| By purchasing bulk stores materials, decentralisation of stores, monitoring and evaluating the respond time on the incident report. | Sanitation incidents | 10% registered sanitation incidents | 90% registered sanitation incidents | Percentage registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | R 39 487 845 .00 | R42 054 445.00 | R44 964 246.00 | SDM |
| By purchasing bulk stores materials, decentralisation of stores, monitoring and evaluating the respond time on the incident report. | Water incidents | 10% registered water incident s | 90% registered water incidents | Percentage registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days |  |  |  |  |
| By monitoring the services of tankering | Delivery of portable water | No water supply to Jane Furse hospital | Pipeline from Ga Malekane to Jane Furse Reservoir | Kℓof water supply to hospital provided | 25760 Kℓ of water supply by tankering | R17 950 108,30 | R11 116 865,34 | R3 839 461,59 | SDM |
| By purchasing fuel contracted service provider and monitor the supply. | Supply of diesel | 39 000 litres diesel supplied | Diesel driven motor pumps | Number of litres of diesel supplied annually | 39 000 of litres of diesel supplied annually | R1 787 808.00 | R1 884 349.00 | R1 986 104.00 | SDM |
| By purchasing fuel contracted service provider and monitor the supply. | Supply of petrol | NA | 5 000 litres petrol supplied | Number of litres of petrol supplied annually | 1200 of litres of petrol supplied annually |  |  |  |  |
| By purchasing fuel contracted service provider and monitor the supply. | Supply of oil | NA | 1500 litres of oil supplied | Number of litres of oil supplied annually | 720 litres of oil supplied annually |  |  |  |  |
| By purchasing bulk stores materials, decentralisation of stores, monitoring and evaluating the respond time on the incident report. | Mechanical & Electrical Services | 90% registered water incidents | 90% resolved registered M&E incidents within 14 days | Percentage of registered mechanical & electrical incidents resolved within 14 days | 90% registered mechanical & electrical incidents resolved within 14 days | R9 620 000.00 | R10 337 800.00 | R10 944 904.00 | SDM |
| By procuring bulk water meters. By constructing chambers and installing bulk water meters | Installation of Bulk Water Meters | NA | Reservoirs in place | Number of Bulk Meters installed | 8 Bulk Water Meters installed | R5 000 000.00 | R6 000 000.00 | R7 000 000.00 | SDM |
| Strategic objective 1: To reduce water services backlog with 90% by June 2022 |  |  |  |  |  |  |  |  |  |
| PLANNING & REGULATION |  |  |  |  |  |  |  |  |  |
| By management of Water Resources and Capacity Assessment. | Water Conservation and Water Demand Management Plan | No WC/WD M strategy in place | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | R2 000 000.00 | R15 000 000.00 | R30 000 000.00 | SDM |
| By appointment of a Professional Service Provider to develop Sanitation Master Plan | Sanitation Master Plan | Assessment completed | Professional Service Provider appointed in Nov 2016 scoping report and methodology developed. | Number of Sanitation Master Plan developed | One Sanitation Master Plan developed | R2 000 000.00 | R1 000 000.00 |  | SDM |
| By appointment of Professional Service Provider for the planning, design and contract documentation of sewer pump- station upgrade | Groblersdal sewer network | Dilapidated sewer pump station | 15% upgrade of the outfall sewer system took place in 2015/16 financial year | % of sewer pump station upgrade completed | 50% Upgrade of Sewer pump station (2 pumps refurbished, screens upgrading and alarm system) | R2 500 000.00 | R30 000 000.00 | R20 000 000 | SDM |
| Appointment of the professional service provider for the development of feasibility study or the upgrading of Marble Hall bulk sewer. | Development of feasibility study in Marble Hall town for bulk sewer and pump station | Old and under capacity of sewer network | Service provider appointed during 2015/16 FY | Number of feasibility studies conducted | 01 Feasibility Study completed for Marble Hall Sewer line and pump-station | R3 000 000.00 | R10 000 000.00 | R15 000 000 | SDM |
| Appointment of Professional Service Provider for the development of the O & M Plans and system | Conduct Condition Assessment and develop O & M Plans | NA | Terms of Reference developed and incorporated into the asset Management Plan Contract and tender advertised for the PsP appointment | Percentage conduct of condition assessment and O & M Plan developed | 60% conduct of Condition Assessment and O & M Plan developed | R1 500 000.00 | R1 800 000.00 | 0 | SDM |
|  | Conduct Feasibility Studies and develop Technical reports | NA | WSDP, IDP and BWS Master completed in plan 2014 | .Number of Feasibility Studies conducted and technical Reports developed for Lebalelo South Villages Phase 2 | 15 Feasibility Studies conducted and technical Reports. developed for Lebalelo South Villages Phase 2 | R5 000 000.00 | 0 | 0 | SDM |
| Update WSDP and Water Master Plan | Review WSDP and Water Master Plan | Outdated WSDP and Water Master Plan | WSDP and water Master Plan | Number of updated WSDP and Water Master Plan | 1 WSDP and 1 Master Plan Updated | R2 000 000.00 | 0 | 0 | SDM |
| By extension of appointed service provider's contract | Application of bulk water infrastructure servitude | No records of servitudes in SDM | Inception report for Nebo, Mooihoek and Moutse | Number of bulk water infrastructure servitude approved | Three servitude registered | R5 000 000.00 | R10 000 000.00 | R12 000 000.00 | SDM |
|  | Promulgation of Bulk contribution policy | NA |  |  |  | R200 000 |  |  |  |
|  | Review of water and sanitation by-law | NA |  |  |  | R200 000 |  |  |  |
| Strategic objective 1: To reduce water services backlog with 90% by June 2022 |  |  |  |  |  |  |  |  |  |
| WSIG PROJECTS |  |  |  |  |  |  |  |  |  |
| By facilitating the approval of final design by DWS By appointing the contractor | Makgane Interventions | 3195hh | No formal water infrastructure in place | % completion of Makgane water reticulation. (2 Sources completed 30% and reticulation constructed 70%) | 100% completion of Makgane water reticulation. (2 Sources completed 30% and reticulation constructed 70%) | 0 | R7 000 000 | 0 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Mokgapaneng | 254hh | No formal water infrastructure in place. | % completion of Mokgapaneng water reticulation (Sources completed 30% and reticulation constructed 70%) | 100% completion of Mokgapaneng water reticulation (Sources completed 30% and reticulation constructed 70%) | 0 | R4 500 000 | 0 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Phokwane Brooklyn water supply | 378hh | There is bulk supply line from Flag Boshielo without formal reticulation. | % completion of Phokwane Brooklyn water reticulation. (Sources completed 30% and reticulation constructed 70%) | 100% of 2km completion for Phokwane Brooklyn water reticulation | R1 000 000 | R5 600 000 | 0 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor |  |  |  |  | (Sources completed 30% and reticulation constructed 70%) |  |  |  |  |
| By facilitating the approval of final design by DWS By appointing the contractor | Manganeng, Madirane water supply | 895hh | There is distribution reservoir without gravity line. | Kilometers of pipeline constructed | 4km Kilometers of gravity pipeline constructed | R2 000 000 | R4 000 000 | 0 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Nebo Phase 1A testing and commissioning(Jane Furse WC/WD Management) | 6183hh | Nebo Phase1A completed but not commissioned | Number of Kilometers of pipeline commissioned | 33km bulk pipeline tested and commissioned | R15 284 400 | R10 000 000 | R5 000 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Madibong Water Supply | 4564hh | Jane Furse 25Ml completed | Number of water source developed and number of technical reports. | 4 water sources developed and number of technical reports prepared | - | 0 | R10 300 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Flag Boshielo Water Conservation Water Demand Management | 1559hh | The village is fully reticulated supplied water for 24hrs without payment | No of household meters installed | 450 household meters Installed | R10 000 000 | R10 000 000 | R12 612 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Bulk meter installation zonal Discretion | 5754hh | The is existing reticulation network and no pressure to other area | % of pipeline pressure analysed. | 100% pipeline pressure analysed. | 0 | 0 | 5 000 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Moraba water reticulation+C66:K67 | 686hh | The borehole is equipped | Kilometers of pipeline constructed | 1km Kilometers of pipeline constructed | 0 | 0 | R5 000 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Nebo Central | 2346hh | No formal water infrastructure in place. | Kilometers of reticulation constructed | 2km reticulation constructed and 20 kl Storage tanks installed. | 0 | 0 | R6 000 000 | WSIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Construction of Moretsele VDIP | 1300HH | New Infrastructure | Number of VDIP sanitation units constructed | 334 VDIP Sanitation units constructed | R7 500 000 | 5 500 000 | R6 000 000 | WSIG |
| Strategic objective 1: To reduce water services backlog with 90% by June 2022 |  |  |  |  |  |  |  |  |  |
| MIG |  |  |  |  |  |  |  |  |  |
| By facilitating the approval of final design by DWS By appointing the contractor | Makhuduthamaga VIP Backlog Programme (Phase 2,3) - Incl. Malokela, Motsiri, Schoonoord | 64 836 | 15 180 VIP units constructed | No of VIP sanitation units completed | 3000 VIP sanitation units constructed | R12 000 000 | R12 000 000.00 | R12 000 000 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Ga-Mashabela water reticulation supply | 1139hh | 60% of water reticulation constructed | Kilometres of pipeline constructed, number of reservoir completed, number of boreholes completed | 30km of pipeline constructed , 4* Reservoir completed, 7*boreholes completed | R1 000 000 | 0 | 0 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Ga-Marishane water reticulation supply | 1087hh | 30% water reticulation constructed | Kilometres of pipeline constructed, number of reservoir completed | 3.4km of bulk pipeline constructed , 1 reservoir completed and 1 WTW completed | R1 000 000 | 0 | R103 603 287.00 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Ga –Mogashoa (Senkgapudi) and Ga- Mogashoa (Manamane) | 1944h/h | New | kilometres of pipeline completed, number of reservoir completed | New | R60 000 000 | R52 258 853.57 | 0 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 12475h/h | New | Kilometres of pipeline completed and number of reservoirs completed | New | R40 000 000 | R47 946 250.15 | 0 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Sekwati Water Supply phase 5 | TBC | New | Kilometres of pipeline completed | New | 0 | R2 500 000.00 | R63 433 174.00 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Ga-Marishane water reticulation supply - phase 2 | TBC | New | Kilometres of pipeline completed | New | 0 | R8 396 713.00 | 0 | MIG |
| By facilitating the approval of final design by DWS By appointing the contractor | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Phaahla, Molapong, Ga-Magolego, Mankontu and Masehleng | 88612 | New | Kilometres of pipeline completed and number of reservoirs completed | 67km of pipeline constructed, 2 reservoir completed | R1 000 000 | R33 000 000.00 | 0 | MIG |

## 5.3. PROJECTS TO BE IMPLEMENTED BY SECTOR DEPARTMENTS (PROVINCE)

## PROJECTS TO BE IMPLEMENTED BY LEDET IN SEKHUKHUNE DISTRICT IN THE 2019-20 FINANCIAL YEAR

| Name of Project/Programme | Short description | Municipal area where the project is implemented | Amount allocated | Leading unit |
| --- | --- | --- | --- | --- |
| Environmental awareness campaigns. | Conduct Environmental awareness campaigns ( world environment day, world Biodiversity day, world Habitat day, Tree planning and clean up campaigns and World Wetlands day celebrations) | All locals municipalities | R150 000 | Environment Empowerment Services. |
| Environment Legislations Capacity building | Conduct workshops to Traditional Leaders and other stakeholders to increase the level of Environmental Management knowledge and voluntary compliance. | All Local Municipalities | R200 000 | Environment Empowerment Services. |
| Limpopo Green Schools programme | Implementation of Green Projects in the 25 Schools registered to participate in the Green Schools programme. | Selected and registered Schools in all Local Municipalities. | - | Environment Empowerment Services |
| Man and Biosphere Programme. | Support Implementation of Kruger to Canyon Biosphere Reserve | Fetakgomo-Tubaste Municicpality | R270 000 | Environment Empowerment services |
| Green Municipality Competition programme | Assess the Green Economy performance of Municipalities against GMC criteria | All Local Municipalities in Sekhukhune | R100 000 | Environment Empowerment services. |

### DEARTMENT OF EDUCATION

| Project Name | Local Municipality | Education District | Type of Infrastructure | Source of Funding | Scope of Work (Project Details) | Implementing Agent | Total Budget over Multiple Financial Years in '000 | Projected Expenditure 2019/20 in '000 | Projected Expenditure 2020/21 in '000 | Projected Expenditure 2021/22 in '000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mahwetse Secondary | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Construction of 16 ordinary classrooms, Nutrition Centre, Medium Admin block. Refurbish 8 classrooms and fence | IDT | 10000 | 5 000 | 4 500 | 500 |
| Baithuti Mohlahledi Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 2 x Grade R facilities, 8 enviroloos, Nutrition Centre, 1 x Multipurpose classroom. Refurbish 8 classrooms, 8 enviroloos, borehole and fence. Demolish 14 pit toilets. | IDT | 8 250 | 0 | 6 115 | 1 709 |
| Baphadima Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 6 classrooms. Refurbish 3 classrooms. Demolish 3 classrooms | IDT | 12 517 | 626 | 0 | 0 |
| Dihlabaneng Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 4 Grade Facilities and Nutrition Centre | IDT | 5 000 | 0 | 4 750 | 250 |
| Diphale Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Renovate 12 classrooms, demolish pit toilets, relocate mobile classrooms and external work. Conversion of 1 x 3 classroom block into Nutrition Centre | IDT | 6356 | 911 | 0 | 0 |
| Human Resource Capacitation | N/A | All Districts | Non Infrastructure | EIG | Compensation of Employees in the Infrastructure Unit |  | 98633 | 32 856 | 34 663 | 34 663 |
| KATANG PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 12 ordinary enviroloos and 4 Grade R toilets. Demolish 12 plain pit toilets | The Mvula Trust | 1 530 | 0 | 1 453 | 77 |
| KEDIKETSE PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos and 3 Grade R toilets. Demolish 4 plain pit toilets | The Mvula Trust | 1 530 | 0 | 1 453 | 77 |
| Kgaruthutu Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 8 classrooms, 2 Grade R facilities, Nutrition centre, Small Admin block. Upgrade existing fence. Demolish 6 classrooms | IDT | 10 200 | 0 | 0 | 5 000 |
| Kgoogo Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | EIG | Construct 24 enviroloos. Demolish 30 pit toilets | The Mvula Trust | 2 074 | 0 | 0 | 1 969 |
| Kopanong Primary | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Construct 12 ordinary classrooms, 6 x Grade R facilities, Nutrition Centre, Medium Admin block. Demolish 7 classrooms, | LDPWR&I | 15800 | 7 000 | 8 010 | 790 |
| Kopjeng Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 22 enviroloos. Demolish 14 pit toilets | The Mvula Trust | 1 980 | 0 | 0 | 1 881 |
| Lamdzanvho Secondary | Makhuduthamaga | Sekhukhune West | Sanitation / SAFE Initiative | EIG | Construct 12 enviroloos. Demolish 16 pit toilets | The Mvula Trust | 1 080 | 0 | 1 026 | 54 |
| Leduma Mahume (At old Moreku Secondary site) | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Fit the following in 2 x 3 existing classroom blocks: New roofs; New Floors; New Walkways; Window frames; Window panes; New Doors; Level the area in front of the two classrooms | LDPWR&I | 3000 | 2 850 | 150 | 0 |
| Lekentle Secondary | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 24 enviroloos. Demolish 7 pit latrines. Refurbish 1 x 4 seats dilapidated enviroloo toilet block | The Mvula Trust | 1800 | 1 710 | 90 | 0 |
| LEKHINE SECONDARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 10 ordinary enviroloos. Demolish 4 plain pit toilets | The Mvula Trust | 900 | 0 | 0 | 855 |
| Lekoko Secondary | Makhuduthamaga | Sekhukhune | Major Infrastructure | EIG | Construct Nutrition Centre. Refurbish 2 x 3 face-brick classrooms blocks, 3 x 3 and 3 x 2 classroom blocks (plastered)=21 classrooms. Reconfigure 1 x 3 classroom block (right hand side as you enter the gate into Mini Admin block (Principal’s Office, Deputy Principal/HOD's Office, Clerks Office/Reception Area and Staffroom). Reconfigure 1 x 2 classroom block (West) into a Science lab. Reconfigure 1 x 2 classroom block Next to new Mini admin block into Media Centre (Computer and Library) | IDT | 20 000 | 0 | 0 | 0 |
| Mabodibeng Secondary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 8 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| Madikanono Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | EIG | Construct 24 enviroloos. Demolish 20 pit toilets | The Mvula Trust | 2 160 | 0 | 0 | 2 052 |
| Makgatsike Primary (Merging with George Clifford Primary at Magatsike Campus) | Makhuduthamaga | Sekhukhune ED | Water and Sanitation | EIG | Construct 14 enviroloos. Refurbish 12 enviroloos, fence and borehole. Demolish 2 pit toilets. | The Mvula Trust | 3 300 | 0 | 3 135 | 165 |
| Makgatsike Primary (Merging with George Clifford Primary at Magatsike Campus) | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 3 Grade R facilities, Nutrition Centre and Medium Admin block. Refurbish 14 classrooms. | LDPWR&I | 10 000 | 0 | 0 | 5 000 |
| Makgoabe Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Build 1x 2 grade R, renovate 2 x 3 classroom and 1 x 2 classroom block and external services. Provide 3 x 10KL tanks | IDT | 9218 | 460 | 0 | 0 |
| MANGOLWANE SENIOR SECONDARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 10 ordinary enviroloos. Demolish 2 plain pit toilets | The Mvula Trust | 900 | 0 | 0 | 855 |
| MASERALA PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos and 5 Grade R toilets. Demolish 17 pit toilets | The Mvula Trust | 1 710 | 0 | 1 624 | 86 |
| Mashegoanyane Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 20 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| Mashile Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | EIG | Construct 18 enviroloos. Demolish 11 pit toilets | The Mvula Trust | 1 620 | 0 | 1 539 | 81 |
| Mashile Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 2 Grade R facilities, Nutrition Centre, Small Admin block. Refurbish 10 classrooms | LDPWR&I | 8 200 | 0 | 0 | 7 000 |
| Mashwele Primary (new)(Katlegong Vleerschboom) | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 10 classrooms, 2 x Grade R facilities, Small Admin block, Nutrition Centre, 16 Waterborne toilet, Fencing. Drilling and equip borehole. | IDT | 18000 | 6 000 | 8 000 | 3 100 |
| Matobule Special School (Phase 1) | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 10 Classrooms for learners with Special Educational needs with attached toilets, Medium Admin block and Multipurpose School hall to accommodate 250 people. Provide Fencing, Drill and equip borehole. | IDT | 9 388 | 0 | 0 | 5 000 |
| Matshele Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 3 classrooms, New fence. Drill and equip borehole. Renovation of 6 classrooms. Demolish 3 classrooms, 12 pit toilets. | IDT | 7464 | 2 206 | 374 | 0 |
| Mmeshi Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 22 enviroloos. Demolish 17 pit toilets | The Mvula Trust | 1 980 | 0 | 0 | 1 881 |
| Modishane Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Renovate 2 x 3 classroom blocks. Minor renovations of the Admin block donated by POPCRU (especially operationalisation of Waterborne toilets). Construction of New Septic tank. Fit new doors in 1 x 3 classroom block. Seal wall cracks in 1 x 3 classroom block, paster and paint. Seal potholes in 2 x 3 classroom blocks and cover with ceramic tiles. Complete ceiling in 1 x 3 classroom block. Complete new roofing of 1 x 2 Grade R facility. Construction of Grade R toilets (waterborne). Operationalize toilets in Admin block. Fit White boards and pin boards in all classrooms. Pave Assembly area. Construct 4 Covered Carports and 4 uncovered parkin areas. | IDT | 9592 | 4 882 | 480 | 0 |
| MOGALETLWA PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 12 ordinary enviroloos and 4 Grade R toilets. Demolish 13 plain pit toilets | The Mvula Trust | 1 530 | 0 | 1 453 | 77 |
| MOKALAPA PRIMARY SCHOOL | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 12 ordinary enviroloos and 6 Grade R toilets. Demolish 16 plain pit toilets | The Mvula Trust | 1 710 | 0 | 1 624 | 86 |
| Mokgeretli Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Build 10 enviroloos, renovate 5x3 classroom blocks, external works | IDT | 9507 | 478 | 0 | 0 |
| Mokgoshi Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 4 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| Moleshatlou Secondary | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Construct 9 classrooms and Nutrition Centre. Refurbish 12 classrooms and 20 enviroloos and 2 Admin blocks. Demolish 10 classrooms | LDPWR&I | 10700 | 6 000 | 4 165 | 535 |
| Moletjane Primary | Makhuduthamaga | Sekhukhune West | Sanitation / SAFE Initiative | EIG | Construct 20 enviroloos. Demolish 12 pit toilets | The Mvula Trust | 1 800 | 0 | 1 710 | 90 |
| MOLETJANE PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 16 ordinary enviroloos and 4 Grade R toilets. Demolish 8 plain pit toilets | The Mvula Trust | 1 890 | 0 | 1 795 | 95 |
| Molomatau Secondary | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 10 ordinary enviroloos. Demolish 16 plain pit toilets | The Mvula Trust | 900 | 0 | 0 | 855 |
| Molwetsi Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 20 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| Monapenape Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 8 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| MORETSELE PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 15 ordinary enviroloos and 3 Grade R toilets. Demolish 26 plain pit toilets | The Mvula Trust | 1 710 | 0 | 1 624 | 86 |
| Motsatsi Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 4 ordinary classrooms, 1 x Grade R facility, Nutrition Centre and 1 x Multipurpose classroom. Refurbish 6 classrooms. Demolish 4 classrooms. | LDPWR&I | 6 000 | 0 | 0 | 5 700 |
| MOTSEMOGOLO PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 10 ordinary enviroloos and 4 Grade R toilets. Demolish 19 plain pit toilets | The Mvula Trust | 1 260 | 0 | 0 | 1 197 |
| Mpelegeng Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 14 classrooms, 3 x Grade R facility, Nutrition Centre, Medium Admin block and Fence. Refurbish existing borehole. Demolish 12 classrooms. | IDT | 15000 | 6 000 | 8 250 | 750 |
| NKGARI PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 12 ordinary enviroloos and 3 Grade R toilets. Demolish 8 plain pit toilets | The Mvula Trust | 1 260 | 0 | 0 | 1 197 |
| Nkgonyeletse Secondary | Makhuduthamaga | Sekhukhune ED | Sanitation | EIG | Construction of 10 enviroloos. Refurbish 10 enviroloos, Existing borehole and fence. | The Mvula Trust | 2 800 | 0 | 2 660 | 140 |
| Nkgonyeletse Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construction of Medium Admin block, Nutrition Centre. Refurbish 23 classrooms | LDPWR&I | 10 900 | 0 | 0 | 6 000 |
| Nthsebele Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construction of 5 classrooms, Medium Admin block, Nutrition Centre. Refurbish 13 classrooms. | LDPWR&I | 9 250 | 0 | 0 | 6 000 |
| PEBETSE PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 15 ordinary enviroloos and 5 Grade R toilets. Demolish 6 pit toilets | The Mvula Trust | 1 890 | 0 | 1 795 | 95 |
| Ramphelane Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct Nutrition Centre. Refurbish 16 classrooms and existing Admin block | IDT | 20 000 | 0 | 0 | 0 |
| Rantobeng Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct 10 ordinary classrooms, 8 enviroloos, and Nutrition Centre. Refurbish 9 classrooms, Science and Computer laboratories and Library. Upgrade fencing | IDT | 18000 | 6 000 | 8 000 | 3 100 |
| Rebone Secondary | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Construct 10 classrooms, Nutrition Centre, Medium Admin block. Refurbish 16 classrooms, and fence | LDPWR&I | 15800 | 6 000 | 9 010 | 790 |
| Rebone Secondary | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 2 enviroloos. Refurbish 20 enviroloos. | The Mvula Trust | 2560 | 2 432 | 128 | 0 |
| Sebase Secondary | Makhuduthamaga | Sekhukhune West | Major Infrastructure | EIG | Replace the roofs 0f 8 storm damaged classrooms and do general renovations to the classrooms | LDPWR&I | 2500 | 2 375 | 125 | 0 |
| SEBOENG PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 10 ordinary enviroloos and 3 Grade R toilets. Demolish 6 plain pit toilets | The Mvula Trust | 1 170 | 0 | 1 111 | 59 |
| Schoonoord Cluster Circuit Office | Makhuduthamaga | Sekhukhune West | Major Infrastructure | ES | Routine Maintenance of the District Office | LDPWR&I | 784 | 39 | 0 | 0 |
| Sedikwe Primary | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos and 5 Grade R toilets. Demolish 19 pit toilets | The Mvula Trust | 1 710 | 0 | 1 624 | 86 |
| Sekale Primary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Construct Small Nutrition Centre. Refurbish 13 classrooms. Demolish 13 pit toilets | IDT | 6 607 | 0 | 5 572 | 331 |
| Thoto Primary | Makhuduthamaga | Sekhukhune ED | Sanitation | ES | Construct 20 enviroloos. Demolish 12 pit toilets | The Mvula Trust | 1 800 | 0 | 0 | 1 710 |
| TISANA PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos and 4 Grade R toilets. Demolish 14 plain pit toilets | The Mvula Trust | 1 710 | 0 | 1 624 | 86 |
| TSATANE PRIMARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos and 6 Grade R toilets. Demolish 20 plain pit toilets | The Mvula Trust | 1 890 | 0 | 1 795 | 95 |
| TSHEGE SECONDARY | Makhuduthamaga | Sekhukhune West | Sanitation | EIG | Construct 14 ordinary enviroloos. Demolish 4 plain pit toilets | The Mvula Trust | 1 260 | 0 | 0 | 1 197 |
| Tshehlwaneng Secondary | Makhuduthamaga | Sekhukhune ED | Major Infrastructure | EIG | Demolition of 18 classrooms, renovation of 3 classrooms and laboratory building, construction of medium sized admin, construction of 16 toilets. Construction of 15 classrooms | IDT | 30327 | 2 756 | 0 | 0 |

### PUBLIC WORKS

| ITEM | PROJECT DESCRIPTION | LOCATION | DISTRICT | TYPE OF MAINTENANCE | TYE OF FACILITY | BUDGET |
| --- | --- | --- | --- | --- | --- | --- |
|  | Construction of Hoeraroep Cost Centre Office | Nebo | Sekhuhune | New Construction | New Office | R3 000 000 |

| Project name | District | Project description | Contract Amount | Current status (percentage if under construction) | Total no. of jobs created as per beneficiary list, contracts and IDs | Completion date | Forecast completion date | Links to APP 2019/20 | Links to APP 2019/20 | Links to APP 2019/20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Completion within the agreed time | Completion within the agreed budget | Total estimated jobs to be created in 2019/20 |
| Modjadji Traditional Council relocated to Mogashoa Ditlhakeneng | Sekhukhune | Construction of new traditional council office | R 8 613 250.30 | Construction | 38 | 17-Jul-19 | 31-Oct-19 | No | Yes | 15 |

## 5.4 PROJECTS TO BE IMPLEMENTED BY NATIONAL DEPARTMENTS

PROJECTS TO BE IMPLEMENTED BY NATIONAL DEPARTMENT OF ENVIRONMENTAL AFFAIRS IN MAKHUDUTHAMAGA MUNICIPAL AREA

| Name of Project / Programme | Area of implementation | Total Budget | Project Time Frames |
| --- | --- | --- | --- |
| Sekhukhune District Good Green Deeds Programme (eradication of illegal dumping sites) | All municipalities | R9 049 773.73 | 2019-2021 |
| Mogaladi Wetland Rehabilitation Project | Makhuduthamaga (Mogaladi Village) | R1 575 000,00 | 2019/20 |
| Youth Community Outreach Programme | All LMs | R | 2019/20 |

## 5.5. PROJECTS BY PARASTATALS

PROJECTS TO BE IMPLEMENTED BY ESKOM IN MAKHUDUTHAMAGA

| Municipality | Project name | DoE Total Planned CAPEX | Total Planned Connections |
| --- | --- | --- | --- |
| Makhuduthamaga | Makhuduthamaga Malaka Ext | R 786 600.00 | 36 |
| Makhuduthamaga | Phatametsane Ext | R 1 232 307.80 | 46 |
| Makhuduthamaga | Ga-Phaahla | R 917 700.00 | 42 |
| Makhuduthamaga | Molelema Ext | R 1 265 000.00 | 35 |
| Makhuduthamaga | Maololo Malegasane Ext | R 1 549 769.90 | 48 |
| Makhuduthamaga | Sekale/Apel Cross | R 4 383 211.20 | 231 |
| Makhuduthamaga | Ga Phaahla Phorome | R 568 100.00 | 26 |
| Makhuduthamaga | Stocking | 1 332 850.00 | 61 |
| Makhuduthamaga | Maololo Malegasane | R 1 195 038.60 | 48 |

RAL PROJECTS FOR 2018/19 and 2019/20

| Municipality | Project no | Project description | Total amount |
| --- | --- | --- | --- |
| Makhuduthamaga | T539C | Tompi/Seleka to Mogaladi to Phokoane | R234 563 980 |
| Makhuduthamaga | T539 B | Tompi Seleka to Mogaladi | R35 920 000 |
| Makhuduthamaga | T857 | Marulaneng to Maila to Mphanama to Nchabeleng | R316 900 800 |
| Makhuduthamaga | T902 | Ga-Masemola | R |
| Makhuduthamaga | T757A | Marulaneng | R |

| Item | Project No. | Road Number | Project Name | Road - surfaced/gravel/bridges/drainage structures/erosion protection, etc. | Budget programme number | MTEF Forward Estimates (19/20) | MTEF Forward Estimates (20/21) | MTEF Forward Estimates (21/22) | MTEF Forward Estimates (22/23) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | RAL/T857 | D4200 | D4200 Jane Furse to Mphanama to Apel | Drainage structure, Road | Roads Infrastructure | R10 984 574 | R18 141 576 | R39 707 000 | R180 000 000 |
| 3 | RAL/T902 | D4253 | Phase A 3 Km of ((Ga-Masemola (D4253 )) | Drainage structure, Road | Roads Infrastructure | R25 000 000 | R17 858 593 | R7 141 407 | R0 |
| 4 | RAL/T539C(A) | D4370 | Phase A Improvements to increase structural capacity of existing pavement layers by adding new granular layers D4370 Tompi Seleka to Mogaladi to Phokwane | Drainage structure, Road | Roads Infrastructure | R0 | R0 | R63 278 000 | R80 000 000 |
| 20 | RAL/T902(A) | D4253, | Ga-Masemola D4253, Phase A Improvements to increase structural capacity of existing pavement layers by adding new granular layers |  |  |  |  |  |  |
| 23 | RAL/T909(b) | D4190 | Installation of road signs, road markings on roads D4190 & D4250 | Maintenance | Roads Infrastructure | R0 | R0 | R0 | R0 |
| 25 | TBA | Various roads | Household based Routine Road Maintenance | Maintenance | Roads Infrastructure | R0 | R0 | R0 | R0 |

## CHAPTER 6: INTEGRATION PHASE

## 6.1. Spatial rationale

Sector plans

| Sector Plan | A brief description and overview |
| --- | --- |
| Spatial Development Framework (SDF) | The MLM has adopted the SDF in 2007 and reviewed during 2014/15 financial year with the help of the National Department of Rural Development and Land Reform so that it can meet the required standard. An Spatial Development Framework (SDF) is a framework that seeks to guide overall spatial distribution of current and desirable land uses within a municipality in order to give effect to the vision, goals and objectives of the municipal IDP. The aims of a spatial development framework are to promote sustainable functional and integrated human settlements, maximise resource efficiency, and enhance regional identity and unique character of a place The contents of the SDF are guided by the Local Government Municipal Systems Act (no 32 of 2000) and the Local Government: Municipal Planning and Performance Regulations (2001). |
| Land Use Management Scheme (LUMS) | Guided by the SDF, the Land Use Management Scheme (LUMS) was developed and adopted in 2008.The plan is recently under review (2018/19).The main orientation of the scheme is to provide mechanism for the control of land use and ensure that development takes place in a coordinated manner. The LUMS set out to address spatial challenges identified in the analysis phase and inherited from the apartheid legacy. |
| Jane Furse Precinct Plan | The Jane Furse Precinct plan was developed by SDM and also noted by MLM council during the 2009/10 financial year .The focus of the plan was to develop a set of guidelines which can and will be used to direct development within the defined area, the Jane Furse node in particular Vergelegen farm. As the growth point of the MLM and SDM the node is currently not developed in a manner that supports most of the characteristics of an ideal growth point node. The plan undertakes precinct analysis/study of the defined area and highlight catalytic public sector LED projects that are required to contribute to the development of the node. |

## 6.2 Basic service delivery and infrastructure Development

Sector plans

| Sector Plan | A brief description and overview |
| --- | --- |
| Disaster Management Plan | The MLM has developed and adopted Disaster Management Plan during the 2007/8 financial year and reviewed during the 2014/15 financial year with the help of CoGHSTA. The plan is aimed at disaster prevention, mitigation, preparedness, response, recovery and rehabilitation. It also aimed at providing an enabling environment for disaster management in the municipal area- Promote pro active disaster management through risk reduction programmes, promote cooperative relationships between all spheres of government in case of emergency incidences. |
| Housing Plan/Chapter | The Housing Chapter for the municipality was developed during 2008/9 financial year with the assistance of CoGHSTA. The plan will be reviewed in the 2019/20 financial year. There are three kinds of housing programmes which Makhuduthamaga has benefitted. The programme include: Rural Housing, People’s Housing programme and Emergency housing/Disaster Housing. The housing chapter attempts to address the following issues: unblocking housing service delivery constraints, planning challenges, contribution to unblocking land constraints, upgrading of rural settlements and enhancement of the quality of houses constructed under the auspices of local government |
| Water Services Development Plan | During the 2005/6 SDM developed and adopted WSDP for its area of jurisdiction wherein issues on water and sanitation are addressed which included Makhuduthamaga Local Municipality. The plan was reviewed during 2015/16 financial year. |
| Draft ITP plan (Integrated Transport Plan) | The Municipality is recently finalizing the development of the plan and it will be adopted by council during the 2019/20 financial year. |
| Road Master plan | The Municipality developed and adopted Road Master Plan during the 2012/13 financial year and it will be reviewed during the 2019/20 |

## 6.3 Economic and environmental analysis

Sector plans

| Sector Plan | A brief description and overview |
| --- | --- |
| Local Economic Development Strategy | MLM has developed and adopted the LED strategy in 2008/9 financial year and was reviewed in the 2017/18 financial year. This document responds to local economic constraints of the municipality. It describes the role of the municipality in LED which is more of facilitating than being the primary implementer. The aim of the LED strategy is to create an enabling environment for employment opportunities for local residents, reduce constraints to business investments and growth, tackle market failures to make market work better and strengthen the competitiveness of local firms. The strategy is thus aligned to key planning documents cited in the previous sections like LEGDP,NSDP etc. |
| LED Implementation plan | Developed and adopted by council during the 2008/9 financial year and will be reviewed in 2018/19 financial year. The plan outlines how the municipality is going to implement the LED strategy. |
| Draft Tourism Strategy | The Municipality has Draft Tourism Strategy that seeks to provide tourism guidelines within Makhuduthamaga municipal area. Its main purpose is to promote tourism within the Municipality. The Strategy was noted by council and will be adopted in the 2019/20 financial year. |
| Integrated Waste Management Plan | The plan was adopted by MLM council in the 2018/19 financial year. |

## 6.4 Financial viability and Management

Sector plans

| Sector Plans | A brief description and overview |
| --- | --- |
| Revenue Enhancement Strategy | The MLM has adopted the Revenue Enhancement Strategy during 2009/10 financial year and reviewed in 2018/19. The strategy is intended to enhance the revenue base of MLM.The is in alignment with the General Finance Policy. The Municipality has started billing for property rates (only Businesses and sector departments) as from July 2009. |
| Credit Control and Debt Management Policy | The Credit Control and Debt Management Policy of MLM was adopted in May 2012 for application applied in the event of none payment of services. It is adopted in terms of Chapter 5 of the Local Government: Municipal Systems Act to contribute towards development of the local economy and provide acceptable services to the communities. The constitutional mandate of the municipality cannot and will never be realized unless there are payments of services. Noting two categories of residents, those who can afford and those who cannot afford to pay for services, the policy emphasize that payment of services must be according to indigent policy. The plan was reviewed in 2015/2016 financial year. |
| Supply Chain Management Policy | The MLM has adopted the Supply Chain Management Policy during 2008/9 financial year and it was reviewed during 2018/19 financial year. It provides policy guidelines as and when the MLM procure goods or services, disposes goods no longer needed, select contractors to provide assistance in the provision of municipal services. |
| Indigent Policy | The MLM has adopted an Indigent policy during 2008/9 and reviewed during 2017/18 financial year. The policy provides indigent support in so far as municipal services to indigent households. Indigent household means a household income of not more than R3400 (monthly) irrespective of the source of income |
| Banking and Investment Policy | This policy is aimed at gaining optimal return on investment, without incurring undue risks, during those periods when cash revenues are not needed for capital or operational purposes. The policy was reviewed in 2018/19 financial year. |
| Financial Management Plan | The MLM has at the moment the 3 years Financial Plan which addresses the financial challenges highlighted in the analysis phase. The financial priority of the municipality is viability and sustainability. The Financial Plan is aligned to the Medium Term Revenue Expenditure Framework and caters for the income, revenue and expenditure for the year under review as well as two outer years. This plan is under stewardship of the Finance department. |
| Asset Management Policy | The Municipality has approved Asset Management Policy during the 2009/10 financial year. The policy was reviewed during 2015/16 financial year. |
| Tariffs Policy | The Municipality has adopted Tariffs Policy during 2011/12 financial year. The objective of the tariffs policy is to enables the MLM to be self sustainable through tariff income, enables the Council to determine tariffs in line with the applicable legislation. All households with the exception of the indigent should pay the full cost of the services consumed. Municipal tariffs must not be unduly a burden to local business through higher tariffs, as cost affects the sustainability and competitiveness of such business. The plan was reviewed by council in 2017/18 financial year. |
| Budget Policy | The Budget for MLM is guided by the recently developed Budget policy. The policy aims to set budgeting principles which the municipality should follow in preparing each annual budget, in implementing and controlling the budget during the financial year, in adjusting the budget as directed by the MLM.The annual budget is the financial planning document that involves all operating and expenditure decisions. In compiling the budget of the Municipality, National Budget Policy guidelines were considered which include macroeconomic indicators as in the guidelines of the National Treasury, the expenditure trends and revenue patterns. The policy was reviewed in the 2015/16 financial year. |
| Virement policy | The Municipality has recently developed and adopted the Virement policy.(2010/11 financial year).The policy was reviewed during 2015/16 financial year. |

## 6.5 Good governance and public participation

Sector plans

| Sector Plan | A brief description and overview |
| --- | --- |
| Communication Strategy | The Municipality has adopted the Communication Strategy in 2015/16 and reviewed in 2018/19 which aims at making communication between the MLM and its residents more effective. The strategy sets out communication channels the municipality should explore with its citizens. |
| Internal Audit Charter | The MLM adopted the Internal Audit Charter in 2016/17 and reviewed in 2018/19 in order to bring about systematic, disciplined approach in evaluating and improving effectiveness of the risk management, control and governance. It clarifies various issues including the work of the internal audit and responsibilities of the MLM‘s Audit Committee which is established in terms of the Municipal Finance Management Act. It is therefore branded as a tool governing the internal audit unit within MLM. |
| Disability Framework for Local Government | Developed by SALGA in partnership with COGHSTA, the MLM approved the Disability Framework for Local Government which aim at guiding municipalities among others to : (1) mainstreaming disability into the Key Performance Areas of local government ‘s IDPs,PGDS, (2) ensure the participation of people with disabilities in governance and democratic processes, (3) develop and implement programmes to empower people with disabilities, and (4) heighten the implementation of the Integrated National Disability Strategy in local government. |
| Policy on Ward committees | This policy regulates the management and functioning of the Ward committees in the municipality. It enables the MLM to have effective Ward committee system that promotes participatory democracy. The policy clarifies the role of ward committee at length, criteria for membership, election processes, term of office, and filling of vacancies, ward committees meetings, municipal support, accountability and relationships. Consequently, ward committees play substantial role in soliciting community views on service delivery and ensure that community views are encapsulated in the IDP /Budget. |
| Makhuduthamaga Youth Development Policy Framework | The MLM‘s Youth Development Policy was approved by council with the overall aim to improve contact between the municipality and youth. |
| Anti Corruption Strategy | MLM has a Draft Anti Corruption Strategy that seeks to protect the Municipal funds and other assets. The strategy was reviewed during the 2016/17 financial year. |
| Risk Management Strategy | The Municipality has a Risk Management Strategy and was reviewed by council in 2016/17 financial year. This outline a high level plan on how the institution will go about implementing the Risk Management Policy. This will enable Heads of departments to manage risk effectively, optimize operational efficiency of the MLM, develop and support knowledge base of the people and the Council and ensure that adequate risk financing is available by provision in both the IDP and multi year budget. |
| Risk Management Policy | The risk management policy outlines MLM commitment to protect MLM against adverse outcomes, which may impact negatively on service delivery.The policy was reviewed by council in 2016/17 financial year. |

## 6.6 Municipal Transformation and Organizational Development

Sector plans

| Sector Plan | A brief description and overview |
| --- | --- |
| Performance Management Strategy | The MLM has adopted the Performance Management Strategy during the 2010/11 financial year and reviewed in 2015/16 to ensure the achievement of individual objectives which are linked to departmental objectives, which in turn are linked to the organizational performance objectives.Performanec management is an ongoing process, not a once year event of conducting a performance review.PMS is aimed at creating a motivating climate for employees and the organization to develop and achieve high standard of performance. It further empowers the MLM to develop set targets, monitor and review performance based on the Integrated Development Plan –linked indicators and report on the performance against the set indicators. |
| Municipal Institutional Plan | The MLM has the Institutional Plan which addresses institutional challenges highlighted in the analysis phase. The primary objective of an institutional plan is to ensure that consistent and integrated measures are put in place for institutional development. The secondary objectives include providing for Gender Equity and appropriate transformation in the light of the Constitution of the Republic Of South Africa and Employment Equity Act, No 55 of 1998 of as well as reviewing the institutional arrangements and implications of planning process in keeping with the IDP. The plan has a consolidated summary of the institutional activities that flow from the prioritized proposals developed in the IDP processes. The institutional plan is required to result in the following outputs: (a) It must address the gender and equity imbalances facing the municipality, (b) A realistic institutional plan given the financial resources at the disposal of the municipality. It is annually reviewed. |
| Workplace Skills Plan | Makhuduthamaga Local Municipality develops and implements the workplace skill plan every financial year .The plan is develop in consultation with the staff members, committees and councilors. Individuals from the mentioned stakeholders complete questionnaire that serve as tools to identify training needs. The training needs are further consolidated into the workplace skills plan and submitted to LG SETA after approval by the council .This should be able to serve as an intervention in addressing the issues of scarce skills. |
| MLM File Plan | The plan was developed and adopted during 2009/10 financial year and it was reviewed in the 2015/16 financial year by council |

ANNEXURE A: DRAFT BUDGET SUMMARY 2019-2021-22

Consolidated Overview of the 2019/20 MTREF

The municipality has budgeted a total Revenue of R 427 million for 2019/20 financial year, R 452 million and R 483 million for 2020/21 and 2021/22 respectively. Total revenue has increased by R 21 million for the 2019/20 financial year when compared to the 2018/19 adjusted revenue budget. For the two outer years, total revenue will increase by 6 per cent and 7 per cent respectively, equating to a total revenue growth of                   R 77 million over the MTREF when compared to the 2018/19 financial year. The total revenue for 2019/20 includes the grants allocations from the national treasury to the amount of R 334 million and own revenue sources to the amount of R 93 million. For the two outer years of the MTREF 2020/21 and 2021/22 total grants allocations included in total revenue amounts to R 354 million and R 380 million respectively while own revenue decreases to R 98 million and R 103 million respectively.

The following bar chart indicates, the revenue growth level of the municipality for the 2019/20 MTREF including the comparison to the past three years:

Total operating expenditure for the 2019/20 financial year has been appropriated at R 342 million and translates into an operating budgeted surplus of R 84 million as indicated in table A4. This surplus is used to fund capital expenditure for 2019/20 as indicated in table 1 above. When compared to the 2018/19 adjusted revenue budget R 14 million by 2020/21. The operating surplus for the two outer years decreases to R 95 million for 2020/21 and increases to R 107 million in 2021/22 financial year.  These surpluses will be used to fund capital projects for two outer years.

The capital budget for 2019/20 financial year amounts to R 83 million and has decreased by 18 per cent as compared to the 2018/19 adjusted capital budget of R 102 million.  For 2020/21 and 2021/22 budget years, the capital expenditure is budgeted at R 95 million and R 107 million respectively. This reflects a further decrease in our capital expenditure due to poor revenue generation and collection by the municipality. The municipality’s revenue enhancements strategies programme is aiming at amongst other things to address this reduction in capital expenditure in the future budget years.

Operating Revenue Framework

The need to generate sustainable revenue is essential to meet funding requirements for Makhuduthamaga local municipality to continue improving the quality of services provided to its communities and to address the service delivery backlogs.  In these tough economic times strong revenue management is fundamental to the financial sustainability of every municipality.  The reality is that we are faced with development backlogs and high level of unemployment, inadequate town planning, and many other socio-economic challenges in our municipality which directly affects negatively the municipality’s revenue generation and collection.

The expenditure required to address these challenges will always exceed available funding; hence difficult choices have to be made in relation to balance expenditures against realistically anticipated revenues. The municipal property rates tariffs remain unchanged at 0.015 cents in a rand due to a material increase in the values of properties as per the new valuation roll for 2016 to 2021. Council will continue with programmes and steps that will ensure an improvement in community cooperation and improved collection on property rates as it is a major source of the municipality’s own revenue. The municipality currently bill property rates on business properties and government properties only, due to the council resolution that was taken to exclude households pending certain processes to be completed.

In an attempt to ensure a strong revenue base, the municipality has also reviewed its revenue enhancement strategy to improve revenue collection in the 2019/20 financial year and the two outer years.

The municipality’s revenue strategy is built around the following key components:

- National Treasury’s guidelines and macroeconomic policy;

- Efficient revenue management, which aims to ensure a 95 per cent annual collection rate for property rates and other key service charges;

- Determining the tariff escalation rate by establishing/calculating the revenue requirement of each service;

- The municipality’s Property Rates Policy approved in terms of the Municipal Property Rates Act, 2004 (Act 6 of 2004) (MPRA);

- Increase ability to extend new services and recover costs; (e.g. Waste collection project, business licensing)

- The municipality’s Indigent Policy and rendering of free basic services; and

- Tariff policies of the Municipality.

- The township establishment in Jane Furse as the primary note for development.

The following table is a summary of the 2019/20 MTREF (classified by main revenue source)

Table 1  Summary of revenue classified by main revenue source

In line with the formats prescribed by the Municipal Budget and Reporting Regulations, capital transfers and contributions are excluded from the operating statement, as inclusion of these revenue sources would distort the calculation of the operating surplus/deficit.

The total revenue for the municipality excluding capital transfers amount to R 365 million for 2019/20,R 387 million for 2020/21 and R 413 million for 2021/22. The total amount for operational grants to be received for 2019/20 is R 272 million. For the two outer years the total operational grants to be received amounts to R 288 million and R 2310 million for 2020/21 and 2021/22 financial years respectively.

Revenue from government grants forms a significant percentage of the total operating revenue for the municipality for all of the 2019/20 MTREF. This clearly indicate that our municipality  is dependent on government grants which contribute  75 per cent of the total operating revenue in 2019/20 budget year and 74 percent in 2020/21 and 75 in 2021/22.

Revenue generated from property rates amount to R 43 million and the projected interest on property rates overdue accounts amounts to R 35 million. The projected interests were calculated considering the current long outstanding accounts in the municipality’s debtor’s book.  The total projected revenue from property rates when including the interests on overdue accounts amounts to R 78 million which is 80 per cent of the total own revenue budget for 2019/20.

The revenue from Property rates is budgeted to remain at R 43 million throughout the 2019/20 financial year.

Revenue from Licenses and permits amount to R 6.5 million for 2019/20 budget year, R 7 million and R 7 million for 2020/21 and 2021/22 financial years respectively. The municipality is currently awaiting approval from the national department of transport to have the eNatis system operating from the municipal head office to accelerate the collection of revenue through the traffic licenses.

Other revenue consists of various items such as income received for selling tender documents, charges for suppliers database registration and other allocations from LG SITA for skills development. Refer to table SA1 under 2.14 (Other supporting documents) for more details.

The following graph indicates the total operational revenue per source and the percentage of each source to the total operational revenue of R 365 million for 2019/20 financial year:

Revenue per source graph

Operating Expenditure Framework

The municipality’s expenditure framework for the 2019/20 budget and MTREF is informed by the following:

- The municipality’s Spatial Development Framework.

- The infrastructure projects plan in the IDP to address the backlog and the repairs and maintenance plan;

- Balanced budget constraint (operating expenditure should not exceed operating revenue) unless there are existing uncommitted cash-backed reserves to fund any deficit;

- Funding of the budget over the medium-term as informed by Section 18 and 19 of the MFMA;

- The capital programme is aligned to backlog eradication plan;

- Operational gains/ surpluses will be directed to funding the capital budget.

- Funding was allocated to only projects which have projects implementation plans to guard against under spending.

- The Demand management plan and procurement plan of the municipality.

The following table is a high level summary of the operating annual budget for 2019/20 and MTREF (classified per main type of operating expenditure):

Table 5 Summary of operating expenditure by standard classification item

Employee Related Costs

The budget allocation for employee related costs for the 2019/20 financial year is R 86 million, which equals to 25 per cent of the total operating expenditure.

The total budget employee related costs has increased from R 74 million in 2018/19 adjusted budget to R 86 million in 2019/20 which reflect a 16 per cent increase. This is as a result of the inclusion of the vacant positions which couldn’t be filled during the 201/18 financial year together with other new vacant positions which are budgeted to be filled in the 2019 financial year.

As part of the municipality’s cost reprioritization and cash management strategy to make enough funds available to fund capital projects, non-critical vacancies on the municipal structure were not funded.  In addition, expenditure for overtime was only budgeted for the municipal drivers, political offices personnel and traffic officers for emergencies and strict measures has been put in place to ensure that it is not abused considering the cost containment measures as per MFMA circular number 82.

The following vacant positions are budgeted to be filled in the 2019/20 financial year.

| Position Name | Department | Position level |
| --- | --- | --- |
| Deputy Senior Manager: Executive Support | Executive Support | Middle management |
| Council Secretary | Executive Support | Middle Management |
| Chauffer : Mayor’s Office | Executive Support | Lower level management |
| VIP Officers X 2 | Executive Support | Lower level management |
| Secretary: Chief Whip | Executive Support | Lower level management |
| Secretary: MPAC | Executive Support | Lower level management |
| HRM Manager | Corporate Services | Middle Management |
| HRM Officer | Corporate services | Lower level management |
| Personal Assistant: MM’s Office | MM’s Office | Lower level management |
| Deputy CFO | Budget & Treasury | Middle management |
| Environmental Manager X 1 | Community services | Middle management |
| Waste Management Office | Community services | Lower level management |
| Personal Assistant | Community services | Lower Level management |
| Library assistant X 2 | Community services | Lower Level management |
| General workers X 4 | Community services | Lower management level |
| General workers X 4 | Infrastructure Development | Lower management level |
| Landfill operator X 2 | Community services | Lower management level |
| Compactor Driver X 1 | Community services | Lower management level |
| Manager | LED | Middle management |
| Senior Manager: Infrastructure | Infrastructure | Senior Management |
| PMU Technician | Infrastructure | Lower level management |
| Plant Operator X 1 | Infrastructure | Lower level management |

Remuneration of Councilors

The cost associated with the remuneration of councilors is determined by the Minister of Co-operative Governance and Traditional Affairs in accordance with the Remuneration of Public Office Bearers Act, 1998 (Act 20 of 1998).  The total budget for councilor allowances is R 24 million for 2019/20, R 26 million and  R 27 million for 2020/21 and 2021/22 respectively. An increase was projected at 7 per cent for 2019/20 and 7 percent for 2020/21 and 2021/22 on the upper limits for councilors.

Debt Impairment

The provision of debt impairment for 2019/20 was determined based on the Debt Write-off Policy of the municipality. For the 2019/20 financial year this amount equates to R 35 million, increases to R 38 million in 2021/21 and decreases to R 39 million in 2021/22 respectively.  This expenditure is projected for property rates debtors and is considered to be a non-cash flow item. This item is not cash funded as there is no service rendered that is associated with the billed debt and therefore no costs associated with rendering the services were determined, to require cash funding. Revenue generated from Property rates is used to fund this expenditure item to avoid cash flow problems that may arise when customers does not pay. For example, the expenditure for Debt recovery is funded through property rates as a percentage of the amount collected, which means, when there is no collection no expenditure will be incurred.

Depreciation

Provision for depreciation and asset impairment has been informed by the Municipality’s Asset Management Policy and GRAP 17. The projections were made taking into consideration the municipality’s assets value as recorded in the 2017/18 AFS and new acquisitions for the current year 2018/19 and 2019/20 budget year and the MTREF. Budget appropriations in this regard are R 27 million for the 2019/20 financial year and equates to 8 per cent of the total operating expenditure.  It increases to R 31 million and 36 million for 2020/21 and 2021/22 budget years respectively.

Contracted Services

Contracted services comprises of security services, cleaning services, repairs and maintenance for infrastructure assets and operating leases for office equipment and machinery and maintenance of the landfill side. The budget on contracted service is R 104 million for the 2019/20 financial year, it decreases to R 102 million and R 103 million in the 2020/21 and 2021/22 outer years.

Repairs and maintenance has been budgeted at 18% percent of the total operational budget and 21 per cent of the Asset value as per 2017/18 AFS taking in to consideration guidelines contained in MFMA circular number 66, 67, 70, 72, 74 ,75, 78, 79, 85, 86, 89,91,93 & 94.

Other Expenditure

The municipality has also budgeted an amount of R 64 million on other general expenditure items for the 2019/20 financial year. The budget for the 2020/21 & 2021/22 is R 66 million & R 70 million for the general expenditure.

Furthermore, in compliance to the cost containment measures as approved by the cabinet, the municipality has reduced spending on excessive advertising, travelling, caterings, promotional materials and mandates that belong to other spheres of government for 2019/20 MTREF. For further details on other expenditure refer to table SA1.

The following bar chart gives a breakdown of the main expenditure categories for the 2019/20 financial year.

Table 6 Main Operational Expenditure categories for 2019/20 financial year

Priority given to repairs and maintenance

Considering National Treasury MFMA circular number 54, 55, 58, 59, 66, 67, 70, 72, 74, 75, 78, 79, 85, 86, 89, 91, 93 & 94 the municipality has put repairs and maintenance as one of the priorities to preserve and maintain the municipality’s current infrastructure, to ensure that the existing assets are in good working conditions and to lengthen the assets life span.  In terms of the Municipal Budget and Reporting Regulations, operational repairs and maintenance is not considered a direct expenditure driver but an outcome of certain other expenditures, such as remuneration, purchases of materials and contracted services.  In the municipality’s case, all repairs and maintenance services for the infrastructure assets will be done through contracted services as indicated in table SA1 of the A schedule. The repairs and maintenance budget for 2019/20 amount to R 62 million, R 59 million and R 57 million for 2020/21 and 2021/22 respectively.

Repairs and maintenance expenditure budget amounts to 18 per cent of the municipality‘s budgeted operational expenditure for 2019/20. For the two outer years, repairs and maintenance is budgeted at 17 per cent and 15 per cent of the budgeted operational expenditure respectively.

Free Basic Services: Electricity tokens

The municipality provides free basic electricity tokens to poor households within the municipal jurisdictions to assist them as they cannot afford the electricity costs. Our municipality does not have a licence to provide electricity and therefore buys the tokens from Eskom for the affected households who registered with the municipality.  To receive these free services the households are required to register in terms of the municipality’s Indigent Policy.  Details relating to free services, cost of free basic services, revenue lost owing to free basic services as well as basic service delivery measurement is contained in Table  MBRR Table A10 (Basic Service Delivery Measurement)

The cost of the free basic electricity of the registered indigent households is financed through the local government equitable share received in terms of the annual Division of Revenue Act and it has been allocated at R 4.5 million for 2019/20, R 4.8 million and R 5 million for 2020/21 and 2021/22 respectively.

Table 2  2019/20 Medium-term capital budget per vote

New and Existing Capital Assets

For 2019/20 an amount of R 83.9 million has been appropriated for the new capital expenditure which will be funded by MIG to the amount of R 62 million and equitable share & VAT refunds to the amount of R 22 million. For 2020/21 and 2021/22 the budget has been appropriated at R 95.5 million and R 107.5 million respectively.

Infrastructure and Development vote is appropriated the highest allocation of R 77.9 million which equates to 93 per cent of the total capital budget for 2019/20 to build roads and bridges, Budget and Treasury is allocated 5 per cent of the total capital budget.  The remaining 2 per cent is allocated to Corporate Services.

Below are the capital projects which form part of the total budgeted capital expenditure for 2019/20 MTREF:

Makgwabe Mphane access road 10km 2019/20 (MIG) – R 8.8 million.

Mashabela Machacha access road 10km 2019/20 (MIG) – R 21 million.

Marishane Phaahla Internal Streets 4.2km 2019/20 (MES) - R 1.2 million.

Matulaneng access bridge 2019/20 (ES) – R 3.6 million.

Lobethal/Tisane access road 3.3km 2019/20 (ES) – R 435 thousand.

Mokwete/Molepane access road 10km 2019/20 (MIG) – R 17.4 million.

Glen Cowie/Old Post Office access road 7km 2019/20 (MIG) – R 435 thousand.

Seruteng/Marishane access bridge 2018/19 (ES) – R 435 thousands.

Maila Mapitsane/Magolego 3.6km Tribal Office 2018/19 (ES) – R 870 thousand.

Phaahla access road 1.5km 2018/19 (ES) – R 6.1 million.

Ga-Mampane access road 5km 2018/19 (MIG) – R 8.8 million.

Stocking Internal Streets 5.3km 2018/19 (ES) – R 8.8 million.

Table 6: 2019/20 MTREF cash backed reserves/accumulated surplus reconciliation

Table 8: 2019/20 MTREF

ANNEXURE B: ORGANISATIONAL STRUCTURE